## Slide 1: Security Hardening Assessment Program
EXECUTIVE BRIEFING
Charter and 12-week roadmap · start date to be confirmed
CISO steering group briefing
Confidential
Notes: Purpose of this briefing: approve the charter and the 12-week plan, and make the six start-up decisions on slide 13. The program assesses and recommends; owning teams implement.

## Slide 2: In 12 weeks we will know what to harden, in what order, and where our tested controls stand against every standard
01 · EXECUTIVE SUMMARY
The situation
AWS, Entra ID / B2C and multi-chain estate; current posture is unknown
High-value targets: signing keys, admin multisigs, customer withdrawals
Overlapping standards (NIST, ISO, SOC 2, CIS, BSSC); PCI, DORA, MiCA, NYDFS pending Legal review
Our approach
Threat-led: attack paths to the crown jewels first, at full depth
Test once, map to every standard through one crosswalk
Assess and recommend only; owners implement after handover
What we need
Approval of the charter and the 12-week plan
Five named workstream leads and read-only access in week 0
Answers on sizing, regulatory scope and the CI/CD platform
TODAY’S ASK
Approve the charter and make the six start-up decisions on slide 13
Security Hardening Assessment Program
2
Notes: One-minute version. The plan fits 12 weeks by focusing depth: Tier 1 and Tier 2 in full, Tier 3 by automated checks, and a crosswalk of every tested control; the full-catalogue crosswalk is a follow-on. The estate spans AWS, Microsoft identity and three blockchain stacks, and nobody has a current, evidence-based picture of its posture. The program is threat-led, maps every test to every standard once, and stops at recommendations. The asks are on slide 13.

## Slide 3: The program defines what to fix, why, to which standard, in what order, and how each fix is verified
02 · PURPOSE AND OBJECTIVES
PURPOSE
Assess the security of OS, containers, cloud, network, data, applications, identity, detection and blockchain, and deliver prioritized, verifiable hardening recommendations.
We assess and recommend. Owning teams implement.
01
Govern and focus. Governance, inventory, crown jewels and 6–8 attack scenarios by week 2
02
Cross-check standards. Every tested control mapped to CSF 2.0, 800-53, ISO 27001, SOC 2, CIS, BSSC, PCI and regulation
03
Assess. Crown-jewel attack paths first; every test evidence-backed and run once
04
Validate. Rated by attack-path proximity; fact-checked with system owners
05
Recommend. Testable baselines with owner, effort, priority and a verification test
06
Sequence. Now / Next / Later roadmap and the remediation governance that follows
07
Hand over. A unified findings and control register, owned by GRC
Security Hardening Assessment Program
3
Notes: The program’s output is decisions, not changes: for every weakness, what to fix, why, against which standard, in what order and how to verify it. Objectives 1 and 2 are front-loaded so the rest of the program is focused and mapped from week 2.

## Slide 4: Scope covers every AWS account, both identity planes and every on-chain application
03 · SCOPE
Cloud and platform
Organizations, Control Tower
EC2 on Amazon Linux 2023, EKS, ECR
VPC, TGW, Firewall, WAF
S3, EBS, EFS, Aurora, OpenSearch
KMS, Secrets Manager, Backup
CloudTrail, GuardDuty, Splunk
Identity
Entra ID (workforce)
Azure AD B2C (customers)
IAM Identity Center and IAM
Workload identity: IRSA, Pod Identity, CI OIDC
Privileged engineer workstations
Apps and DevSecOps
Tier 1 web apps and APIs
B2C login-to-withdrawal path
CI/CD, IaC and deploy paths
dApp front end, DNS and registrar
Blockchain
Solidity on Ethereum and Base
Solana programs (Rust)
Daml on Canton Network
Vault signing, multisigs, signer devices
Alchemy and Blockdaemon nodes, oracles
Third parties in scope
AWS, Microsoft, Alchemy, Blockdaemon, CrowdStrike, Splunk, HashiCorp, the CI/CD platform, oracle and bridge providers
Out of scope
Fixes, other devices, unrelated SaaS, physical security, other chains. Follow-on: full-catalogue crosswalk, Tier 3 in depth
Security Hardening Assessment Program
4
Notes: Scope follows the attack paths, not the org chart. That is why signer devices, engineer workstations and the dApp front end are in: recent large crypto losses came through those routes rather than through the cloud. Node operation is outsourced: Alchemy runs the Ethereum, Base and Solana nodes, and Blockdaemon runs the Canton Network validator, which hosts our Daml parties and, by default, their keys.

## Slide 5: Five workstreams: WS1 sets one method and stitches every finding into one roadmap
04 · WORKSTREAMS AND PROGRAM STRUCTURE
WS1 · Governance, scope and architecture
Governance and gates · crown jewels and attack scenarios · architecture · standards crosswalk · rating model · IR and resilience
WS2
OS and containers
Amazon Linux 2023 fleet, EKS, images, Vault hosts, runtime detection
WS3
Identity and access
Entra ID, B2C, Identity Center, IAM, workload identity, telemetry
WS4
Cloud, AppSec, SDLC
Guardrails, network, data, logging and SIEM, apps, supply chain
WS5
Blockchain
Contracts, admin keys, signing, Vault custody, on-chain monitoring
Each layer workstream delivers an assessment report, a target baseline and recommendations in one format
Unified findings and control register
De-duplicated, root-caused, traced to every standard
Recommendations and roadmap
Target baselines; Now / Next / Later with owners and effort
Outside the program: owning teams implement; a CISO-chaired remediation forum tracks progress after handover
Security Hardening Assessment Program
5
Notes: Read top to bottom. WS1 sets one method for everyone. The four layer workstreams assess and include their own logging and detection. Everything lands in one register and one roadmap. Detection and response sit inside each layer, not in a separate workstream, to keep focus.

## Slide 6: WS1 gives the program one method, one crosswalk and one roadmap, starting from the crown jewels
05 · WORKSTREAM 1 OF 5 · GOVERNANCE, SCOPE AND ARCHITECTURE
FOCUS AREAS
Governance, steering, gate criteria
Reconciled inventory and crown jewels
6–8 cross-layer attack scenarios, validated end to end
Architecture: current state (week 2), target state (week 11)
IR and resilience: IR plan, DORA and NYDFS reporting, BCP/DR
METHOD IT SETS
Rating: attack-path proximity × impact; value at risk for chain findings
Sampling: Tier 1 100%; Tier 2 tools plus ≥ 25% manual sample; Tier 3 tools only
Crosswalk: direct NIST IR 8477 links, published maps first, second review
Crown jewel = attacker’s target; Tier 1 = assessed first (crown jewels and assets ≤ 2 steps away)
OUTPUTS
Crosswalk v1, v2, v3 and the cross-check report
Unified findings and control register, handed to GRC
Now / Next / Later remediation roadmap
Executive report and handover pack
Team
Program manager, lead architect, GRC lead and crosswalk analyst
Standards anchor
CSF 2.0 hub · 800-53 · ISO 27001 · SOC 2 · CIS · BSSC · PCI · DORA, MiCA, NYDFS
Security Hardening Assessment Program
6
Notes: WS1 is the spine of the program. Its week-2 outputs (crown jewels, attack scenarios, rating model and crosswalk v1) decide what the other workstreams test first and how every finding is scored and mapped. The 12-week crosswalk maps every tested control; mapping the rest of each catalogue is handed over as a follow-on. Where standards differ, the strictest requirement wins; true conflicts go to Legal.

## Slide 7: WS2 hardens the Amazon Linux 2023 fleet and EKS, and closes the pod runtime-coverage gap
05 · WORKSTREAM 2 OF 5 · OS AND CONTAINERS
WHAT WE ASSESS
Amazon Linux 2023 AMIs and fleet against CIS (Inspector)
EKS against CIS EKS: RBAC, Pod Security, network policy
ECR images, containers on EC2, Vault hosts
CrowdStrike, GuardDuty Runtime and EKS audit logs into Splunk
TARGET BASELINE
Golden AMI to CIS Level 1; Level 2 for signer and internet-facing hosts
IMDSv2 everywhere; SSM-only access; 14-day critical patching
EKS: private endpoint, Pod Identity, customer-managed KMS key
Pod Security restricted; signed images enforced at admission
OUTPUTS
OS and container assessment report
Amazon Linux 2023 and EKS hardening baselines
Image Builder and policy-as-code specifications
Container-escape playbook inputs
Crown jewels and Tier 1 paths
Crown jewels: signing keys, Vault root and unseal material. Tier 1: signer and Vault hosts; clusters running signing or withdrawal services
Standards anchor
CIS Amazon Linux 2023 · CIS EKS · CSF 2.0 PR.PS · 800-53 CM, SI · BSSC NOS
Security Hardening Assessment Program
7
Notes: Crown jewel = what an attacker wants; Tier 1 = what we assess first (crown jewels plus anything two steps or fewer away). Key point: CrowdStrike covers EC2 only, and EKS pods run without Fargate. WS2 will confirm whether the Falcon sensor runs on the EKS worker nodes and how GuardDuty Runtime Monitoring covers pods. IMDS hop limit 1 applies to EKS nodes using Pod Identity or IRSA; documented container hosts may need 2.

## Slide 8: WS3 closes the paths from a phished identity to production, keys and customer funds
05 · WORKSTREAM 3 OF 5 · IDENTITY AND ACCESS
WHAT WE ASSESS
Entra ID: Conditional Access, MFA strength, PIM, break-glass
Identity Center federation, permission sets, IAM users and keys
Workload identity: IRSA, Pod Identity, CI credentials
B2C: policies, token lifetimes, MFA, abuse protection
Sign-in and audit telemetry in Splunk
TARGET BASELINE
Phishing-resistant MFA and PIM for every privileged role
Just-in-time AWS elevation; zero IAM users or static keys
OIDC for CI; quarterly access reviews
B2C hardening and an Entra External ID migration plan
OUTPUTS
Identity assessment report
Privileged-access map
Target identity baseline
Credential-compromise playbook inputs
Crown jewels and Tier 1 paths
Crown jewels: Entra Global Admin and the Identity Center trust; B2C login-to-withdrawal. Tier 1: identities and roles two steps or fewer away
Standards anchor
CSF 2.0 PR.AA · 800-53 AC, IA · ISO 27001 A.5.15–A.5.18, A.8.5 · BSSC GSP
Security Hardening Assessment Program
8
Notes: Identity is the most likely first step of an attack. Compromising Entra compromises AWS through the Identity Center trust, so that trust is a crown jewel, and therefore Tier 1. Entra ID P2 / ID Governance licensing is confirmed, so PIM and access reviews are available. Azure AD B2C is no longer sold to new customers, so a migration plan to Entra External ID is part of the baseline.

## Slide 9: WS4 covers the broadest surface in two tracks, and proves our detections actually fire
05 · WORKSTREAM 4 OF 5 · CLOUD, DATA, LOGGING, APPSEC AND SDLC
WHAT WE ASSESS
Platform track, weeks 3–6: org guardrails, Security Hub CSPM, network and egress, data encryption, backup restore test
Logging: CloudTrail and GuardDuty into Splunk; ATT&CK coverage; detection tests
Application track, weeks 4–10: ASVS 5.0 on Tier 1 apps, DAST, CI/CD, SBOM, SLSA
TARGET BASELINE
Landing-zone guardrail set (SCPs, RCPs)
Segmentation and egress pattern
Data-protection and backup standard
Logging standard and priority detections
Secure SDLC gates; SLSA Build Level 2, then 3
OUTPUTS
Cloud, network and data assessment
Validated detection coverage map
AppSec findings and SDLC maturity score (SAMM)
Guardrails-as-code specification
Crown jewels and Tier 1 paths
Crown jewels: management account, deploy paths, PII stores, dApp front end. Tier 1: assets ≤ 2 steps away
Standards anchor
CIS AWS benchmarks · FSBP · ASVS 5.0 · SLSA · 800-53 AC, SC, AU, SA · PCI DSS
Security Hardening Assessment Program
9
Notes: WS4 is the heaviest workstream, so it runs as two staggered tracks: platform in weeks 3–6 (written up during the week-7 buffer) and application in weeks 4–10. The platform window covers Tier 1; platform Tier 2 sampling runs with the rest of Tier 2 in weeks 8–10. Detection is tested, not just mapped: atomic tests in weeks 9–10 prove priority detections reach Splunk. Full ASVS depth applies to Tier 1 apps; others get tool-based checks. PCI applies only if cardholder data is confirmed in scope.

## Slide 10: WS5 protects the signing keys, the admin paths and the code that moves value
05 · WORKSTREAM 5 OF 5 · BLOCKCHAIN AND SMART CONTRACTS
WHAT WE ASSESS
Solidity, Solana and Daml code: static analysis, fork fuzzing, Anchor checks
Upgrade and admin keys: multisig thresholds, timelocks
Signing procedures and signer devices; no blind signing
Vault custody; Alchemy and Blockdaemon nodes; oracles, bridges, monitoring
TARGET BASELINE
Contract SDLC gates
Multisig plus timelock admin model
Signing-architecture decision: HSM, AWS KMS (secp256k1) or MPC
Exploit and key-compromise playbooks with SEAL 911
OUTPUTS
Assessment against the 386-control register
Contract findings and protocol threat models
Key-custody design recommendation
List of contracts needing an external audit
Crown jewels and Tier 1 paths
Crown jewels: signing keys, Canton party keys, admin and upgrade multisigs, treasury contracts. Tier 1: contracts, signers and pipelines that can reach them
Standards anchor
BSSC NOS, TIS, KMS, SCS, GSP · OWASP SCSVS, SC Top 10 · SEAL · CCSS v9.0
Security Hardening Assessment Program
10
Notes: Vault is the Enterprise edition, so the custody review also covers its Enterprise controls: HSM-backed seal and seal wrap, DR replication with a tested failover, namespaces, Sentinel policies, and control groups for multi-person approval of signing-key operations. Vault Transit has no secp256k1 key type, so Ethereum signing needs a decision: an HSM, AWS KMS secp256k1 keys, MPC, or a plugin. Ed25519 for Solana is native. Node operation is outsourced. Alchemy runs the Ethereum, Base and Solana nodes and holds no keys, so its review covers API-key handling, access and dependency risk. Blockdaemon runs the Canton Network validator, which hosts our Daml parties: by default it generates and stores their party keys and holds the contract data, so the Blockdaemon-hosted validator is treated as a crown jewel and reviewed through its assurance reports, contract terms and our access to it, against BSSC NOS. External contract audits are out of scope; WS5 produces the list of contracts that need one. If the WS5 assessor lacks Solana or Daml skills, a short specialist engagement is decided at gate 1.

## Slide 11: Tier 1 is assessed first, and four gates take the program to sign-off in week 12
06 · ROADMAP
Week
1
2
3
4
5
6
7
8
9
10
11
12
Mobilize and scope
Weeks 1–2
Assess Tier 1
Weeks 3–6
Buffer
Week 7
Tier 2, Tier 3 checks
Weeks 8–10
Recommend, handover
Weeks 11–12
Gates, milestones
G1
Flash
G2
G3
G4
G1 · Week 2
Tier 1 access ≥ 90%, inventory reconciled, scenarios approved, RoE signed
G2 · Week 6
Tier 1 fully assessed; criticals escalated, containment status known
G3 · Week 10
Tier 2 assessed, Tier 3 checked; detections validated; crosswalk v3
G4 · Week 12
Report signed; owner decisions recorded; access removed
Security Hardening Assessment Program
11
Notes: Weeks are counted from the program start date, which is still to be confirmed. The crown-jewel flash readout is in week 4. Week 7 is a one-week buffer for write-up and crosswalk mapping only; once the start date is set, place it over the main holiday or leave period. To fit 12 weeks, Tier 3 gets automated checks only and the crosswalk covers every tested control; the full-catalogue mapping and in-depth Tier 3 review are follow-ons. Gate cards abbreviate the charter’s full criteria. If the buffer falls over a leave period, the WS4 platform write-up moves into week 8. A missed gate needs a recorded CISO decision: extend, add staff, or move named scope. Capacity is tight (about 70 usable person-weeks); the gate-1 re-estimate confirms it.

## Slide 12: Deliverables land at every gate, so steering sees value from week 2, not only at the end
07 · DELIVERABLES
GATE 1 · WEEK 2
Charter, gate criteria, RACI
Inventory, crown jewels, current-state architecture
6–8 attack scenarios
Rules of engagement, evidence standard
Crosswalk v1, method and workbooks
GATE 2 · WEEKS 4–6
Crown-jewel flash readout (week 4)
Tier 1 results and critical findings
Tier 1 owner reviews
Crosswalk v2
GATE 3 · WEEK 10
Tier 2 results; Tier 3 scan results
Detection validation results
Findings to week 9 fact-checked
Crosswalk v3, all tested controls
GATE 4 · WEEKS 11–12
Standards cross-check report
Target baselines and target-state architecture
Findings register and remediation roadmap
Executive report, readiness per standard
Handover pack, follow-on scope
Security Hardening Assessment Program
12
Notes: The cross-check report, baselines, target-state architecture, register and roadmap are due in week 11; the executive report and handover pack in week 12. The handover pack lists the follow-on work: the full-catalogue crosswalk and in-depth review of Tier 3. Findings issued in week 10 are fact-checked by mid-week 11, before recommendations are final. The readiness view per standard is an internal view, not a certification or attestation opinion.

## Slide 13: Six decisions let the program start
08 · DECISIONS REQUESTED
1
Approve the charter, the 12-week plan, the gate criteria and a start date
2
Name five workstream leads; confirm WS5 skills in Solidity, Solana and Daml
3
Grant read-only access in week 0: audit role, Splunk, Entra, Vault, repositories
4
Confirm sizing: AWS accounts, EKS clusters and contract codebases
5
Confirm targets: PCI scope, MiCA and NYDFS licenses, ISO or SOC 2 goal
6
Confirm the CI/CD platform and any cross-chain bridges
Security Hardening Assessment Program
13
Notes: Decisions 1–3 are needed before week 1. The start date sets where the one-week buffer falls: place it over the main holiday or leave period that the 12 weeks cover. Week-0 preparation (access, inventory exports, rules of engagement draft) is essential: there is no slack to absorb a late start. Decisions 4–6 can land by gate 1 (week 2), but sizing drives the capacity re-estimate, so earlier is better.

## Slide 14: Frameworks, standards and regulations
09 · APPENDIX · REFERENCES 1 OF 3
NIST CSF 2.0 · The NIST Cybersecurity Framework (CSF) 2.0, NIST CSWP 29 (2024)
NIST SP 800-53 Rev. 5 · Security and Privacy Controls for Information Systems and Organizations
NIST SP 800-61 Rev. 3 · Incident Response Recommendations and Considerations for Cybersecurity Risk Management (2025)
NIST IR 8477 · Mapping Relationships Between Documentary Standards, Regulations, Frameworks, and Guidelines
ISO/IEC 27001:2022 · Information security management systems — Requirements
AICPA SOC 2 · 2017 Trust Services Criteria, with revised points of focus (2022)
PCI DSS v4.0.1 · Payment Card Industry Data Security Standard
CIS Controls v8.1 · CIS Critical Security Controls, version 8.1
DORA · Regulation (EU) 2022/2554, Digital Operational Resilience Act
MiCA · Regulation (EU) 2023/1114, Markets in Crypto-Assets
NYDFS Part 500 · 23 NYCRR 500, Cybersecurity Requirements for Financial Services Companies (amended 2023)
FATF Recommendations · R.15 (new technologies) and R.16 (wire transfers, “travel rule”)
EU TFR · Regulation (EU) 2023/1113, information accompanying transfers of funds and crypto-assets
EU AMLR · Regulation (EU) 2024/1624, anti-money laundering and countering the financing of terrorism
GDPR · Regulation (EU) 2016/679, General Data Protection Regulation
PCI DSS and the regulations apply only where Legal confirms applicability. Mappings reuse the project’s Unified Blockchain Control Register.
Security Hardening Assessment Program
14
Notes: Versions are pinned in the crosswalk register. NIST’s published informative references link CSF 2.0 to SP 800-53, CIS Controls v8.1, ISO/IEC 27001:2022 and PCI DSS 4.0.1. FATF, EU TFR, EU AMLR and GDPR come from the existing blockchain register.

## Slide 15: Cloud, operating system and application benchmarks
09 · APPENDIX · REFERENCES 2 OF 3
CIS AWS Foundations · CIS Amazon Web Services Foundations Benchmark
CIS AWS Services · CIS AWS Compute, Database and Storage Services Benchmarks
CIS Amazon Linux 2023 · CIS Amazon Linux 2023 Benchmark
CIS Amazon EKS · CIS Amazon Elastic Kubernetes Service (EKS) Benchmark
CIS Azure Foundations v6.0.0 · CIS Microsoft Azure Foundations Benchmark; Entra ID identity and logging sections only, from the project’s Azure CIS register
CIS Azure Services v2.0.0 · CIS Microsoft Azure Compute, Database and Storage Services Benchmarks; in the Azure CIS register, not applicable to this AWS estate
AWS FSBP · AWS Foundational Security Best Practices standard (Security Hub CSPM)
OWASP ASVS 5.0 · Application Security Verification Standard, version 5.0 (2025)
OWASP SAMM v2 · Software Assurance Maturity Model, version 2
SLSA v1.2 · Supply-chain Levels for Software Artifacts, Build track
MITRE ATT&CK · Enterprise matrix, including the Cloud and Containers platforms
CIS Benchmark versions are confirmed and pinned in the crosswalk register at gate 1.
Security Hardening Assessment Program
15
Notes: The Azure CIS register in the project covers Azure services; only its Entra ID rows apply to this AWS estate. The AWS, Amazon Linux 2023 and EKS benchmark rows are imported by ID into crosswalk v1.

## Slide 16: Blockchain and smart-contract standards
09 · APPENDIX · REFERENCES 3 OF 3
BSSC NOS v2 · Node Operation Standard
BSSC TIS v1 · Token Integration Standard
BSSC KMS v1 · Key Management Standard
BSSC SCS v1 · Smart Contract Security Standard
BSSC GSP v2 · General Security and Privacy Guidelines
OWASP SCSVS · Smart Contract Security Verification Standard
OWASP SC Top 10 (2026) · Smart Contract Top 10
OWASP Web3 Top 15 · Web3 Attack Vectors Top 15 (WA01–WA15), published alongside the SC Top 10
EthTrust Security Levels · EEA EthTrust Security Levels Specification; now with the W3C EthTrust Community Group
SEAL Frameworks · Security Alliance frameworks: multisig, treasury, wallet, incident and operational security
CCSS v9.0 · CryptoCurrency Security Standard, CryptoCurrency Certification Consortium (C4)
All are mapped in the project’s Unified Blockchain Control Register: 386 controls (325 BSSC, 61 supplementary).
Security Hardening Assessment Program
16
Notes: BSSC is the Blockchain Security Standards Council. The register maps each control to CSF 2.0, ISO/IEC 27001:2022 and CIS Controls v8.1; SP 800-53 links are added in the crosswalk.

## Slide 17: Acronyms A to E
09 · APPENDIX · ACRONYMS 1 OF 3
AC · Access Control (SP 800-53 family)
AICPA · American Institute of Certified Public Accountants
AMI · Amazon Machine Image
AMLR · Anti-Money Laundering Regulation (EU)
API · Application programming interface
AppSec · Application security
ASVS · Application Security Verification Standard (OWASP)
ATT&CK · Adversarial Tactics, Techniques, and Common Knowledge (MITRE)
AU · Audit and Accountability (SP 800-53 family)
AWS · Amazon Web Services
Azure AD B2C · Azure Active Directory Business-to-Consumer
BCP · Business continuity plan
BSSC · Blockchain Security Standards Council
C4 · CryptoCurrency Certification Consortium
CCSS · CryptoCurrency Security Standard
CI · Continuous integration
CI/CD · Continuous integration / continuous delivery
CIS · Center for Internet Security
CISO · Chief Information Security Officer
CM · Configuration Management (SP 800-53 family)
CSF · Cybersecurity Framework (NIST)
CSPM · Cloud security posture management
CSWP · Cybersecurity White Paper (NIST)
dApp · Decentralized application
DAST · Dynamic application security testing
DevSecOps · Development, security and operations
DNS · Domain Name System
DORA · Digital Operational Resilience Act (EU)
DR · Disaster recovery
EBS · Amazon Elastic Block Store
EC2 · Amazon Elastic Compute Cloud
ECR · Amazon Elastic Container Registry
EEA · Enterprise Ethereum Alliance
Security Hardening Assessment Program
17
Notes: Abbreviations used across the deck and its speaker notes, in alphabetical order.

## Slide 18: Acronyms E to P
09 · APPENDIX · ACRONYMS 2 OF 3
EFS · Amazon Elastic File System
EKS · Amazon Elastic Kubernetes Service
EU · European Union
EVM · Ethereum Virtual Machine
FATF · Financial Action Task Force
FSBP · AWS Foundational Security Best Practices
G1–G4 · Program gates 1 to 4
GDPR · General Data Protection Regulation (EU)
GRC · Governance, risk and compliance
GSP · General Security and Privacy Guidelines (BSSC)
HSM · Hardware security module
IA · Identification and Authentication (SP 800-53 family)
IaC · Infrastructure as code
IAM · AWS Identity and Access Management
IEC · International Electrotechnical Commission
IMDS, IMDSv2 · EC2 Instance Metadata Service (version 2)
IR · Incident response; in “NIST IR 8477”, NIST Interagency or Internal Report
IRSA · IAM Roles for Service Accounts (EKS)
ISO · International Organization for Standardization
KMS · AWS Key Management Service; in BSSC, Key Management Standard
MFA · Multi-factor authentication
MiCA · Markets in Crypto-Assets Regulation (EU)
MPC · Multi-party computation
NIST · National Institute of Standards and Technology
NOS · Node Operation Standard (BSSC)
NYCRR · New York Codes, Rules and Regulations
NYDFS · New York State Department of Financial Services
OIDC · OpenID Connect
OS · Operating system
OWASP · Open Worldwide Application Security Project
P2 · Microsoft Entra ID P2 license
PII · Personally identifiable information
PCI DSS · Payment Card Industry Data Security Standard
Security Hardening Assessment Program
18
Notes: Abbreviations used across the deck and its speaker notes, in alphabetical order.

## Slide 19: Acronyms P to W
09 · APPENDIX · ACRONYMS 3 OF 3
PIM · Privileged Identity Management (Entra ID)
PR.AA · CSF Protect: Identity Management, Authentication, and Access Control
PR.PS · CSF Protect: Platform Security
R.15, R.16 · FATF Recommendations 15 and 16
RACI · Responsible, accountable, consulted, informed
RBAC · Role-based access control
RCP · Resource control policy (AWS Organizations)
RoE · Rules of engagement
S3 · Amazon Simple Storage Service
SA · System and Services Acquisition (SP 800-53 family)
SAMM · Software Assurance Maturity Model (OWASP)
SaaS · Software as a service
SBOM · Software bill of materials
SC · System and Communications Protection (SP 800-53 family); in “SC Top 10”, Smart Contract
SCP · Service control policy (AWS Organizations)
SCS · Smart Contract Security Standard (BSSC)
SCSVS · Smart Contract Security Verification Standard (OWASP)
SDLC · Software development lifecycle
SEAL · Security Alliance
SI · System and Information Integrity (SP 800-53 family)
SIEM · Security information and event management
SLSA · Supply-chain Levels for Software Artifacts
SOC 2 · System and Organization Controls 2 (AICPA)
SP · Special Publication (NIST)
SSM · AWS Systems Manager
TFR · Transfer of Funds Regulation (EU)
TGW · AWS Transit Gateway
TIS · Token Integration Standard (BSSC)
TSC · Trust Services Criteria (AICPA)
VPC · Amazon Virtual Private Cloud
W3C · World Wide Web Consortium
WAF · Web application firewall (AWS WAF)
WA01–WA15 · OWASP Web3 Attack Vectors 1 to 15
WS1–WS5 · Workstreams 1 to 5
Security Hardening Assessment Program
19
Notes: Abbreviations used across the deck and its speaker notes, in alphabetical order.