## Slide 1: Security Hardening, Monitoring & Governance Program
EXECUTIVE BRIEFING · OCTOBER 2026
A 26-week plan for AWS workloads, Ethereum and Solana dApps, and Microsoft Entra ID / Azure AD B2C identity — independently reviewed and re-baselined
Plan v2 · 75 tasks · 6 workstreams · 4 governance gates
Notes: Purpose: secure approval for a 26-week program and three immediate actions. The plan was reviewed by four independent specialist reviewers before this briefing.

## Slide 2: In 26 weeks we close today’s critical gaps and leave an operating model that keeps security current
EXECUTIVE SUMMARY
75
tasks in 6 workstreams, sequenced and dependency-checked
5 + 4
internal + contractor FTE, plus an MDR partner and external auditors
4
steering gates: weeks 6, 15, 20 and 26
3
immediate actions that cannot wait for mobilization
Outcome: hardened OS and containers (CIS Level 1 ≥95%), unified monitoring across cloud, identity and chain, and SOC 2 readiness.
Sustainability: standing forums, KPIs and event triggers keep controls aligned as AWS, Microsoft, Ethereum and Solana change.
Ask: approve the program, staffing and partner bookings, and the three immediate actions on the next slide.
Source: Security_Hardening_Governance_Project_Plan.xlsx (v2, 17 Oct 2026)
Notes: Bottom line first. The plan was re-baselined after independent review; figures here match the v2 workbook.

## Slide 3: Three exposures are live today
ACT THIS WEEK — BEFORE THE PROGRAM STARTS
21 OCTOBER 2026
Solana Alpenglow consensus switch
Validators must run an Agave 4.3.0-based client and fund vote accounts (0.8 SOL per epoch), or they stop producing blocks. Firedancer is not supported during the switch.
ENDED 1 JULY 2026
MiCA transition and DORA duties
Confirm authorisation status now. If we are a CASP, DORA incident reporting (4h / 72h / 1 month) applies today, so an interim procedure is needed.
ENDED 30 JUNE 2026
Amazon Linux 2 support
Any remaining AL2 hosts no longer receive security updates. Inventory now; migrate to AL2023 or Bottlerocket under task O-11.
Notes: These were surfaced by the independent review and re-verified against vendor sources on 17 Oct 2026 (Solana/Anza, AWS AL2 FAQ, ESMA/AMF on MiCA, DORA Art. 19). Owners: Blockchain Infra Engineer (B-00), Compliance Counsel (G-04, M-00), Platform Engineer (O-11).

## Slide 4: Four objectives, each with a measurable end state
PROGRAM OBJECTIVES
1 · Harden operating systems and containers
CIS-hardened AL2023/Bottlerocket images, EKS/ECS to CIS EKS v2.0.0. Target: CIS L1 ≥95%, AL2 = 0, critical patches ≤14 days.
2 · Harden security monitoring
One SIEM view of AWS, Entra/B2C, hosts and on-chain activity. Target: 100% log sources, MTTD <5 min on-chain, <30 min identity.
3 · Secure identity, keys and contracts
Phishing-resistant admin MFA, 0 human IAM users, every privileged on-chain role under multisig + timelock, audited code.
4 · Build sustainable governance
Policies, unified control matrix and forums in BAU. Target: SOC 2 observation window open, regulatory obligations mapped.
Notes: Frameworks used: NIST CSF 2.0 as the outcome map, CIS benchmarks for technical settings, BSSC and CCSS for blockchain, SOC 2 and MiCA/DORA (and PCI DSS v4.0.1 if in scope) for assurance.

## Slide 5: What the business receives, phase by phase
PROGRAM DELIVERABLES
Phase · weeks | Key deliverables | Exit
Immediate · now | Validators ready for Alpenglow; regulatory go/no-go started; AL2 inventory | Validators live
0 Mobilize · 1–3 | Charter; partners booked; GuardDuty, Inspector, Security Hub on; validator monitoring; interim DORA procedure | Visibility on
1 Assess · 2–7 | Inventory, risk appetite, threat model, gap assessment, licensing, governance charter | Gate 1 · wk 6
2 Build · 6–18 | Guardrails; golden AMIs; AL2 retired; EKS/ECS hardened; CA, PIM, federation; log archive; multisig + timelocks; custody; policies v1.0 | Gate 2 · wk 15
3 Validate · 11–22 | Detections and SOAR; IR playbooks; audits and bounty; pentest; DR test; CIS L1 ≥95%; SOC 2 readiness | Gate 3 · wk 20
4 Operate · 21–26 | Runbooks and handover; BAU calendar; continuous compliance; scorecard; phase-2 roadmap | Gate 4 · wk 26
Notes: Each deliverable maps to a task ID in the Project Plan tab. Gates are Steering Committee go/no-go decisions with signed criteria.

## Slide 6: Phases overlap; four gates keep the program honest
26-WEEK ROADMAP
wk 1
wk 6
wk 11
wk 16
wk 21
wk 26
Immediate (now)
0 · Mobilize
1 · Assess & design
2 · Build & harden
3 · Monitor & validate
4 · Operationalize
Alpenglow · regulatory go/no-go · AL2 inventory
wk 1–3
wk 2–7
wk 6–18
wk 11–22
wk 21–26
Gate 1 · wk 6
Architecture & decisions
Gate 2 · wk 15
Build checkpoint
Gate 3 · wk 20
Validated
Gate 4 · wk 26
BAU handover
Notes: Critical path runs through AL2/EKS remediation, EKS hardening and fleet roll-out; track their float weekly.

## Slide 7: OS & container hardening
WORKSTREAM 1 OF 6 · 14 TASKS
Focus areas
Day-one visibility: GuardDuty, Inspector, Security Hub
CIS AL2023 / Bottlerocket images; AL2 retired
EKS to CIS EKS v2.0.0; ECS task standards
Org guardrails: SCPs, RCPs, IMDSv2, Allowed AMIs
Level 2 builds for validator and RPC hosts
Key tasks (weeks)
Security services baseline (2–3)
SSM fleet enrolment and patching (4–6)
AL2 and EKS version remediation (6–17)
Golden AMI and signed image pipelines (8–10)
EKS hardening (11–16); enforce admission policy (17–18)
Fleet roll-out and CIS measurement (14–22)
Deliverables
Linux and container hardening standards
Hardened AMI catalogue, monthly rebuild
Signed images with SBOMs
CIS L1 ≥95% report; exception register
AL2 = 0; EKS on standard support
Roles: Cloud Security Engineer (lead) · Platform/DevOps Engineer · Kubernetes Security Engineer (CKS) · DevSecOps Engineer · Blockchain Infra Engineer
References: CIS AL2023 v1.0.0 · CIS Amazon EKS v2.0.0 · CIS AWS Foundations v5/v6 · NIST CSF PR.PS
Notes: Independent review moved SSM enrolment ahead of scanning, added AL2 retirement, and extended EKS hardening to six weeks to include access entries and version upgrades.

## Slide 8: Identity hardening — Entra ID, Azure AD B2C, AWS
WORKSTREAM 2 OF 6 · 10 TASKS
Focus areas
Phishing-resistant MFA (passkeys) for admins
Just-in-time privilege with Entra PIM
Customer accounts: step-up MFA, anti-fraud
AWS access only via Entra federation
Wallet sign-in that cannot bypass MFA
Key tasks (weeks)
Licensing gap plan, P1/P2/ID Governance (4–5)
Break-glass, Conditional Access (6–8)
B2C vs External ID decision (7–8)
PIM and B2C hardening (9–11)
AWS federation; wallet sign-in (12–14)
Anti-fraud; workload identity; detections (14–17)
Deliverables
Conditional Access policy set
PIM roll-out, quarterly access reviews
0 human IAM users in AWS
CIAM decision paper and roadmap
Workforce and customer takeover detections
Roles: Identity Engineer (lead, SC-300) · CIAM Engineer (B2C custom policies) · Security Architect · DevSecOps Engineer
Context: B2C closed to new customers May 2025, supported to at least May 2030; B2C P2 retired March 2026
Notes: B2C P2 retirement removed Identity Protection for customer accounts, so the plan adds explicit anti-fraud controls and step-up MFA for withdrawals and wallet linking. External ID does not run B2C custom policies, which drives the week-8 decision.

## Slide 9: Security monitoring, response and resilience
WORKSTREAM 3 OF 6 · 15 TASKS
Focus areas
One SIEM view: AWS, Entra/B2C, hosts, chain
Immutable central log archive
On-chain alerts for Ethereum and Solana
24/7 response with an MDR partner
Regulator-ready incident reporting; DR
Key tasks (weeks)
Validator monitoring; interim DORA procedure (2–4)
SIEM decision; logging foundation (6–10)
On-chain monitoring; detections (11–16)
IR playbooks; DR restore test (14–18)
SOAR, pentest, container detections (17–20)
Tabletop and purple-team (20–21)
Deliverables
Monitoring architecture, SIEM live
Detection catalogue mapped to ATT&CK
IR plan incl. key compromise, exploit
Tested restore with RTO/RPO
Security operations KPI dashboard
Roles: Detection Engineer (lead) + MDR partner · Cloud Security Engineer · IR Lead (held by Security Architect) · Blockchain Security Engineer
If Microsoft Sentinel is chosen: onboard in the Defender portal from day one (Azure portal support ends 31 Mar 2027)
Notes: Contract pausing from SOAR uses a dedicated pause-only guardian role held in HSM or MPC, never an upgrade key. Container detections follow container telemetry; the review caught the original ordering error.

## Slide 10: Blockchain security — contracts, keys, validators
WORKSTREAM 4 OF 6 · 12 TASKS
Focus areas
Hard-fork readiness: Alpenglow, Glamsterdam
Admin keys under Safe / Squads + timelocks
MPC or HSM custody, key ceremonies
Secure Solidity and Rust/Anchor pipelines
Validator keys, slashing protection
Key tasks (weeks)
Alpenglow readiness (now)
Role inventory; withdrawal credentials (4–5)
Secure SDLC; Solana baseline (6–9)
Multisig and timelocks (8–10); custody (7–14)
Audits and bug bounty (11–18)
Validator hardening (14–17); PQC review (16–17)
Deliverables
100% privileged roles multisig + timelock
Blocking security gates, verified builds
Custody architecture and procedures
Audit reports; bounty with Safe Harbor
Validator runbooks; crypto-agility plan
Roles: Blockchain Security Engineers (2 contractors: EVM + Solana) · Blockchain Infra Engineer · Key Management Specialist · external auditors
References: BSSC SCS v1, NOS v2, KMS v1 · CCSS v9 · SEAL multisig framework · OWASP SC Top 10
Notes: Signers recompute Safe transaction hashes independently (lesson of the Feb 2025 Bybit loss). Solana upgrades go through Squads with solana-verify build checks. Pectra made Ethereum withdrawal credentials control keys, so they move under multisig or cold storage.

## Slide 11: Governance & compliance
WORKSTREAM 5 OF 6 · 11 TASKS
Focus areas
Regulatory scope: MiCA, DORA, PCI DSS
Policies and one unified control matrix
Vendor and ICT third-party risk
Automated evidence in a GRC platform
SOC 2 readiness and training
Key tasks (weeks)
Regulatory go/no-go (1–2)
Operating model and RACI (2–4)
Policies v1.0; control matrix (5–10)
Vendor risk; GRC tooling (8–11)
Exceptions; HR controls (11–12)
SOC 2 readiness; training (16–20)
Deliverables
Regulatory obligations register
11 approved policies, hardening standards
Control matrix: SOC 2, CSF, CIS, BSSC
Continuous control monitoring live
SOC 2 window open (~week 20)
Roles: GRC Lead (lead) · GRC Analyst · Compliance Counsel · Program Lead (vendor risk) · all control owners
SOC 2 uses the 2017 Trust Services Criteria (2022 points of focus); Type II window 3–12 months, so the report lands in 2027
Notes: PCI DSS v4.0.1 applies only if cardholder data is in scope; tokenisation is the preferred way to keep scope small. DORA applies to authorised CASPs.

## Slide 12: Program management & sustainment
WORKSTREAM 6 OF 6 · 13 TASKS
Focus areas
Charter, risk appetite, threat model
Early partner booking (lead times)
Gate reviews with signed criteria
Knowledge transfer from contractors
Hand-over to an evergreen BAU rhythm
Key tasks (weeks)
Charter; book partners (1–2)
Inventory; risk appetite (2–3)
Threat model; gap assessment (4–5)
Gates at weeks 6, 15, 20
Continuous compliance; runbooks (22–24)
Gate 4 and phase-2 roadmap (25–26)
Deliverables
Charter, RAID log, signed partner SOWs
Threat model and gap assessment
Approved target architecture
Runbook library, KT sign-off
BAU calendar; phase-2 roadmap
Roles: Program Lead (lead) · Security Architect · CISO/Sponsor (gates) · GRC Lead · Cloud Security Engineer
Critical path: AL2/EKS remediation → EKS hardening → fleet roll-out → handover; float tracked weekly
Notes: Combines the Program and Sustainment tracks of the workbook (9 + 4 tasks).

## Slide 13: A lean core team, specialists where depth matters
TEAM AND SKILLS
Internal (5.0 FTE) | FTE | Evidence
Security Architect (also IR Lead) | 1.0 | CISSP
Cloud Security Engineer | 1.0 | AWS Security
GRC Lead | 0.75 | CISA / CRISC
Program Lead | 0.5 | PMP
Platform/DevOps Engineer | 0.5 | AWS DevOps
Identity Engineer | 0.5 | SC-300
Detection Engineer | 0.5 | SC-200
DevSecOps Engineer | 0.25 | GCSA
Contractors (4.0 FTE) | FTE | Evidence
Blockchain Security Eng. ×2 | 1.5 | Audit record
Kubernetes Security Engineer | 0.75 | CKS
CIAM Engineer (B2C) | 0.5 | SC-300
Blockchain Infra Engineer | 0.5 | Validator ops
GRC Analyst | 0.5 | SOC 2
Key Management Specialist | 0.25 | CCSSA
Partners: MDR, audit, pentest | — | SOWs wk 1–2
Notes: Internal FTE meets the 3–5 target only at its upper bound. To trim: merge Program Lead into the Security Architect role or move more detection work to the MDR partner. Plan to convert one blockchain security role to an internal hire before handover.

## Slide 14: Six forums with clear decision rights
GOVERNANCE MODEL
Three lines: engineering teams own controls · Security and GRC set standards and monitor · auditors and pentesters assure independently
Forum | Cadence | Decides
Security Steering Committee | Monthly | Risk appetite, policies, budget, High/Critical risk acceptance; risk and compliance review
Architecture Review Board | Bi-weekly | Designs, standards, Medium exceptions, reference architectures
Contract Upgrade & Key Committee | Per change + monthly | Upgrades, parameter changes, signer changes, key ceremonies (internal chair)
Change Advisory | Weekly | AMI roll-outs, EKS and validator client upgrades
Incident Response Team | 24/7 with MDR | Invoke playbooks: pause, key rotation, regulator and customer notices
Independent assurance | Annual | SOC 2, contract audits, pentest, independent review of GRC-tested controls
Notes: The review merged the separate risk forum into Steering, moved the key committee to an internal chair, and added independent assurance so the GRC Lead does not mark their own homework.

## Slide 15: A loop that runs on a calendar and on events
EVERGREEN OPERATING MODEL
Monitor
SIEM · CSPM · GRC
Measure
KPIs · KRIs · drift
Review
Steering · ARB
Improve
Backlog · standards
Assure
Audits · tests
continuous improvement
Calendar
Weekly · vulnerability and alert triage, change advisory
Monthly · Steering with KPI/KRI pack, risk register
Quarterly · access reviews, standards refresh
Semi-annual · tabletops, DR test, CSF re-score
Annual · risk assessment, pentest, SOC 2 audit
Event triggers force a re-assessment
Contract deploy or upgrade · hard fork or client release · new CIS, BSSC or vendor version · major incident · new vendor · regulatory change
Notes: Control health is measured automatically in the GRC platform (target ≥95% passing). Incidents, exercises and audit findings feed one backlog prioritised at Steering. Exceptions expire automatically (max 6 months). Policies and the control matrix live in version control. A contractor-dependency KRI tracks knowledge retention.

## Slide 16: Ten headline measures reported monthly to Steering
HOW WE WILL KNOW IT WORKS
Area | Measure | Target
OS hardening | CIS Level 1 score; hosts on current image | ≥95% / ≥95%
Patching | Critical vulnerabilities fixed in SLA | ≥95% within 14 days
AWS posture | AL2 hosts; IMDSv2; Security Hub score | 0 / 100% / ≥90%
Containers | Images signed and scanned before deploy | 100%
Identity | Phishing-resistant admin MFA; standing admins | 100% / 0
Customer identity | Withdrawals with step-up MFA | 100%
Monitoring | MTTD on-chain / identity; MTTR critical | <5 min / <30 min / <4 h
On-chain | Privileged roles under multisig + timelock | 100%
Validators | Slashing events; Ethereum single-client share | 0 / <33%
Governance | SOC 2 controls passing automated tests | ≥95%
Notes: Full list with data sources and owners is in the KPIs tab. Solana client-diversity targets are paused until after the Alpenglow migration because only Agave-based clients are supported during the switch.

## Slide 17: Four reviewers found 19 issues: 18 fixed in v2, 1 deferred
INDEPENDENT REVIEW
2
critical
12
high
5
medium
+19
tasks added, 1 merged
Finding | Resolution
Solana Alpenglow (21 Oct) not in plan | Immediate readiness task; validator monitoring wk 2
MiCA/DORA scope assessed too late | Go/no-go wks 1–2; interim DORA procedure
Amazon Linux 2 past end of support | Migration task; AL2 banned in the standard
Sequencing errors (SSM, telemetry, audits) | Re-ordered; every dependency re-checked
No DR test, pentest, risk appetite, gates | Added, with four signed gates
Key roles overloaded | GRC analyst, 2nd blockchain engineer, MDR
Reviewers: cloud/OS, identity and monitoring, blockchain, governance/PMO · full log in the workbook’s Review Log tab
Notes: Each reviewer worked independently from current vendor documentation. Three critical facts were re-verified directly: Alpenglow 21 Oct 2026, AL2 end of support 30 Jun 2026, Sentinel Azure-portal end 31 Mar 2027.

## Slide 18: What could derail the plan, and what we must decide
RISKS AND DECISIONS
Top delivery risks
Critical: validators miss the Alpenglow cut-over
Critical: unconfirmed MiCA/DORA status
High: contractor key-person dependency
High: validator slashing during changes
High: B2C fraud gap after P2 retirement
Medium: hardening breaks apps (audit mode first)
Decisions and due week
Regulatory status; MDR partner — wk 2
On-chain monitoring vendor (Solana) — wk 5
Custody: MPC, HSM or hybrid — wk 6
SIEM platform — wk 7
Stay on B2C or plan External ID — wk 8
Kubernetes policy engine — wk 11
SOC 2 Type I date and window — wk 16
Notes: Full risk register and decision log in the workbook (Risks, Decisions tabs).

## Slide 19: Approve the program and start the three immediate actions
DECISIONS REQUESTED TODAY
Authorise Solana Alpenglow readiness before 21 October.
Commission the MiCA/DORA go/no-go and the interim incident procedure.
Approve the 26-week program, 5.0 internal + 4.0 contractor FTE and an MDR partner.
Release partner bookings this week: contract auditors, SOC 2 CPA, pentest, GRC platform.
Confirm the Security Steering Committee and the week-6 Gate 1 date.
Result by week 26: hardened and measured infrastructure, monitored chains and identities, and a governance loop that keeps pace with change.
Notes: Budget figures are not included; tooling (SIEM, on-chain monitoring, GRC platform, MPC custody) and audit fees should be costed before Gate 1.