## Slide 1
Security Hardening & Evergreen Governance Program
26-week execution plan for OS & container hardening, security monitoring, and a sustainable governance model - AWS, Entra ID / Azure AD B2C, Ethereum & Solana
OS & container hardening
Identity hardening
Monitoring, response & resilience
Blockchain security
Governance & compliance
Program mgmt & sustainment
Steering Committee | Monday 19 October 2026 | Plan v2 (after four independent reviews)
Notes: Purpose: approve the program, its immediate actions and the first decisions. Plan v2 incorporates four independent adversarial reviews (cloud, identity & monitoring, blockchain, governance/PMO) and a re-verification of the three most consequential facts. All figures in this deck come from the accompanying workbook Security_Program_Plan_v2.xlsx. Week 0 is this week (19-25 Oct 2026); Week 1 starts Monday 26 Oct 2026; Week 26 ends Sunday 25 Apr 2027.

## Slide 2: Executive summary: a staffed, sequenced 26-week program
Exposures land now: Solana Alpenglow activates 21 Oct; EKS 1.31 support ends 26 Nov and 1.34 standard support 2 Dec; Amazon Linux 2 is already past end of support
16 Immediate actions with named owners and deadlines start this week
150 tasks in 6 workstreams pass every check: dependencies, end week, decision dates and role load
Needs 5.0 internal FTE, 8 contractors (6.5 FTE at peak, 133 FTE-weeks) and 7 partner firms; the budget is not yet costed
150
tasks across 6 workstreams
16
Immediate actions, owned
5.0 + 6.5
internal FTE + contractor FTE (peak)
4
Steering gates: W6, W15, W20, W26
25
KPIs with targets and owners
62
review findings applied in v2
Notes: Bottom line: the program is decision-ready. 150 tasks, 16 of them Immediate actions with owners and deadlines. Sequencing checks are formulas in the workbook (Overview tab): 0 dependency violations, 0 tasks after W26, 0 decision misalignments, 0 role overloads. Internal team 5 FTE (top of the 3-5 range); 8 contractors peaking at 6.5 FTE (133 FTE-weeks) plus 7 partner firms (smart-contract auditor, MDR, pentest, readiness assessor, SOC 2 CPA, counsel, internal audit). Budget is not costed - an interim envelope is requested today (D-17).

## Slide 3: Time-critical exposures fall before and inside the window
Already past - open findings
30 Jun 2026: Amazon Linux 2 end of support - remaining AL2 hosts are unsupported
1 Jul 2026: OpenZeppelin Defender shut down - check for orphaned relayers and roles
1 Jul 2026: Azure MFA Phase 2 postponement ended - automation running as users fails
Rolling: Entra keeps sign-in/audit logs 30 days (P1/P2) - archive now
W0
W6
W15
W20
W26
21 Oct
Solana Alpenglow mainnet (epoch 1064)
26 Oct
Glamsterdam on Hoodi testnet
26 Nov
EKS 1.31 extended support ends
2 Dec
EKS 1.34 standard support ends
23 Mar
EKS 1.32 extended support ends
27 Mar
EKS 1.35 standard support ends
Glamsterdam mainnet date not yet set; EKS auto-upgrades at end of extended support without notice or rollback
Notes: Sources (Sources tab): solana.com/upgrades/alpenglow (epoch 1064, ~15:00 UTC 21 Oct; validator admission ticket 0.8 SOL burned per epoch; only Agave-4.3.0-based clients during migration); blog.ethereum.org Glamsterdam Hoodi announcement (26 Oct; no mainnet date); EKS Kubernetes versions page (1.31 extended EOS 26 Nov 2026; 1.34 standard EOS 2 Dec 2026; 1.32 extended EOS 23 Mar 2027; 1.35 standard EOS 27 Mar 2027; auto-upgrade without notice and no rollback); AL2 FAQ (EOS 30 Jun 2026); OpenZeppelin Defender phase-out; Microsoft mandatory MFA page; Entra data retention reference. The three most consequential of these (Alpenglow, EKS calendar, Entra retention) were re-verified by the lead after the reviews.

## Slide 4: 16 Immediate actions, each with an owner and a deadline
Blockchain Sec Eng (BSE)
BC-01 Tue 20 Oct
Alpenglow readiness confirmed in writing by staking provider
BC-02 Fri 30 Oct
Staking withdrawal authorities verified on-chain
BC-22 Fri 6 Nov
Interim multisig thresholds + Squads time lock
BC-04 Fri 27 Nov
Glamsterdam gas-repricing impact report
Cloud & Platform Sec Eng (CSE)
HD-01 Fri 30 Oct
AL2/EKS EOL inventory + upgradePolicy
MR-01 Fri 30 Oct
Agentless AWS detection in all accounts
MR-21 Fri 30 Oct
Archive Entra and B2C logs
HD-03 Fri 6 Nov
AL2 containment + migration backlog
HD-02 20 / 27 Nov
EKS 1.31 upgraded; 1.34 per D-10
HD-16B Fri 26 Feb
All clusters on 1.36
Identity & SecOps Eng (ISE)
MR-00 Fri 30 Oct
Interim 24/7 on-call and paging
ID-01 Fri 30 Oct
Break-glass for Entra and AWS tested
ID-02 Fri 6 Nov
Fix automation broken by MFA Phase 2
Program Lead / GRC Lead
PM-01 Fri 23 Oct
Immediate-actions cell stood up (PL)
ID-00 Fri 23 Oct
FIDO2 keys + signer wallets ordered (PL)
GC-01 Fri 20 Nov
Regulatory go/no-go memo D-01 (GRC)
Notes: Every Immediate action is in the Project Plan tab with owner and deadline in the 'Immediate action' column. BC-01 is the most urgent: the staking provider must confirm BLS registration, VAT funding (0.8 SOL per epoch), and an Agave-4.3.0-based client before Alpenglow activates on 21 Oct; rewards for epochs 1065-1066 are checked by 30 Oct. HD-02: 1.31 clusters are upgraded to 1.32 by 20 Nov (deadline 26 Nov) and 1.34 clusters handled per D-10 by 27 Nov (deadline 2 Dec). HD-16B carries the 23 Mar 2027 hard stop for 1.32.

## Slide 5: Objectives with measurable targets
1 OS & container hardening
Amazon Linux 2 instances: 0 by W20
EKS on standard support: 100% by W18
CIS AL2023 L1 pass rate >=90% by W20
IMDSv2 coverage 100% by W12
Signed production images 100% by W19
2 Monitoring & response
24/7 coverage from W0 (interim), MDR fully live W13
MTTD identity: median <=15 min, p90 <=60 min
MTTD on-chain: median <=5 min
MTTR Sev-1 containment: median <=4 h
>=80% prioritised ATT&CK techniques validated by W18
3 Evergreen governance
SOC 2 Type I as of 21 Mar 2027; Type II period from 22 Mar
Automated control pass rate >=95% by W20
Exceptions past expiry: 0
Critical runbooks with internal owner: 100% by W24
Independent assurance report to Board by W24
Enablers Identity & on-chain
Phishing-resistant admin MFA 100% by W12
Standing admins (excl. break-glass) 0 by W15
Step-up MFA on withdrawals 100% by W13
Upgrade/admin roles under multisig + timelock 100% by W15
Notes: Targets come from the KPIs tab (K01-K25 and KRI-1). MTTD is event time to notable/MDR ticket; MTTR-contain is acknowledgement to logged containment; medians and p90 are reported monthly. SOC 2 dates come from task GC-15: Type I as-of Sunday 21 Mar 2027 (end of W21) and a gap-free Type II period from Monday 22 Mar 2027. The minimum Type II period is UNVERIFIED (AICPA FAQ login-gated); the plan assumes 3-6 months, confirmed with the CPA in GC-07.

## Slide 6: Deliverables by phase
P0 Immediate
W0-W2 | 13 tasks
Immediate-actions tracker
Alpenglow confirmation
Break-glass + interim 24/7
EOL register
P1 Mobilize
W1-W6 | 16 tasks
Charter + interim budget
Partners booked
Regulatory memo (D-01)
Risk appetite, BIA
P2 Assess & Design
W2-W10 | 38 tasks
Gap assessment + threat model
ARB-approved designs
Policy set v1.0
Control matrix, TPRM
P3 Build & Harden
W6-W20 | 60 tasks
Org guardrails live
AL2 retired; EKS 1.36
CA + PIM enforced
Multisig + timelock
P4 Monitor & Validate
W10-W22 | 16 tasks
Detections waves 1-2
Pentest + retest
Smart-contract audit
SOC 2 readiness
P5 Operationalize
W14-W26 | 7 tasks
Evergreen calendar live
Bug bounty live
SOC 2 Type I + Type II start
BAU handover signed
Notes: Phases overlap by design; each task is assigned to one phase. Task counts per phase are from the Project Plan tab: P0 13, P1 16, P2 38, P3 60, P4 16, P5 7 (total 150). Weeks 9-10 (21 Dec - 3 Jan) are a production change freeze; design and non-prod work continues.

## Slide 7: Roadmap: 27 weeks, four signed gates, holiday freeze respected
Freeze
W0
W2
W4
W6
W8
W10
W12
W14
W16
W18
W20
W22
W24
W26
OS & container hardening
EKS EOS
Nodes
EKS hops to 1.36
AL2 wave 2
SSM
Guardrails
AL2 wave 1
Signing
Identity hardening
BG
CA report-only
Enforce
PIM
B2C step-up
Wallet sign-in
Monitoring, response & resilience
24/7
Telemetry
Detect 1
Detect 2
Pentest
Retest
MDR onboarding
DR test
Tabletop
Blockchain security
Multisig
Monitor
Timelocks
F
Audit
Fixes
Bounty
Staking DD
Anchor 1.x
Governance & compliance
D-01
Policies
Matrix
Ready
Remed.
SOC 2 Type I
TPRM
Evergreen
IA
Program mgmt & sustainment
Book
Threat model
Handover
LL
G1 W6
G2 W15
G3 W20
G4 W26
Notes: Bars are taken from task start and end weeks in the Project Plan (workbook Gantt shows all 150 tasks). Gate criteria: G1 W6 Mobilize exit; G2 W15 designs complete and critical exposures closed; G3 W20 build complete (pentest done, audit preliminary report, DR test); G4 W26 BAU acceptance with SOC 2 Type I fieldwork done and Type II period running. BG = break-glass; F = code freeze (W15); LL = lessons learned. Production changes avoid weeks 9-10.

## Slide 8: Workstream 1: OS & container hardening
Focus areas
Org guardrails: SCP, RCP, EC2 declarative policies, Control Tower controls (EBS encryption via controls, not declarative)
End-of-life: AL2 to zero; EKS node OS then version hops to 1.36
Golden AL2023 image to CIS L1; SSM before Inspector CIS and runtime agents
Kubernetes baseline, signed images, network and data protection
29 tasks. Tasks led by role: KHE 13, CSE 12, CPE 4
ID | Key task | Weeks | Lead
HD-02 | EKS end-of-support remediation (1.31 before 26 Nov; 1.34 per D-10... | W2-W5 | CSE
HD-06 | SSM enrolment fleet-wide (prerequisite for runtime agents, Patch... | W2-W6 | KHE
HD-16A | EKS node groups AL2 -> AL2023/Bottlerocket at 1.32 (non-prod W6-7,... | W6-W8 | CPE
HD-10 | Deploy org guardrails (sandbox/non-prod W7-W8; prod from W11) | W7-W12 | CSE
HD-16B | EKS version hops 1.32 -> 1.36 (before 1.32 extended EOS 23 Mar 2027) | W11-W18 | CSE
HD-17 | Kubernetes hardening rollout | W11-W15 | KHE
HD-15 | AL2 migration wave 2 (to zero AL2) | W17-W20 | CSE
HD-18 | Container supply chain: signing and verification | W16-W19 | KHE
Deliverables: Guardrails live in all OUs; AL2 count 0; all clusters on 1.36; CIS L1 baseline; signed-image enforcement; immutable log archive
References: CIS AWS Foundations v5.0.0 (automated) / v7.1.0 (delta); CIS AL2023 v1.0.0; CIS EKS v2.0.0; CIS Bottlerocket v1.0.0; Security Hub EC2.7/EC2.8/SSM.1/EKS.2/EKS.8/ECR.2
Notes: Accountable: Cloud & Platform Security Engineer (CSE). 29 tasks in this workstream. Tasks led by role: KHE 13, CSE 12, CPE 4. Key tasks shown with weeks from the Project Plan. HD-02 (W2-W5, lead CSE): EKS end-of-support remediation (1.31 before 26 Nov; 1.34 per D-10 before 2 Dec). Deliverable: No 1.31 clusters; 1.34 handled per D-10. HD-06 (W2-W6, lead KHE): SSM enrolment fleet-wide (prerequisite for runtime agents, Patch Manager, Inspector CIS). Deliverable: >=95% EC2 managed by SSM. HD-16A (W6-W8, lead CPE): EKS node groups AL2 -> AL2023/Bottlerocket at 1.32 (non-prod W6-7, prod W8). Deliverable: No AL2 EKS nodes. HD-10 (W7-W12, lead CSE): Deploy org guardrails (sandbox/non-prod W7-W8; prod from W11). Deliverable: Guardrails live in all OUs. HD-16B (W11-W18, lead CSE): EKS version hops 1.32 -> 1.36 (before 1.32 extended EOS 23 Mar 2027). Deliverable: All clusters on 1.36. HD-17 (W11-W15, lead KHE): Kubernetes hardening rollout. Deliverable: K8s baseline enforced. HD-15 (W17-W20, lead CSE): AL2 migration wave 2 (to zero AL2). Deliverable: AL2 count = 0 or approved exceptions. HD-18 (W16-W19, lead KHE): Container supply chain: signing and verification. Deliverable: Signed-image enforcement. References: CIS AWS Foundations v5.0.0 (automated) / v7.1.0 (delta); CIS AL2023 v1.0.0; CIS EKS v2.0.0; CIS Bottlerocket v1.0.0; Security Hub EC2.7/EC2.8/SSM.1/EKS.2/EKS.8/ECR.2.

## Slide 9: Workstream 2: Identity hardening
Focus areas
Break-glass first, then Conditional Access report-only, then enforce after FIDO2 enrolment
Zero standing admin: PIM incl. PIM for Groups to AWS IAM Identity Center
Customer identity: B2C hardening and step-up on withdrawals; External ID roadmap before May 2030
Workload identities, app-consent governance, wallet sign-in (EIP-4361)
21 tasks. Tasks led by role: IDC 9, ISE 8, PL 1, BSE 1, CPE 1, BSC 1
ID | Key task | Weeks | Lead
ID-01 | Break-glass accounts before any Conditional Access change | W0-W1 | ISE
ID-02 | Azure MFA Phase 2 (enforced): move user-run automation to workload... | W0-W2 | ISE
ID-08 | Entra Conditional Access baseline in report-only | W7-W10 | IDC
ID-10 | Enrol device-bound FIDO2 keys for admins | W9-W10 | ISE
ID-08B | Enforce Conditional Access baseline (after freeze) | W11-W12 | IDC
ID-13 | B2C hardening and step-up MFA on withdrawals | W9-W13 | IDC
ID-09 | PIM: zero standing privileged access (Entra, Azure, PIM for Groups... | W13-W15 | ISE
ID-14 | Customer identity roadmap: B2C to External ID (D-06) | W14-W15 | IDC
Deliverables: Phishing-resistant admin MFA; zero standing admins; step-up on withdrawals; External ID roadmap (D-06); hardened wallet sign-in
References: Entra licensing, auth strengths, emergency access; B2C FAQ (P2 retired 15 Mar 2026); External ID features; IAM Identity Center SCIM limits; EIP-4361; CIS Controls 5/6
Notes: Accountable: Identity & Security Operations Engineer (IR Lead) (ISE). 21 tasks in this workstream. Tasks led by role: IDC 9, ISE 8, PL 1, BSE 1, CPE 1, BSC 1. Key tasks shown with weeks from the Project Plan. ID-01 (W0-W1, lead ISE): Break-glass accounts before any Conditional Access change. Deliverable: Break-glass runbook + test record. ID-02 (W0-W2, lead ISE): Azure MFA Phase 2 (enforced): move user-run automation to workload identities. Deliverable: Automation identity register; remediated pipelines. ID-08 (W7-W10, lead IDC): Entra Conditional Access baseline in report-only. Deliverable: Report-only impact analysis. ID-10 (W9-W10, lead ISE): Enrol device-bound FIDO2 keys for admins. Deliverable: 100% admins enrolled. ID-08B (W11-W12, lead IDC): Enforce Conditional Access baseline (after freeze). Deliverable: CA baseline enforced. ID-13 (W9-W13, lead IDC): B2C hardening and step-up MFA on withdrawals. Deliverable: Step-up live; B2C logs in Splunk. ID-09 (W13-W15, lead ISE): PIM: zero standing privileged access (Entra, Azure, PIM for Groups -> AWS). Deliverable: Standing admins = break-glass only. ID-14 (W14-W15, lead IDC): Customer identity roadmap: B2C to External ID (D-06). Deliverable: D-06 roadmap. References: Entra licensing, auth strengths, emergency access; B2C FAQ (P2 retired 15 Mar 2026); External ID features; IAM Identity Center SCIM limits; EIP-4361; CIS Controls 5/6.

## Slide 10: Workstream 3: Monitoring, response & resilience
Focus areas
Day-one AWS detection independent of SIEM; interim 24/7 until MDR
Telemetry before detections: Splunk add-ons incl. Security Hub OCSF; Entra via Event Hub; B2C via Lighthouse
Detection-as-code, two detection waves, SOAR, purple team
On-chain and staking monitoring; IR plan, tabletop, DR test, pentest
25 tasks. Tasks led by role: DET 9, ISE 5, CSE 4, CPE 3, PMC 1, MDR 1, BSE 1, PEN 1
ID | Key task | Weeks | Lead
MR-00 | Interim 24/7 coverage until MDR is live | W0-W1 | ISE
MR-01 | Enable agentless AWS detection services org-wide (independent of SIEM) | W0-W1 | CSE
MR-11 | MDR onboarding in phases (EDR/GuardDuty/Entra first, Splunk... | W5-W13 | MDR
MR-07 | Onboard telemetry to Splunk | W7-W10 | DET
MR-13 | On-chain monitoring deployment (production) | W7-W9 | BSE
MR-08 | Detection wave 1: identity and control plane | W11-W13 | DET
MR-16 | Penetration test (cloud, EKS, dApp front-end, wallet sign-in, B2C... | W18-W19 | PEN
MR-18 | Tabletop exercises | W19-W20 | ISE
Deliverables: 24/7 MDR live; log sources 100% green; detections in production; IR plan and on-chain playbooks; DR restore evidence; pentest retest letter
References: NIST SP 800-61r3; MITRE ATT&CK; Splunkbase 1876/8642/3110/5082; GuardDuty Runtime Monitoring docs; SEAL Monitoring
Notes: Accountable: Identity & Security Operations Engineer (IR Lead) (ISE). 25 tasks in this workstream. Tasks led by role: DET 9, ISE 5, CSE 4, CPE 3, PMC 1, MDR 1, BSE 1, PEN 1. Key tasks shown with weeks from the Project Plan. MR-00 (W0-W1, lead ISE): Interim 24/7 coverage until MDR is live. Deliverable: On-call rota + paging + interim runbook. MR-01 (W0-W1, lead CSE): Enable agentless AWS detection services org-wide (independent of SIEM). Deliverable: Detection services coverage report. MR-11 (W5-W13, lead MDR): MDR onboarding in phases (EDR/GuardDuty/Entra first, Splunk notables after MR-07). Deliverable: 24/7 MDR live. MR-07 (W7-W10, lead DET): Onboard telemetry to Splunk. Deliverable: Log source register 100% green. MR-13 (W7-W9, lead BSE): On-chain monitoring deployment (production). Deliverable: On-chain monitors live. MR-08 (W11-W13, lead DET): Detection wave 1: identity and control plane. Deliverable: Wave-1 detections in prod. MR-16 (W18-W19, lead PEN): Penetration test (cloud, EKS, dApp front-end, wallet sign-in, B2C step-up). Deliverable: Pentest report. MR-18 (W19-W20, lead ISE): Tabletop exercises. Deliverable: After-action reports. References: NIST SP 800-61r3; MITRE ATT&CK; Splunkbase 1876/8642/3110/5082; GuardDuty Runtime Monitoring docs; SEAL Monitoring.

## Slide 11: Workstream 4: Blockchain security
Focus areas
Interim multisig hardening now; role matrix with timelocks, pause guardian and canceller
Signer hygiene after Bybit and Drift: clear signing, independent hash checks, no durable-nonce admin txs
Secure SDLC for Solidity and Rust/Anchor; verified builds; code freeze before audit
Custody (CCSS v9), staking oversight, hard-fork readiness, bug bounty, crypto-agility
30 tasks. Tasks led by role: BSE 18, BSC 5, CSO 4, CPE 1, SCA 1, ISE 1
ID | Key task | Weeks | Lead
BC-01 | Alpenglow readiness confirmation from staking provider (activates... | W0-W1 | BSE
BC-22 | Interim multisig hardening (Drift-pattern exposure) | W0-W2 | BSE
BC-07 | Staking provider due diligence | W6-W9 | BSE
BC-10 | Privileged on-chain roles under multisig and timelock (role matrix) | W11-W14 | BSE
BC-11 | Signer operations hardening | W13-W15 | BSE
BC-15 | Code freeze for audit scope | W15 | BSE
BC-16 | Smart-contract audit (Ethereum + Solana, parallel teams) | W16-W19 | SCA
BC-18 | Bug bounty and SEAL Safe Harbor decision (D-09) | W23-W24 | BSE
Deliverables: Privileged-role register; 100% upgrade/admin roles under multisig + timelock; audit + fix review; live bounty; fork runbook; PQ roadmap
References: BSSC SCS, KMS, NOS v2; CCSS v9.0; OWASP SC Top 10 2026; SEAL Frameworks; EIP-7002/7251/7702; Safe 1.5.0; Squads v4
Notes: Accountable: Blockchain Security Engineer (BSE). 30 tasks in this workstream. Tasks led by role: BSE 18, BSC 5, CSO 4, CPE 1, SCA 1, ISE 1. Key tasks shown with weeks from the Project Plan. BC-01 (W0-W1, lead BSE): Alpenglow readiness confirmation from staking provider (activates 21 Oct 2026). Deliverable: Provider confirmation + reward-delta check note. BC-22 (W0-W2, lead BSE): Interim multisig hardening (Drift-pattern exposure). Deliverable: Interim multisig hardening record. BC-07 (W6-W9, lead BSE): Staking provider due diligence. Deliverable: Staking provider assessment. BC-10 (W11-W14, lead BSE): Privileged on-chain roles under multisig and timelock (role matrix). Deliverable: 100% upgrade/admin roles under multisig+timelock. BC-11 (W13-W15, lead BSE): Signer operations hardening. Deliverable: Signer SOP + drill record. BC-15 (W15, lead BSE): Code freeze for audit scope. Deliverable: Frozen audit scope. BC-16 (W16-W19, lead SCA): Smart-contract audit (Ethereum + Solana, parallel teams). Deliverable: Audit report (preliminary). BC-18 (W23-W24, lead BSE): Bug bounty and SEAL Safe Harbor decision (D-09). Deliverable: Live bounty + D-09. References: BSSC SCS, KMS, NOS v2; CCSS v9.0; OWASP SC Top 10 2026; SEAL Frameworks; EIP-7002/7251/7702; Safe 1.5.0; Squads v4.

## Slide 12: Workstream 5: Governance & compliance
Focus areas
Regulatory go/no-go first: MiCA/DORA/PCI out of scope with conditions; custodial/MSB question answered
Version-controlled policies, unified control matrix, TPRM and vendor exit plans
SOC 2: independent readiness, Type I as of 21 Mar 2027, gap-free Type II
Three firms kept separate: implementation, readiness, attestation; IA reports to the Board
27 tasks. Tasks led by role: GRC 11, GRCC 5, PL 3, CSO 2, PMC 1, ISE 1, HRB 1, RDA 1, CPA 1, IA 1
ID | Key task | Weeks | Lead
GC-01 | Regulatory scope go/no-go (D-01) with counsel engaged in W0 | W0-W4 | GRC
GC-07 | SOC 2 scope, system description and period plan (D-08, D-12) | W5-W7 | GRC
GC-04 | Policy framework (version-controlled) | W5-W8 | GRCC
GC-06 | Third-party / ICT risk programme | W6-W9 | GRC
GC-05 | Unified control matrix | W8-W11 | GRCC
GC-13 | SOC 2 readiness assessment (independent firm) | W17-W18 | RDA
GC-15 | SOC 2 Type I (as-of Sun 21 Mar 2027) and Type II period start (Mon... | W22-W25 | CPA
GC-16 | Independent assurance review (third line) | W22-W24 | IA
Deliverables: Regulatory memo; policy set v1.0; control matrix; TPRM register; readiness report; SOC 2 Type I; IA report
References: AICPA TSC 2017 (2022 PoF); NIST CSF 2.0; ISO/IEC 27001:2022; CIS Controls v8.1; MiCA Art 61/143; DORA Art 2; FinCEN CVC guidance; OFAC VC guidance
Notes: Accountable: GRC & Risk Lead (2nd line) (GRC). 27 tasks in this workstream. Tasks led by role: GRC 11, GRCC 5, PL 3, CSO 2, PMC 1, ISE 1, HRB 1, RDA 1, CPA 1, IA 1. Key tasks shown with weeks from the Project Plan. GC-01 (W0-W4, lead GRC): Regulatory scope go/no-go (D-01) with counsel engaged in W0. Deliverable: Signed regulatory scope memo (D-01). GC-07 (W5-W7, lead GRC): SOC 2 scope, system description and period plan (D-08, D-12). Deliverable: Scope memo + draft system description. GC-04 (W5-W8, lead GRCC): Policy framework (version-controlled). Deliverable: Approved policy set v1.0. GC-06 (W6-W9, lead GRC): Third-party / ICT risk programme. Deliverable: TPRM procedure + tier-1 assessments. GC-05 (W8-W11, lead GRCC): Unified control matrix. Deliverable: Unified control matrix. GC-13 (W17-W18, lead RDA): SOC 2 readiness assessment (independent firm). Deliverable: Readiness report. GC-15 (W22-W25, lead CPA): SOC 2 Type I (as-of Sun 21 Mar 2027) and Type II period start (Mon 22 Mar 2027). Deliverable: Type I report (draft) + Type II period running. GC-16 (W22-W24, lead IA): Independent assurance review (third line). Deliverable: IA report. References: AICPA TSC 2017 (2022 PoF); NIST CSF 2.0; ISO/IEC 27001:2022; CIS Controls v8.1; MiCA Art 61/143; DORA Art 2; FinCEN CVC guidance; OFAC VC guidance.

## Slide 13: Workstream 6: Program mgmt & sustainment
Focus areas
Charter, interim budget and partner bookings in weeks 0-2
Risk appetite, threat model and CSF 2.0 gap baseline before design
Two ARB reviews; four signed gates
BAU handover, KPI dashboard, evergreen model, next-year roadmap
18 tasks. Tasks led by role: PL 14, PMC 2, GRC 2
ID | Key task | Weeks | Lead
PM-02A | Interim budget approval for long-lead commitments (D-17) | W0 | PL
PM-03 | Book long-lead partners and contractors (weeks 1-2) | W1-W2 | PL
PM-05 | Threat model (cloud, identity, on-chain, supply chain, insider) | W3-W5 | PL
PM-06 | Baseline gap assessment (CSF 2.0 current/target profile) | W3-W5 | GRC
PM-09A | ARB #1: guardrail, image, identity, telemetry designs | W6 | PL
PM-09B | ARB #2: network, Kubernetes, workload identity, CIAM, DR, SSDLC... | W8 | PL
PM-13 | Evergreen operating model live before SOC 2 period | W14-W16 | GRC
PM-12 | Runbooks and BAU handover per workstream | W21-W24 | PL
Deliverables: Charter; booked SOWs; risk appetite; threat model; ARB approvals; gate minutes; handover acceptance; FY roadmap
References: NIST CSF 2.0 GV; ISO 27001 clauses 5-10; IIA Three Lines
Notes: Accountable: Security Program Lead (PL). 18 tasks in this workstream. Tasks led by role: PL 14, PMC 2, GRC 2. Key tasks shown with weeks from the Project Plan. PM-02A (W0, lead PL): Interim budget approval for long-lead commitments (D-17). Deliverable: Approved interim budget. PM-03 (W1-W2, lead PL): Book long-lead partners and contractors (weeks 1-2). Deliverable: Signed SOWs / booked slots. PM-05 (W3-W5, lead PL): Threat model (cloud, identity, on-chain, supply chain, insider). Deliverable: Threat model + prioritised scenarios. PM-06 (W3-W5, lead GRC): Baseline gap assessment (CSF 2.0 current/target profile). Deliverable: Gap assessment + baseline KPIs. PM-09A (W6, lead PL): ARB #1: guardrail, image, identity, telemetry designs. Deliverable: ARB #1 approvals log. PM-09B (W8, lead PL): ARB #2: network, Kubernetes, workload identity, CIAM, DR, SSDLC designs. Deliverable: ARB #2 approvals log. PM-13 (W14-W16, lead GRC): Evergreen operating model live before SOC 2 period. Deliverable: Evergreen calendar + dashboards. PM-12 (W21-W24, lead PL): Runbooks and BAU handover per workstream. Deliverable: Signed handover acceptance. References: NIST CSF 2.0 GV; ISO 27001 clauses 5-10; IIA Three Lines.

## Slide 14: Team: 5.0 internal FTE, contractors for the build peak
Role | Type | FTE | Window | Leads | Certifications / evidence
Security Program Lead | Internal | 1.0 | W0-W26 | 18 | CISSP or CISM; PMP/PRINCE2 or equivalent...
Cloud & Platform Security Engineer | Internal | 1.0 | W0-W26 | 16 | AWS Certified Security - Specialty; CKS
Identity & Security Operations Engineer | Internal | 1.0 | W0-W26 | 15 | SC-300; SC-200 or Splunk ES Certified Admin...
GRC & Risk Lead | Internal | 1.0 | W0-W26 | 13 | CISA and/or CRISC; ISO 27001 Lead Implementer
Blockchain Security Engineer | Internal | 1.0 | W0-W26 | 20 | Public audit/contest track record (audit...
Contract Cloud/K8s Hardening Engineer | Contractor | 1.0 | W2-W22 | 13 | CKS; AWS Security Specialty; CIS-CAT experience
Contract Cloud Platform Security Engineer | Contractor | 1.0 | W3-W20 | 9 | AWS Security Specialty or SA Professional
Contract Detection Engineer (Splunk) | Contractor | 1.0 | W3-W24 | 9 | Splunk Certified Cybersecurity Defense...
Contract Identity Specialist (Entra/B2C) | Contractor | 0.5 | W3-W18 | 9 | SC-300; delivered B2C custom-policy projects
Contract Custody, Staking & Sanctions Specialist | Contractor | 1.0 | W3-W22 | 6 | CCSS auditor (CCSSA) or equivalent custody...
Contract Smart-Contract Security Engineer | Contractor | 0.5 | W5-W22 | 6 | Public audit or contest record on EVM and Solana
Contract SOC 2 Implementation Consultant | Contractor | 1.0 | W3-W24 | 5 | CISA; >=3 SOC 2 implementations
Contract PMO Coordinator | Contractor | 0.5 | W1-W26 | 4 | PMP/CAPM or equivalent
5.0
internal FTE (range 3-5)
6.5
contractor FTE at peak (8 roles)
133
contractor FTE-weeks
7
partner firms
Load rule: <=3 concurrent lead tasks per FTE and weighted load <=4.0 per FTE in every week; all roles pass (internal roles peak at the limit)
Notes: Internal: Program Lead, Cloud & Platform Sec Eng, Identity & SecOps Eng (IR lead), GRC & Risk Lead (2nd line), Blockchain Sec Eng = 5 FTE. Contractors: 8 roles peaking at 6.5 FTE, 133 FTE-weeks in total. Partners (0 program FTE): smart-contract audit firm, MDR, pentest firm, independent readiness assessor, SOC 2 CPA, regulatory counsel, outsourced internal audit. Business contributors outside program FTE: platform/app engineering (supporting only) and People Ops (leads HR controls). Live load matrices are on the Roles & Skills tab; internal roles reach the limit (3 leads, weighted 4.0) in several weeks, tracked as risk R22. Contractor dependency is tracked by KRI-1/KRI-2.

## Slide 15: Governance sized for a small team, with independent assurance
Steering Committee
Monthly + gates
Scope, budget, gates, risk acceptance, policy approval; quarterly board report
Architecture Review Board
Fortnightly (in CAB slot)
Approve designs and standards; time-boxed exceptions (<=90 days)
Contract Upgrade & Key Committee
Fortnightly + ad hoc <=4h
Internal chair; deploys, upgrades, signer/threshold/timelock, custody and staking changes
Change Advisory Board
Weekly; emergency <=2h
Production changes; freeze windows
Incident Response forum
24/7 (interim on-call, MDR)
Declare and contain; notify per D-01; invoke emergency pause
Independent assurance
Annual IA + SOC 2
IA reports to Board; CPA, readiness assessor and implementer are separate firms
1st line Engineers and control owners run controls
2nd line GRC Lead oversees, never tests own controls
3rd line Outsourced IA + SOC 2 CPA test independently
Decision rights, inputs and outputs per forum: Governance Model tab
Notes: Six forums with cadences sized for 5 internal FTE (the ARB meets in the first 30 minutes of the weekly CAB slot, fortnightly; the CUKC meets fortnightly plus ad hoc within 4 hours for emergencies). The Contract Upgrade & Key Committee has an internal chair (Head of Blockchain Engineering) and the Blockchain Security Engineer holds a security veto. Independence: SOC 2 implementation consultant, independent readiness assessor and the CPA are three different firms; outsourced internal audit reports directly to the Board/Audit Committee and tests both 1st- and 2nd-line controls.

## Slide 16: Evergreen model: monitor, measure, review, improve, assure
Monitor
Automated control health
Measure
Weekly KPI/KRI refresh
Review
Monthly Steering
Improve
CAPA, ARB, CUKC
Assure
IA + SOC 2 Type II
Calendar
Weekly
Evidence calendar, patch SLA, detection tuning, CAB, CUKC, on-chain alert review
Monthly
Steering + risk review, exception expiry, privileged access review, staking report
Quarterly
Access reviews, tabletop, restore tests, signer drill, benchmark/version check, board report
Semi-annual
Policy tranche, pause drill, custody/staking reassessment
Annual
SOC 2 Type II, pentest, full DR test, risk & fraud assessment, IA, management review
Re-assessment triggers
Contract deploy or upgrade
Hard fork or client release
New benchmark or vendor version
Major incident (ours or industry)
New or changed vendor
Regulatory change or new market
Signer, admin or key-person change
EOL announcement; exception expiry
Notes: The loop runs on automated control health (Security Hub CSPM, Inspector, GRC-platform tests, Splunk silent-source alerts, on-chain monitors), a weekly KPI/KRI refresh and monthly Steering review. Corrective actions are logged and design changes go through the ARB/CUKC; assurance comes from IA and the annual SOC 2 Type II. Exceptions are time-boxed to 90 days with one renewal at most. Policies live in git with semantic versions. The contractor-dependency KRI (critical runbooks without a trained internal owner) must be 0 by W24. The full calendar and trigger responses are on the Governance Model tab.

## Slide 17: KPIs: 25 measures, each with a target, data source and owner
Amazon Linux 2 / EOL OS instance count
0 (or approved exceptions with expiry) by W20
EKS clusters on a standard-support version
100% by W18
CIS AL2023 Level 1 pass rate
>=90% by W20
IMDSv2 coverage
100% of instances by W12
Security Hub CSPM security score
>=90% by W20
Production workloads running signed images
100% by W19
Admins using phishing-resistant MFA
100% by W12
Standing privileged admins
0 by W15
Customer withdrawals / payout-address changes protected by step-up MFA
100% of flows by W13
MTTD - identity high-severity events
Median <=15 min; p90 <=60 min from W14
MTTD - on-chain privileged events
Median <=5 min; p90 <=15 min from W13
MTTR - Sev-1 containment
Median <=4 h; p90 <=8 h from W17
Upgrade/admin on-chain roles under multisig + timelock
100% by W15
Staking - Ethereum: effectiveness vs provider SLA; slashing events
>= SLA; 0 slashing
SOC 2 automated control pass rate
>=95% by W20
Exceptions past expiry
0
Notes: 16 of the 25 KPIs are shown; all 25 plus 3 KRIs are on the KPIs tab, each with a definition, target, data source, frequency and proposed owner role. Current value and named owner are left blank for the program to fill in. Staking KPIs are measured against the staking provider's SLA; Solana metric definitions after Alpenglow are UNVERIFIED and get fixed in MR-14.

## Slide 18: What the independent review changed
Chart: 62 findings by severity
| Critical | High | Medium | Low
Findings | 7 | 26 | 22 | 7
Tasks grew from 109 in v1 to 150 in v2. 55 findings fixed or verified; 7 are partially fixed, contingent or awaiting validation, each with a named validation task.
Cloud
Runtime agents only after SSM; EKS split into node migration before the freeze, then version hops to 1.36 ahead of the 23 Mar 2027 hard stop
Identity & SOC
Interim 24/7 on-call from W0; FIDO2 keys ordered and enrolled before CA is enforced; Entra/B2C logs archived now; Security Hub OCSF uses its own Splunk add-on
Blockchain
Interim multisig hardening now; pause guardian kept outside timelocks; Alpenglow fee is per epoch; code freeze after timelocks; Anchor 1.x migration
Governance
Custodial/MSB question added to D-01; BIA, BCP and fraud risk assessment; three separate assurance firms; evergreen calendar live before the SOC 2 period
Notes: Four adversarial reviewers (cloud/OS & container 11, identity & monitoring 16, blockchain 15, governance/PMO 16 findings) plus 4 lead re-verification entries. Severity: 7 critical, 26 high, 22 medium, 7 low. After the fixes, the sequencing and load checks were re-run and all pass. Items still open are labelled on the Review Log tab: Bottlerocket CIS method, AWS Backup EKS support, Glamsterdam EIP list, post-Alpenglow Solana metrics, CrowdStrike AL2023/Bottlerocket support, Solana coverage claims of monitoring vendors, SOC 2 minimum period, and the contingent AML programme.

## Slide 19: Top risks and how the plan mitigates them
ID | Risk | Rating | Mitigation | Owner
R01 | AL2 workloads cannot migrate on time (app dependencies) | 16 | Containment (HD-03), two migration waves, time-boxed exceptions with expiry, CrowdStrike prevention | CSE
R06 | Small team overload / key-person dependency | 16 | Capacity rule enforced (<=3 leads and weighted <=4.0 per FTE); 8 contractors for build peaks; deputies named in RACI | PL
R04 | Signer-UI compromise or multisig social engineering (Bybit/Drift patterns) | 15 | BC-10 timelocks/thresholds/delegatecall guard/durable-nonce ban; BC-11 clear signing and independent hash check; MR-13 alerts | BSE
R17 | Business is custodial / an MSB -> FinCEN, state licensing, FTC Safeguards obligations not in plan | 15 | D-01 answers explicitly; re-plan at Gate 1 if yes | GRC
R02 | EKS forced upgrade after 26 Nov 2026 breaks workloads | 12 | HD-02 controlled 1.31->1.32 upgrade by W4; add-on testing; rollback | CSE
R05 | Smart-contract audit slot slips | 12 | Book in W1-2 (PM-03) sized by nSLOC; code freeze W15; parallel EVM/Solana teams; backup auditor shortlisted | PL
R08 | Splunk ingest/licence overrun (Entra non-interactive logs 5-10x; OCSF volumes) | 12 | Volume sizing in MR-03; filtering at Event Hub/HEC; tiered retention | ISE
Rating = likelihood x impact (1-5 each); 15+ is High. All 22 risks with owners are on the Risks and Decisions tab.
Notes: The seven highest-rated risks out of 22 are shown. The custodial/MSB risk (R17) is resolved by D-01 in W4. If the business turns out to be custodial or a money transmitter, Gate 1 triggers a re-plan to add an AML/licensing workstream. Team overload (R06/R22) is the structural risk: internal roles run at the capacity limit, so Steering is asked to pre-approve a descope list (HD-26, HD-30, BC-20, ID-17) if needed.

## Slide 20: Decisions requested from Steering
ID | Decision | Options | Due
D-17 | Contractor capacity envelope (8 contractors, 6.5 FTE peak, 133 FTE-weeks) vs descope | Approve / approve with descope list (HD-26, HD-30, BC-20, ID-17) / reject | W1 - Fri 30 Oct
D-10 | EKS 1.34 clusters and upgradePolicy | Upgrade to 1.35 before 2 Dec / EXTENDED at $0.60 per cluster-hr | W2 - Fri 6 Nov
D-14 | Hot-wallet caps and velocity limits | Per risk appetite tiers | W3 - Fri 13 Nov
D-01 | Regulatory scope: MiCA/DORA/PCI no-go conditions; custodial/MSB/state licensing/Safeguards Rule; OFAC | Out of scope with conditions / in scope (re-plan at G1) / partial | W4 - Fri 20 Nov
D-03 | MDR provider and 24/7 owner per alert source | Falcon Complete Next-Gen MDR / Splunk-integrated MDR / other | W4 - Fri 20 Nov
D-15 | Security services plan and cost (Security Hub per-resource, GuardDuty, Inspector, EKS extended, Splunk ingest) | Essentials / add-ons / reduced scope | W4 - Fri 20 Nov
D-02 | Entra licensing (admins, access-review population, workforce risk CA, workload identities) | P2 / ID Governance / Entra Suite / Workload ID Premium | W5 - Fri 27 Nov
D-05 | EKS node OS | AL2023 managed nodes / Bottlerocket / EKS Auto Mode | W4 - Fri 20 Nov
Approve today
Charter, scope and gate dates (W6, W15, W20, W26)
16 Immediate actions and their owners
Interim budget envelope (D-17)
Known gaps
Budget not costed (licences, partners, contractors)
Custodial/MSB status unknown until D-01
7 review items await validation
Notes: 17 decisions are in the decision log, each with an owning task and due week; the workbook checks that every decision is due on or before the first task that needs it. Shown here are the 8 decisions due by W5. D-17 (W1, Fri 30 Oct) approves the contractor envelope: 8 contractors, 6.5 FTE at peak, 133 FTE-weeks, with a pre-agreed descope list. D-10 (W2, Fri 6 Nov) decides whether 1.34 clusters are upgraded before 2 Dec or kept on extended support at $0.60 per cluster-hour. D-01 (W4, Fri 20 Nov) is the regulatory scope memo; a yes on custodial/MSB triggers a re-plan at Gate 1.