## Overview
Security Hardening & Evergreen Governance Program - Plan v2
Prepared 19 Oct 2026. Yellow cells are inputs. All dated/versioned facts are sourced on the Sources tab.
Program Week 1 start (input) | 2026-10-26
Program Week 26 end | 2027-04-25
Week 0 (Immediate) start | 2026-10-19
Goal | Deliver a decision-ready, staffed 26-week security program that (1) hardens OS and containers, (2) hardens security monitoring and response, and (3) installs an evergreen governance model, for an AWS-hosted Ethereum/Solana dApp business pursuing SOC 2.
Timeline | Week 0 = 19-25 Oct 2026 (Immediate actions). Week 1 starts Mon 26 Oct 2026; Week 26 ends Sun 25 Apr 2027. Weeks 9-10 (21 Dec 2026 - 3 Jan 2027) are reduced-capacity with a production change freeze (emergency changes only).
In scope | AWS multi-account org (Control Tower, Organizations, EC2 Linux, EKS, ECS/EC2 containers, data services, network, logging, backup); Microsoft Entra ID (workforce), Azure AD B2C (customers), IAM Identity Center; Splunk SIEM/SOAR, CrowdStrike EDR, MDR; Ethereum Solidity contracts and Solana Rust/Anchor programs, admin multisigs (Safe/Squads), MPC custody vendor oversight, staking-provider oversight; SOC 2 readiness and Type I; policies, TPRM, HR controls, training.
Out of scope | MiCA/DORA/PCI DSS build-out (go/no-go only, D-01); AML/money-transmission programme (contingent on D-01); running own validators; executing the B2C -> External ID migration (roadmap only); ISO 27001 certification (alignment only); Windows workloads; physical security; budget costing (envelope requested at Gate 1).
Headline numbers (live)
Total tasks | 150
Immediate actions (with owner + deadline) | 16
Workstreams | 6
Steering gates | 4
Internal program FTE | 5
Contractor FTE (peak concurrent) | 6.5
Contractor FTE-weeks | 133
Partner/firm engagements | 7
KPIs | 25
Decisions in log | 17
Risks in register | 22
Review findings logged | 62
Dependency violations (must be 0) | 0
Tasks ending after W26 (must be 0) | 0
Decision misalignments (must be 0) | 0
Role overloads (must be 0) | 0
Assumptions
• Non-EU firm; no EU solicitation of customers; SOC 2 is the primary compliance driver (user-confirmed). Confirmed or overturned by D-01 in W4.
• No cardholder data in scope (user-confirmed); any future card acceptance via hosted iframe/redirect would fall under PCI DSS v4.0.1 SAQ A.
• Amazon Linux 2 workloads remain in the fleet alongside AL2023 (user-confirmed); exact count from HD-01.
• Staking is delegated to a third-party staking provider (no self-run validators); treasury/hot wallets on a third-party MPC custody platform; admin keys in Safe (EVM) and Squads v4 (Solana) multisigs.
• Splunk remains the SIEM (Enterprise Security 8.x, SOAR available); CrowdStrike Falcon covers EC2. Microsoft Sentinel is not adopted, so its Azure-portal retirement (31 Mar 2027) is noted but not actioned.
• Security program team = 5.0 internal FTE plus contractors/partners; platform and application engineering teams implement changes (supporting role, outside program FTE).
• Assumed US-headquartered entity for OFAC/state-law purposes (to be confirmed in D-01).
• Whether the business is custodial for customer funds (withdrawal flows exist) is UNVERIFIED; D-01 answers custodial / FinCEN MSB / state licensing / FTC Safeguards Rule. Any 'yes' triggers a re-plan at Gate 1.
• Weeks 9-10 (21 Dec 2026 - 3 Jan 2027) are a production change freeze; design and non-prod work continues at reduced capacity.
• Capacity rule: each role leads at most round(3 x FTE) concurrent tasks and carries a weighted load (lead 1.0 + support 0.25 per task) of at most 4 x FTE in any week.
• Budget is not costed in this plan; licence uplifts (Entra P2/ID Governance, Security Hub per-resource pricing, EKS extended support, Splunk ingest) are flagged as decisions/risks.
Phases
Phase | Name | Start wk | End wk | Start date | Purpose
P0 | Immediate (pre-program) | 0 | 2 | 2026-10-19 | Close exposures that land before or at the very start of the program
P1 | Mobilize | 1 | 6 | 2026-10-26 | Charter, budget, partner bookings, scope, risk appetite, threat model, baseline
P2 | Assess & Design | 2 | 10 | 2026-11-02 | Gap assessment and ARB-approved designs per workstream
P3 | Build & Harden | 6 | 20 | 2026-11-30 | Guardrails, hardening, identity, telemetry, on-chain controls
P4 | Monitor & Validate | 10 | 22 | 2026-12-28 | Detections, pentest, audit, tabletop, DR test, SOC 2 readiness
P5 | Operationalize & Handover | 14 | 26 | 2027-01-25 | Evergreen model, runbooks, BAU handover, SOC 2 Type I / Type II start
Steering Committee gates (signed)
Gate | Week | Name | Exit criteria | Gate task | Gate date (Fri)
G1 | 6 | Mobilize exit | Charter and interim budget approved; long-lead partners booked; D-01 regulatory scope signed (custodial/MSB answered); risk appetite approved; threat model and CSF 2.0 gap baseline issued; zero EKS 1.31 clusters; agentless AWS detection services in 100% of accounts/Regions; interim 24/7 on-call and paging live; break-glass tested; interim multisig hardening complete. | PM-08 | 2026-12-04
G2 | 15 | Design complete & critical exposures closed | ARB #1 and #2 approvals; org guardrails live in all OUs; Conditional Access enforced with phishing-resistant admin MFA; telemetry sources 100% onboarded; MDR 24/7 live; on-chain monitors live; custody policy engine configured; no AL2 EKS nodes; Inspector CIS baseline captured; policies v1.0 approved; control matrix, TPRM and risk/exception registers live. | PM-10 | 2027-02-05
G3 | 20 | Build complete | 100% upgrade/admin on-chain roles under multisig + timelock (pause guardian per role matrix); detection waves 1-2 in production; pentest executed; smart-contract audit preliminary report received; Kubernetes baseline enforced; all clusters on 1.36; DR restore test passed; SOC 2 readiness assessment complete. | PM-11 | 2027-03-12
G4 | 26 | Program close & BAU acceptance | BAU handover signed; KPIs at target or exceptions approved; SOC 2 Type I fieldwork done; Type II engagement letter signed with period dates and first in-period evidence for every recurring control; IA report reviewed by Board/Audit Committee; bug bounty live; AL2 count 0 or approved exceptions; review-log items closed or formally deferred. | PM-16 | 2027-04-23
Formulas:
Start date = B4+7*([Start wk]-1)
Purpose = B4+7*([Name]-1)+4

## Project Plan
Project Plan - 150 tasks; End wk, dates and checks are formulas; Gantt W0-W26 via conditional formatting
Status column has a dropdown. Dependency check = every dependency ends before this task starts. Weeks 9-10 shaded = production change freeze.
Legend: | HD OS & Container Hardening | ID Identity Hardening | MR Security Monitoring, Response & Resilience | BC Blockchain Security | GC Governance & Compliance | PM Program Management & Sustainment
[22 empty] | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19
ID | Phase | Workstream | Task | Key activities | Start wk | Duration (wks) | End wk | Dependencies (IDs) | Latest dependency end | Dependency check | End-week check | Start date | End date | Lead role | Supporting roles | Skill set required | Deliverable | Benchmark / standard reference | Status | Immediate action (owner / deadline) | Support (delimited) | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PM-01 | P0 Immediate (pre-program) | PM | Stand up Immediate-actions cell and name owners | Daily 15-min stand-up for Immediate actions; owners/deadlines confirmed by exec sponsor | 0 | 1 | 0 |  |  | OK | OK | 2026-10-19 | 2026-10-23 | PL | CSE; ISE; BSE; GRC | Program management | Immediate-actions tracker with owners | NIST CSF 2.0 GV.RR | Not started | Owner PL - Fri 23 Oct 2026 | ;CSE;ISE;BSE;GRC;
ID-00 | P0 Immediate (pre-program) | ID | Order FIDO2 security keys and signer hardware wallets | Device-bound FIDO2 keys (approved models/AAGUIDs) for break-glass, admins, spares; clear-signing hardware wallets for on-chain signers | 0 | 1 | 0 |  |  | OK | OK | 2026-10-19 | 2026-10-23 | PL | ISE; BSE | Procurement | Purchase orders; delivery tracked to W3 | Entra passkey (FIDO2) docs; SEAL Wallet Security | Not started | Owner PL - order by Fri 23 Oct 2026 | ;ISE;BSE;
GC-01 | P0 Immediate (pre-program) | GC | Regulatory scope go/no-go (D-01) with counsel engaged in W0 | Counsel opinion: MiCA Art 61 reverse solicitation/ESMA guidelines; DORA (only via MiCA authorisation); PCI DSS (no CHD); US: custodial vs non-custodial, FinCEN MSB status, state money-transmission, OFAC, FTC Safeguards Rule, NYDFS; any 'yes' triggers re-plan at Gate 1 | 0 | 5 | 4 |  |  | OK | OK | 2026-10-19 | 2026-11-20 | GRC | LEG; PL | Regulatory analysis | Signed regulatory scope memo (D-01) | MiCA Art 61/143; ESMA35-1872330276-2030; DORA Art 2(1)(f); PCI DSS v4.0.1; FinCEN FIN-2019-G001; OFAC VC guidance | Not started | Owner GRC - signed by Steering Fri 20 Nov 2026 (W4) | ;LEG;PL;
BC-01 | P0 Immediate (pre-program) | BC | Alpenglow readiness confirmation from staking provider (activates 21 Oct 2026) | By Tue 20 Oct: written confirmation of BLS pubkey registration, VAT funding (0.8 SOL burned PER EPOCH above rent-exempt, auto top-up), Agave-4.3.0-based client (Firedancer/Frankendancer unsupported during migration), VAT pass-through in commission; pre-approved re-delegation fallback; verify rewards for epochs 1065-1066 | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | BSE |  | Solana staking, vendor management | Provider confirmation + reward-delta check note | solana.com/upgrades/alpenglow; BSSC NOS v2 | Not started | Owner BSE - confirmation Tue 20 Oct 2026; reward check Fri 30 Oct 2026 | ;;
BC-02 | P0 Immediate (pre-program) | BC | Staking authority inventory and on-chain verification | Every Ethereum validator: credential type (0x00/0x01/0x02) and that 0x01/0x02 point to our custody address; plan 0x00 change signed by us; provider-owned 0x01 -> exit/re-deposit via BC-19; Solana stake withdraw authority = our MPC vault; interim alerts on EIP-7002 requests and authority changes | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | BSE | CSO | Ethereum/Solana staking internals | Staking authority register (signed) | EIP-7002; EIP-7251; Anza delegate-stake & vote-account docs; CCSS v9 | Not started | Owner BSE - Fri 30 Oct 2026 | ;CSO;
BC-22 | P0 Immediate (pre-program) | BC | Interim multisig hardening (Drift-pattern exposure) | Raise Safe/Squads thresholds to policy minimum; enable Squads time lock on upgrade authorities; ban durable-nonce/pre-signed admin txs; confirm signer set and devices; emergency CUKC path | 0 | 3 | 2 |  |  | OK | OK | 2026-10-19 | 2026-11-06 | BSE | CSO | Safe/Squads operations | Interim multisig hardening record | SEAL Multisig framework; Squads v4 docs | Not started | Owner BSE - Fri 6 Nov 2026 | ;CSO;
HD-01 | P0 Immediate (pre-program) | HD | EOL inventory: AL2 hosts/AMIs, EKS versions and upgradePolicy (D-10) | Org-wide Config query + SSM inventory + EKS API: AL2 instances/AMIs/launch templates, ECS AMIs, cluster versions (1.31-1.37), node AMI types, per-cluster upgradePolicy (STANDARD auto-upgrades at end of standard support; EXTENDED costs $0.60/cluster-hr); D-10 recommendation | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | CSE | ENG | AWS Config, EKS | EOL register + D-10 recommendation | AL2 FAQ (EOS 2026-06-30); EKS kubernetes-versions page; SH EKS.2/EKS.9 | Not started | Owner CSE - Fri 30 Oct 2026 | ;ENG;
MR-01 | P0 Immediate (pre-program) | MR | Enable agentless AWS detection services org-wide (independent of SIEM) | Delegated admin; GuardDuty all accounts/Regions incl. EKS audit-log monitoring, S3 Protection, Malware Protection for EC2; Security Hub CSPM (FSBP + CIS AWS v5.0.0) and Security Hub; Inspector EC2/ECR/Lambda; Access Analyzer external + internal; Config all Regions; org CloudTrail. Runtime agents follow in MR-01B | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | CSE | ISE | AWS security services | Detection services coverage report | SH GuardDuty.1/.5/.8/.10, Config.1, CloudTrail.1, Inspector.1-.4; CIS AWS v5.0.0 | Not started | Owner CSE - Fri 30 Oct 2026 | ;ISE;
MR-21 | P0 Immediate (pre-program) | MR | Archive Entra and B2C logs before they expire | Diagnostic settings for Entra (sign-in incl. non-interactive/SP/MI, audit, risk, Graph activity) and B2C (via Azure Lighthouse) to immutable storage; Entra keeps only 30 days on P1/P2 | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | CSE | ISE | Azure Monitor | Log archive live (evidence preserved) | Entra data-retention reference; B2C Azure Monitor docs | Not started | Owner CSE - Fri 30 Oct 2026 | ;ISE;
MR-00 | P0 Immediate (pre-program) | MR | Interim 24/7 coverage until MDR is live | On-call rota incl. holiday weeks; paging tool; GuardDuty/Security Hub/Falcon high-severity alerts via EventBridge/SNS to pager; interim IR runbook (severity, contacts, SEAL 911, counsel) | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | ISE | BSE | SOC operations | On-call rota + paging + interim runbook | NIST SP 800-61r3; CSF 2.0 DE.CM/RS.MA | Not started | Owner ISE - Fri 30 Oct 2026 | ;BSE;
ID-01 | P0 Immediate (pre-program) | ID | Break-glass accounts before any Conditional Access change | 2 cloud-only permanent Global Admins with FIDO2/certificate auth distinct from admins; excluded from blocking CA; Sev-0 sign-in alert via Log Analytics to pager until Splunk; AWS break-glass: management-account root (2 FIDO2) + emergency role with alarm; test every 90 days | 0 | 2 | 1 |  |  | OK | OK | 2026-10-19 | 2026-10-30 | ISE |  | Entra ID, AWS IAM | Break-glass runbook + test record | Microsoft emergency-access guidance; mandatory Azure MFA; SH IAM.4/IAM.6 | Not started | Owner ISE - Fri 30 Oct 2026 | ;;
ID-02 | P0 Immediate (pre-program) | ID | Azure MFA Phase 2 (enforced): move user-run automation to workload identities | Find CLI/PowerShell/IaC/SDK automation running as users (breaking now); migrate to managed identities/service principals with federated credentials (exempt) | 0 | 3 | 2 |  |  | OK | OK | 2026-10-19 | 2026-11-06 | ISE | ENG | Entra workload identities | Automation identity register; remediated pipelines | Microsoft mandatory MFA (Phase 2) | Not started | Owner ISE - Fri 6 Nov 2026 | ;ENG;
PM-02 | P1 Mobilize | PM | Program charter, scope, success criteria and Steering ToR | Charter; scope/out-of-scope; Steering membership and decision rights | 1 | 1 | 1 | PM-01 | 0 | OK | OK | 2026-10-26 | 2026-10-30 | PL | GRC; PMC | Program management | Signed charter | NIST CSF 2.0 GV.OC/GV.RR | Not started |  | ;GRC;PMC;
PM-02A | P0 Immediate (pre-program) | PM | Interim budget approval for long-lead commitments (D-17) | CFO approves envelope for partners, 8 contractors (6.5 FTE peak) and licences booked in W1-2 (D-17); full budget at Gate 1 | 0 | 1 | 0 |  |  | OK | OK | 2026-10-19 | 2026-10-23 | PL | PMC | Finance | Approved interim budget | NIST CSF 2.0 GV.RR-03 | Not started |  | ;PMC;
PM-03 | P1 Mobilize | PM | Book long-lead partners and contractors (weeks 1-2) | Sign: smart-contract auditor (slot W16-W19, sized by nSLOC; >4k nSLOC -> parallel teams), SOC 2 CPA, independent readiness assessor, MDR, pentest (W18), GRC platform trial, contractors (KHE/CPE/DET/IDC/CSO/BSC/GRCC/PMC) | 1 | 2 | 2 | PM-01, PM-02A | 0 | OK | OK | 2026-10-26 | 2026-11-06 | PL | GRC; BSE; ISE; PMC | Procurement | Signed SOWs / booked slots | NIST CSF 2.0 GV.SC | Not started |  | ;GRC;BSE;ISE;PMC;
PM-04 | P1 Mobilize | PM | Risk appetite statement and tolerances (D-14) | On-chain loss tolerance, hot-wallet caps, velocity limits, max time-to-pause, patch SLAs, exception limits (max 90 days, one renewal) | 2 | 2 | 3 | PM-02 | 1 | OK | OK | 2026-11-02 | 2026-11-13 | PL | GRC; BSE | Risk management | Approved risk appetite statement | NIST CSF 2.0 GV.RM; ISO 27001 6.1 | Not started |  | ;GRC;BSE;
PM-07 | P1 Mobilize | PM | RACI, RAID log, interim exception log and operating rhythm | RACI; weekly status; RAID log; interim exception log; change calendar incl. W9-W10 freeze | 2 | 1 | 2 | PM-02 | 1 | OK | OK | 2026-11-02 | 2026-11-06 | PMC | PL | PMO | RACI + RAID + interim exception log | ISO 27001 5.3 | Not started |  | ;PL;
PM-05 | P1 Mobilize | PM | Threat model (cloud, identity, on-chain, supply chain, insider) | Signer-UI compromise (Bybit), durable-nonce pre-signing (Drift), EIP-7702 delegation phishing, DPRK IT workers, domain/front-end hijack, CI/CD poisoning, ransomware, B2C account takeover, helpdesk reset fraud | 3 | 3 | 5 | PM-02 | 1 | OK | OK | 2026-11-09 | 2026-11-27 | PL | CSE; ISE; BSE | Threat modelling | Threat model + prioritised scenarios | MITRE ATT&CK; OWASP SC Top 10 2026; SEAL Frameworks | Not started |  | ;CSE;ISE;BSE;
PM-06 | P1 Mobilize | PM | Baseline gap assessment (CSF 2.0 current/target profile) | CSF 2.0 profiles; CIS Controls v8.1 IG1/IG2; Security Hub CSPM baseline; Inspector; identity and on-chain gaps | 3 | 3 | 5 | PM-02, MR-01 | 1 | OK | OK | 2026-11-09 | 2026-11-27 | GRC |  | Assessment | Gap assessment + baseline KPIs | NIST CSF 2.0; CIS Controls v8.1 | Not started |  | ;;
GC-02 | P1 Mobilize | GC | Governance operating model and forum ToRs | Steering, ARB (fortnightly), CUKC (fortnightly + ad hoc, internal chair), CAB (weekly), IR forum, independent assurance; three lines; decision rights | 3 | 2 | 4 | PM-02, PM-07 | 2 | OK | OK | 2026-11-09 | 2026-11-20 | PL | GRC | Governance design | Governance model + ToRs | NIST CSF 2.0 GV.RR; ISO 27001 5.1-5.3; IIA Three Lines | Not started |  | ;GRC;
MR-02 | P1 Mobilize | MR | MDR selection and contract (D-03) | Falcon Complete Next-Gen MDR vs Splunk-integrated MDR; named 24/7 owner per alert source (incl. Splunk notables); acknowledge/contain SLAs; authority to disable accounts/isolate hosts; escalation to CUKC | 3 | 2 | 4 | PM-03 | 2 | OK | OK | 2026-11-09 | 2026-11-20 | ISE | PL | SOC operations, vendor evaluation | Signed MDR contract (D-03) | NIST SP 800-61r3; CSF 2.0 DE/RS | Not started |  | ;PL;
MR-23 | P1 Mobilize | MR | Security services cost review before trials end (D-15) | Security Hub per-resource pricing, GuardDuty/Inspector, EKS extended support, Splunk ingest sizing; plan selection | 3 | 2 | 4 | MR-01 | 1 | OK | OK | 2026-11-09 | 2026-11-20 | PMC |  | Cost analysis | D-15 cost decision | Security Hub pricing; EKS pricing | Not started |  | ;;
GC-03 | P1 Mobilize | GC | GRC platform selection (D-04) | Vanta/Drata/Secureframe: AWS, Entra (licence/role needs), GitHub, HRIS integrations; pricing | 3 | 2 | 4 | PM-03 | 2 | OK | OK | 2026-11-09 | 2026-11-20 | GRCC | GRC | GRC tooling | GRC platform decision (D-04) | AICPA TSC 2017 (2022 PoF) | Not started |  | ;GRC;
GC-18 | P1 Mobilize | GC | Business impact analysis (BIA) | Critical services, dependencies (custody, staking, RPC, Splunk), RTO/RPO, tolerable on-chain downtime | 4 | 2 | 5 | PM-02 | 1 | OK | OK | 2026-11-16 | 2026-11-27 | GRC | PL; CSE; BSE | BC planning | Approved BIA | NIST CSF 2.0 ID.AM/RC; ISO 27001 A.5.30 | Not started |  | ;PL;CSE;BSE;
GC-20 | P1 Mobilize | GC | Board oversight of cyber risk | Board/Audit Committee terms; quarterly cyber report format; first briefing | 5 | 2 | 6 | PM-02 | 1 | OK | OK | 2026-11-23 | 2026-12-04 | PL | GRC | Board reporting | Board reporting cadence + first pack | SOC 2 CC1.2; NIST CSF 2.0 GV.OV | Not started |  | ;GRC;
GC-08 | P1 Mobilize | GC | Change management / CAB live | CAB ToR; change types; emergency CAB; freeze rules; link to CUKC for on-chain changes | 5 | 2 | 6 | GC-02 | 4 | OK | OK | 2026-11-23 | 2026-12-04 | PMC | PL | ITSM | CAB procedure live | SOC 2 CC8.1; ISO 27001 A.8.32 | Not started |  | ;PL;
PM-08 | P1 Mobilize | PM | Gate 1 - Mobilize exit (Steering, W6) | Criteria in Overview: charter + budget; partners booked; D-01 signed; risk appetite; threat model + gap baseline; 1.31 clusters gone; agentless detection 100% accounts; interim 24/7 live; break-glass tested; interim multisig hardening done | 6 | 1 | 6 | PM-02A, PM-03, PM-04, PM-05, PM-06, GC-01, GC-02, HD-02, MR-01, MR-00, ID-01, BC-22 | 5 | OK | OK | 2026-11-30 | 2026-12-04 | PL | PMC | Governance | Signed Gate 1 minute | Program governance | Not started |  | ;PMC;
HD-04 | P2 Assess & Design | HD | Org guardrail design: SCPs, RCPs, declarative policies, Control Tower controls | SCP: protect CloudTrail/GuardDuty/Config, allow guardduty:SendSecurityTelemetry, region allowlist, block Identity Store writes; RCP data perimeter; declarative: IMDSv2 (hop limit set per launch template: EKS 1, ECS bridge 2), snapshot/AMI BPA, VPC BPA with exclusions, serial console, allowed images (audit mode first); EBS default encryption via Control Tower/Config + automation (not a declarative attribute) | 3 | 3 | 5 | HD-01, PM-02 | 1 | OK | OK | 2026-11-09 | 2026-11-27 | CSE | KHE | AWS Organizations policy design | Guardrail design (ARB pack) | SH EC2.7/EC2.8/EC2.170/S3.1; CIS AWS v5.0.0; declarative policy docs | Not started |  | ;KHE;
HD-05 | P2 Assess & Design | HD | Hardened image standard and EKS node OS decision (D-05) | CIS AL2023 v1.0.0 L1; AL2023 vs Bottlerocket vs EKS Auto Mode for nodes; CIS EKS v2.0.0 / Auto Mode v1.0.0; Inspector CIS is x86_64-oriented and excludes Bottlerocket -> alternate evidence; CrowdStrike AL2023/Bottlerocket support in writing | 2 | 3 | 4 | HD-01 | 1 | OK | OK | 2026-11-02 | 2026-11-20 | KHE | CSE | CIS benchmarks | Image standard + D-05 | CIS AL2023 v1.0.0; CIS Bottlerocket v1.0.0; CIS EKS v2.0.0 | Not started |  | ;CSE;
HD-24 | P2 Assess & Design | HD | EKS upgrade-readiness matrix per version hop | Per hop 1.32->1.36: add-ons, Karpenter/CA, deprecated APIs, cgroup v2, containerd 2.x, ingress controller replacement; rollback limits | 2 | 3 | 4 | HD-01 | 1 | OK | OK | 2026-11-02 | 2026-11-20 | KHE | ENG | EKS | Upgrade-readiness matrix | EKS kubernetes-versions & upgrade docs | Not started |  | ;ENG;
HD-06 | P2 Assess & Design | HD | SSM enrolment fleet-wide (prerequisite for runtime agents, Patch Manager, Inspector CIS) | Instance profiles with AmazonSSMManagedInstanceCore + AmazonInspector2ManagedCisPolicy as primary path; DHMC where no profile (needs IMDSv2); per-instance IMDSv2 conversion where compatible; VPC endpoints | 2 | 5 | 6 | HD-01 | 1 | OK | OK | 2026-11-02 | 2026-12-04 | KHE | ENG | Systems Manager | >=95% EC2 managed by SSM | SH SSM.1; Inspector CIS prerequisites | Not started |  | ;ENG;
HD-22 | P2 Assess & Design | HD | Immutable log archive | Log Archive account; S3 Object Lock; CloudTrail data events (critical S3/KMS/Secrets); log-file validation; KMS encryption; retention by log class | 3 | 3 | 5 | MR-01 | 1 | OK | OK | 2026-11-09 | 2026-11-27 | CPE |  | AWS logging | Immutable log archive | SH CloudTrail.2/.4, S3.5; CIS AWS v5.0.0 | Not started |  | ;;
HD-02 | P1 Mobilize | HD | EKS end-of-support remediation (1.31 before 26 Nov; 1.34 per D-10 before 2 Dec) | Controlled 1.31->1.32 upgrade (last AL2-AMI version); add-on compatibility; 1.34 clusters upgraded to 1.35 or upgradePolicy set to EXTENDED per D-10; rollback plan | 2 | 4 | 5 | HD-01 | 1 | OK | OK | 2026-11-02 | 2026-11-27 | CSE | KHE; ENG | EKS upgrades | No 1.31 clusters; 1.34 handled per D-10 | EKS kubernetes-versions page; SH EKS.2/EKS.9 | Not started | Owner CSE - 1.31 upgraded by Fri 20 Nov 2026; 1.34 by Fri 27 Nov 2026 | ;KHE;ENG;
HD-03 | P1 Mobilize | HD | AL2 containment and migration backlog | Tag/isolate remaining AL2; CrowdStrike prevention policy; restrict SGs; owners/dates per workload; time-boxed exceptions | 2 | 2 | 3 | HD-01 | 1 | OK | OK | 2026-11-02 | 2026-11-13 | CSE | ENG | Linux ops, CrowdStrike | AL2 backlog + exceptions | AL2 FAQ; CIS Controls v8.1 2.2/7 | Not started | Owner CSE - Fri 6 Nov 2026 | ;ENG;
HD-07 | P2 Assess & Design | HD | Network baseline design | VPC segmentation, TGW route domains, Network Firewall egress allowlist, NAT, VPC endpoints, WAF managed rules, SG standards, flow logs, Route 53 Resolver DNS Firewall | 6 | 2 | 7 | PM-05 | 5 | OK | OK | 2026-11-30 | 2026-12-11 | KHE | CSE | AWS networking | Network design (ARB pack) | SH EC2.2/EC2.6/EC2.9/ELB.16/WAF.10/WAF.11/NetworkFirewall.2/.4/.5; CIS Controls 12/13 | Not started |  | ;CSE;
HD-08 | P2 Assess & Design | HD | Kubernetes security baseline design (D-11) | PSA restricted; admission policy (ValidatingAdmissionPolicy vs Kyverno) + signature verifier (D-11); NetworkPolicies; private endpoint; access entries; audit logs; KMS secrets encryption (no SH control - custom Config rule); Pod Identity/IRSA | 5 | 2 | 6 | HD-05 | 4 | OK | OK | 2026-11-23 | 2026-12-04 | CSE | KHE | Kubernetes security | K8s baseline design (ARB pack) | CIS EKS v2.0.0; CIS Kubernetes v2.1.0; SH EKS.1/EKS.8 | Not started |  | ;KHE;
HD-09 | P2 Assess & Design | HD | CIS AWS Foundations v7.1.0 delta vs automated v5.0.0 | Map deltas; custom Config rules or manual evidence; feed control matrix | 6 | 2 | 7 | PM-06 | 5 | OK | OK | 2026-11-30 | 2026-12-11 | KHE | GRCC | CIS benchmarks | CIS v7.1.0 delta register | CIS AWS Foundations v7.1.0; Security Hub CIS docs | Not started |  | ;GRCC;
HD-27 | P2 Assess & Design | HD | Control Tower currency, drift and account vending baseline | Landing-zone version; drift remediation; account factory baseline; OU structure for staged guardrails | 6 | 4 | 9 | HD-04 | 5 | OK | OK | 2026-11-30 | 2026-12-25 | CSE | KHE | Control Tower | Control Tower baseline report | AWS Control Tower docs | Not started |  | ;KHE;
ID-03 | P2 Assess & Design | ID | Entra licensing and workforce identity design (D-02) | D-02 covers: P2/ID Governance for admins and for every user in access reviews, P2 for workforce risk-based CA, Workload ID Premium for risky SPs; CA baseline; authentication strengths (device-bound FIDO2, AAGUID allowlist); PIM incl. PIM for Groups | 3 | 3 | 5 | ID-01, PM-03 | 2 | OK | OK | 2026-11-09 | 2026-11-27 | IDC | ISE | Entra ID architecture | Identity design + D-02 | Entra licensing; authentication strengths; CIS Controls 5/6 | Not started |  | ;ISE;
ID-04 | P2 Assess & Design | ID | AWS workforce access design (IAM Identity Center) incl. JIT approach (D-16) | Entra SAML + SCIM (flat groups; 1-yr SCIM token rotation diarised); permission sets; JIT: PIM for Groups via SCIM (accept delay) vs alternative (verify maintenance); SCP blocks Identity Store writes; no IAM users/keys for humans | 3 | 3 | 5 | ID-01, HD-01 | 1 | OK | OK | 2026-11-09 | 2026-11-27 | ISE | CSE | IAM Identity Center | AWS access design + D-16 | IAM Identity Center Entra/SCIM docs; SH IAM.1/.2/.4/.8/.22 | Not started |  | ;CSE;
ID-05 | P2 Assess & Design | ID | Workload identity and secrets design | EKS Pod Identity (IRSA for Fargate/Windows); CI/CD OIDC federation; Secrets Manager rotation; KMS key policies | 6 | 2 | 7 | ID-04 | 5 | OK | OK | 2026-11-30 | 2026-12-11 | ISE | CSE; ENG | AWS IAM, EKS | Workload identity design | EKS Pod Identity docs; SH SecretsManager.1/.3, KMS.3/.4 | Not started |  | ;CSE;ENG;
ID-06 | P2 Assess & Design | ID | Customer identity (Azure AD B2C) assessment and custom-policy security review | Policies in git with CI; policy keys; API-connector auth; redirect URIs; ROPC off; MFA coverage; risk gap after P2 retirement (15 Mar 2026); fraud/bot vendor (D-13); step-up design (acr_values/max_age, server-side auth_time check bound to transaction); External ID options | 4 | 4 | 7 | PM-03 | 2 | OK | OK | 2026-11-16 | 2026-12-11 | IDC | ISE | B2C/IEF, CIAM | B2C assessment + step-up design + D-13 | B2C FAQ; B2C claim resolvers; External ID supported features; OWASP ASVS | Not started |  | ;ISE;
ID-07 | P2 Assess & Design | ID | Wallet sign-in design (SIWE / Sign-In With Solana) | EIP-4361 (Final) verification; nonce/replay store; domain/URI/chain-id binding; EIP-1271 for contract wallets; verifier API from B2C policy or custom OIDC IdP; no EIP-7702 authorisation prompts | 8 | 2 | 9 | ID-06 | 7 | OK | OK | 2026-12-14 | 2026-12-25 | BSE | BSC | Web3 auth | Wallet sign-in design | EIP-4361; EIP-1271; EIP-7702 security considerations | Not started |  | ;BSC;
ID-18 | P2 Assess & Design | ID | App consent and service-principal governance | User consent off; admin-consent workflow; app inventory; SP credential expiry/creation alerts | 6 | 3 | 8 | ID-03 | 5 | OK | OK | 2026-11-30 | 2026-12-18 | ISE |  | Entra app governance | App governance baseline | Entra app consent docs; CIS Controls 6 | Not started |  | ;;
MR-03 | P2 Assess & Design | MR | Logging and telemetry architecture for Splunk | Splunk Add-on for AWS 8.2.x (CloudTrail/VPC/Config); Splunk Add-on for AWS Security Hub (OCSF via EventBridge->HEC); Entra via Event Hub (MS Cloud Services add-on 6.3.x) incl. NonInteractive/SP/MI sign-ins, risk, Graph activity; B2C (Audit, SignIn) via Lighthouse; CrowdStrike Event Streams; on-chain alert webhooks; retention; volume sizing and filtering | 3 | 3 | 5 | MR-01, PM-03 | 2 | OK | OK | 2026-11-09 | 2026-11-27 | ISE | DET | Splunk architecture | Telemetry architecture + log source register | Splunkbase 1876/8642/3110/5082; Entra Event Hub docs; B2C Azure Monitor docs | Not started |  | ;DET;
MR-04 | P2 Assess & Design | MR | Detection use-case catalogue mapped to threat model and ATT&CK | Identity, control plane, workload, on-chain use cases; ESCU baseline | 6 | 2 | 7 | PM-05, MR-03 | 5 | OK | OK | 2026-11-30 | 2026-12-11 | DET | ISE; BSE | Detection engineering | Use-case catalogue | MITRE ATT&CK; Splunk ESCU | Not started |  | ;ISE;BSE;
MR-05 | P2 Assess & Design | MR | Incident response plan (NIST SP 800-61r3 / CSF 2.0 profile) incl. on-chain | Severity matrix; roles; 24/7 escalation; on-chain incidents (pause/guardian, SEAL 911); notification matrix from D-01 (e.g. FTC Safeguards 30 days if applicable); DORA timelines as benchmark only (4h/24h, +72h, 1 month) | 6 | 3 | 8 | GC-01, PM-05 | 5 | OK | OK | 2026-11-30 | 2026-12-18 | ISE | BSE; GRC; PL | Incident management | Approved IR plan | NIST SP 800-61r3; SEAL Frameworks; Del. Reg. (EU) 2025/301 | Not started |  | ;BSE;GRC;PL;
MR-06 | P2 Assess & Design | MR | Backup and DR design | AWS Backup org policies; logically air-gapped vault (direct for supported types, copy otherwise); Aurora PITR (backtrack MySQL only); EKS backup approach (verify AWS Backup EKS support vs alternative); RTO/RPO from BIA | 6 | 2 | 7 | PM-06, GC-18 | 5 | OK | OK | 2026-11-30 | 2026-12-11 | CSE | ENG | AWS Backup, Aurora | Backup & DR design | SH Backup.1/RDS.11/RDS.14; CSF 2.0 RC | Not started |  | ;ENG;
BC-03 | P2 Assess & Design | BC | Retired-tool sweep: OpenZeppelin Defender (shut down 1 Jul 2026) | Find remaining Defender relayers/monitors/scripts; list on-chain roles still held by old relayer addresses; revoke via multisig | 2 | 1 | 2 |  |  | OK | OK | 2026-11-02 | 2026-11-06 | BSE |  | EVM ops tooling | Retired-tool list + revocation txs | OpenZeppelin Defender phase-out notice | Not started |  | ;;
BC-05 | P2 Assess & Design | BC | On-chain asset and privilege inventory; audit scope sizing | All contracts/programs, upgrade authorities, ProxyAdmin/Ownable owners, Safe versions/modules/guards, Squads config authority, spending limits, vault vs multisig authority, Anchor IDL authority; nSLOC per chain for auditor | 2 | 3 | 4 | BC-02 | 1 | OK | OK | 2026-11-02 | 2026-11-20 | BSE |  | Ethereum/Solana | Privileged-role register + audit scope | BSSC SCS & KMS; SEAL Multisig framework; Squads v4 | Not started |  | ;;
BC-04 | P2 Assess & Design | BC | Glamsterdam impact triage (Hoodi 26 Oct; mainnet TBD) | EF repricing checker; transfer/send, hardcoded gas, gasleft branching, presigned fixed-gas txs; Fusaka 2^24 tx gas cap; other Glamsterdam EIPs affecting monitoring/exit SLA (to verify against meta-EIP) | 3 | 3 | 5 |  |  | OK | OK | 2026-11-09 | 2026-11-27 | BSE | BSC | EVM gas semantics | Glamsterdam impact report | blog.ethereum.org Glamsterdam posts; EIP-7825 | Not started | Owner BSE - Fri 27 Nov 2026 | ;BSC;
BC-24 | P2 Assess & Design | BC | Interim on-chain monitoring (self-hosted OpenZeppelin Monitor) | Privileged-role changes, upgrades, Safe/Squads proposals, stake authority changes; route to pager; AGPL review | 3 | 3 | 5 | BC-03 | 2 | OK | OK | 2026-11-09 | 2026-11-27 | BSE | ISE | On-chain monitoring | Interim monitors live | OpenZeppelin Monitor repo | Not started |  | ;ISE;
BC-06 | P2 Assess & Design | BC | Custody vendor assessment (CCSS v9.0, BSSC KMS) | Policy engine (quorum, allowlists, velocity), hot-wallet caps, approver devices, key ceremony evidence, co-signer host, vendor SOC 2, PQ roadmap | 5 | 4 | 8 | BC-05, PM-03 | 4 | OK | OK | 2026-11-23 | 2026-12-18 | CSO | BSE; GRC | Custody assessment | Custody assessment report | CCSS v9.0; BSSC KMS | Not started |  | ;BSE;GRC;
BC-07 | P2 Assess & Design | BC | Staking provider due diligence | SOC report; BSSC NOS v2 attestation; EIP-3076 slashing-protection; client mix post-Alpenglow; Glamsterdam/ePBS readiness; SLA, insurance, exit procedure | 6 | 4 | 9 | BC-01, BC-02, PM-03 | 2 | OK | OK | 2026-11-30 | 2026-12-25 | BSE | CSO | Staking risk | Staking provider assessment | BSSC NOS v2; EIP-3076; Anza vote-account guide | Not started |  | ;CSO;
BC-08 | P2 Assess & Design | BC | Secure SDLC design for Solidity and Rust/Anchor | CI: Slither, Aderyn, Foundry fuzz/invariant, Echidna/Medusa, Halmos; storage layout + _disableInitializers checks; Rust: cargo-audit, clippy, Trident; Solana checks (owner/signer/discriminator, arbitrary CPI, PDA bumps, re-init, closed-account revival, Token-2022 extensions); solana-verify; deploy via multisig | 5 | 3 | 7 | BC-05 | 4 | OK | OK | 2026-11-23 | 2026-12-11 | BSC | BSE; ENG | Smart-contract security | SSDLC standard | OWASP SC Top 10 2026; BSSC SCS & TIS; NIST SSDF v1.1 | Not started |  | ;BSE;ENG;
BC-09 | P2 Assess & Design | BC | On-chain monitoring vendor selection (D-07) | Solana coverage confirmed in writing; Hypernative, Hexagate, OZ Monitor; routing to Splunk/SOAR | 5 | 2 | 6 | PM-03, BC-03 | 2 | OK | OK | 2026-11-23 | 2026-12-04 | BSE | DET | On-chain monitoring | D-07 decision | Vendor docs (claims confirmed in writing) | Not started |  | ;DET;
GC-25 | P2 Assess & Design | GC | Asset and data inventory with data classification | Systems, data stores, wallets, keys, vendors; classification scheme; owners | 4 | 4 | 7 | PM-02 | 1 | OK | OK | 2026-11-16 | 2026-12-11 | GRCC |  | Asset management | Asset & data register | CSF 2.0 ID.AM; ISO 27001 A.5.9/A.5.12; SOC 2 CC6.1 | Not started |  | ;;
GC-04 | P2 Assess & Design | GC | Policy framework (version-controlled) | Info-sec, access, change, crypto & key mgmt, SSDLC, IR, BC/DR, vendor, HR, acceptable use, data classification, logging; git-based | 5 | 4 | 8 | GC-01, GC-02 | 4 | OK | OK | 2026-11-23 | 2026-12-18 | GRCC | GRC | Policy authoring | Approved policy set v1.0 | ISO 27001:2022 5.2/A.5.1; SOC 2 CC1-CC5 | Not started |  | ;GRC;
GC-07 | P2 Assess & Design | GC | SOC 2 scope, system description and period plan (D-08, D-12) | TSC categories; carve-out vs inclusive for custody/staking providers; CPA consulted only (no design role); Type I as-of date and gap-free Type II start; which pre-period annual controls the CPA accepts | 5 | 3 | 7 | GC-01, PM-03 | 4 | OK | OK | 2026-11-23 | 2026-12-11 | GRC | GRCC; CPA | SOC 2 | Scope memo + draft system description | AICPA TSC 2017 (2022 PoF); DC 200 (2018, 2022 guidance) | Not started |  | ;GRCC;CPA;
GC-06 | P2 Assess & Design | GC | Third-party / ICT risk programme | Tiering; due diligence for custody, staking, RPC, Splunk, CrowdStrike, MDR, auditors; subservice orgs | 6 | 4 | 9 | GC-02 | 4 | OK | OK | 2026-11-30 | 2026-12-25 | GRC | CSO | TPRM | TPRM procedure + tier-1 assessments | CSF 2.0 GV.SC; ISO 27001 A.5.19-5.22 | Not started |  | ;CSO;
GC-12 | P2 Assess & Design | GC | Risk register and exception process (expiry-based) | Risk register (spreadsheet until GRC platform); exceptions max 90 days, one renewal; KRIs | 6 | 2 | 7 | PM-04, PM-07 | 3 | OK | OK | 2026-11-30 | 2026-12-11 | GRC | PL | Risk mgmt | Risk + exception registers | ISO 27001 6.1/8.2; CSF 2.0 GV.RM; SOC 2 CC3.1 | Not started |  | ;PL;
GC-09 | P2 Assess & Design | GC | GRC platform deployment and automated control tests | Integrate AWS, Entra, GitHub, HRIS; tests mapped after GC-05 | 6 | 4 | 9 | GC-03 | 4 | OK | OK | 2026-11-30 | 2026-12-25 | GRCC |  | GRC platform | Automated control monitoring live | AICPA TSC 2017 (2022 PoF) | Not started |  | ;;
PM-09A | P2 Assess & Design | PM | ARB #1: guardrail, image, identity, telemetry designs | Review HD-04, HD-05, ID-03, ID-04, MR-03; exceptions | 6 | 1 | 6 | HD-04, HD-05, ID-03, ID-04, MR-03 | 5 | OK | OK | 2026-11-30 | 2026-12-04 | PL | CSE; ISE | Architecture governance | ARB #1 approvals log | ISO 27001 A.8.27 | Not started |  | ;CSE;ISE;
GC-17 | P2 Assess & Design | GC | Security and fraud risk assessment | Annual risk assessment and fraud risk assessment (CC3.2/CC3.3); refreshed annually in BAU | 8 | 2 | 9 | GC-12, PM-05 | 7 | OK | OK | 2026-12-14 | 2026-12-25 | GRC | PL | Risk assessment | Risk assessment report | SOC 2 CC3.2/CC3.3; ISO 27001 8.2 | Not started |  | ;PL;
GC-05 | P2 Assess & Design | GC | Unified control matrix | SOC 2 TSC <-> CSF 2.0 <-> ISO 27001 Annex A (93) <-> CIS v8.1 <-> CIS benchmarks <-> BSSC/CCSS/SEAL; owners; tests; denominators for K17 | 8 | 4 | 11 | PM-06, GC-07, HD-09 | 7 | OK | OK | 2026-12-14 | 2027-01-08 | GRCC | GRC | Control frameworks | Unified control matrix | AICPA TSC 2017 (2022 PoF); CSF 2.0; ISO 27001:2022 | Not started |  | ;GRC;
GC-22 | P2 Assess & Design | GC | EU-marketing controls (condition of MiCA no-go) | No EU-targeted ads/influencers/EU-language sites/EU domains; geo-marketing review; evidence | 8 | 3 | 10 | GC-01 | 4 | OK | OK | 2026-12-14 | 2027-01-01 | GRC | LEG | Marketing compliance | EU marketing control evidence | MiCA Art 61; ESMA reverse-solicitation guidelines | Not started |  | ;LEG;
PM-09B | P2 Assess & Design | PM | ARB #2: network, Kubernetes, workload identity, CIAM, DR, SSDLC designs | Review HD-07, HD-08, ID-05, ID-06, MR-06, BC-08; exceptions | 8 | 1 | 8 | HD-07, HD-08, ID-05, ID-06, MR-06, BC-08 | 7 | OK | OK | 2026-12-14 | 2026-12-18 | PL | CSE; ISE | Architecture governance | ARB #2 approvals log | ISO 27001 A.8.27 | Not started |  | ;CSE;ISE;
MR-01B | P3 Build & Harden | MR | GuardDuty Runtime Monitoring agents (after SSM) | Automated agent via SSM on EC2; EKS add-on on EC2 nodes; ECS on EC2 (agent >=1.77.0 / AMI >=2023-09-29); EKS on Fargate unsupported -> HD-25 | 7 | 2 | 8 | HD-06, GC-08, MR-01 | 6 | OK | OK | 2026-12-07 | 2026-12-18 | CPE | CSE | GuardDuty | Runtime Monitoring coverage report | GuardDuty Runtime Monitoring docs; SH GuardDuty.7/.11/.13 | Not started |  | ;CSE;
HD-10 | P3 Build & Harden | HD | Deploy org guardrails (sandbox/non-prod W7-W8; prod from W11) | SCP/RCP/declarative staged with CAB; EBS default encryption all Regions; S3 account BPA; Control Tower controls | 7 | 6 | 12 | PM-09A, GC-08 | 6 | OK | OK | 2026-12-07 | 2027-01-15 | CSE | KHE | AWS Organizations | Guardrails live in all OUs | SH EC2.7/EC2.8/S3.1/IAM.4 | Not started |  | ;KHE;
HD-16A | P3 Build & Harden | HD | EKS node groups AL2 -> AL2023/Bottlerocket at 1.32 (non-prod W6-7, prod W8) | Per D-05; drain/replace node groups; validate workloads; before freeze | 6 | 3 | 8 | HD-02, HD-05, HD-24 | 5 | OK | OK | 2026-11-30 | 2026-12-18 | CPE | CSE; ENG | EKS node groups | No AL2 EKS nodes | EKS AL2 AMI deprecation FAQ; AL2 FAQ | Not started |  | ;CSE;ENG;
HD-23 | P3 Build & Harden | HD | Container hosts on EC2 (ECS/Docker) to AL2023 (non-prod W7-8, prod W11-14) | ECS-optimized AL2023 AMI; cgroup v2 memory checks (JVM); agent versions | 7 | 8 | 14 | HD-03, HD-05 | 4 | OK | OK | 2026-12-07 | 2027-01-29 | KHE | ENG | ECS, Linux | No AL2 container hosts | ECS AMI docs; AL2 FAQ | Not started |  | ;ENG;
HD-11 | P3 Build & Harden | HD | Patch Manager baselines and patch SLA | Baselines per OS; maintenance windows; SLA crit 7d/high 14d | 8 | 3 | 10 | HD-06, PM-04 | 6 | OK | OK | 2026-12-14 | 2027-01-01 | KHE | ENG | SSM Patch Manager | Patch SLA live | SH SSM.2/SSM.3; CIS Controls 7 | Not started |  | ;ENG;
HD-12 | P3 Build & Harden | HD | Inspector CIS scans (AL2023 L1) scheduled | Scheduled scans; baseline score; Graviton/Bottlerocket evidence via HD-26 | 8 | 1 | 8 | HD-06, HD-05 | 6 | OK | OK | 2026-12-14 | 2026-12-18 | KHE |  | Amazon Inspector | CIS scan baseline | Inspector CIS scans docs; CIS AL2023 v1.0.0 | Not started |  | ;;
HD-13 | P3 Build & Harden | HD | Golden AMI pipeline (EC2 Image Builder) | CIS AL2023 L1 + CrowdStrike sensor + SSM agent; allowed-images policy | 9 | 3 | 11 | HD-05, PM-09A | 6 | OK | OK | 2026-12-21 | 2027-01-08 | KHE | CSE | Image Builder | Golden AMI v1 | CIS AL2023 v1.0.0; EC2 declarative policies | Not started |  | ;CSE;
HD-19 | P3 Build & Harden | HD | Network baseline implementation (prod after freeze) | Network Firewall egress; WAF managed rules + logging; SG cleanup; VPC endpoints; flow logs; DNS Firewall | 9 | 5 | 13 | HD-07, PM-09B, GC-08 | 8 | OK | OK | 2026-12-21 | 2027-01-22 | CSE | KHE; ENG | AWS networking | Network baseline live | SH EC2.2/EC2.6/ELB.16/WAF.10/WAF.11/NetworkFirewall.2/.4/.5 | Not started |  | ;KHE;ENG;
HD-16B | P3 Build & Harden | HD | EKS version hops 1.32 -> 1.36 (before 1.32 extended EOS 23 Mar 2027) | One hop at a time per HD-24 matrix; add-ons; nodes; no reliance on forced auto-upgrade (no notice, no rollback) | 11 | 8 | 18 | HD-16A, HD-24, PM-09B | 8 | OK | OK | 2027-01-04 | 2027-02-26 | CSE | KHE; ENG | EKS | All clusters on 1.36 | EKS kubernetes-versions page; SH EKS.2/EKS.9 | Not started | Owner CSE - complete by Fri 26 Feb 2027 (hard stop 23 Mar 2027) | ;KHE;ENG;
HD-17 | P3 Build & Harden | HD | Kubernetes hardening rollout | PSA restricted; admission policies; NetworkPolicies; private endpoints; audit logs; access entries; Pod Identity | 11 | 5 | 15 | HD-08, PM-09B, ID-05 | 8 | OK | OK | 2027-01-04 | 2027-02-05 | KHE | CSE; ENG | Kubernetes security | K8s baseline enforced | CIS EKS v2.0.0; SH EKS.1/EKS.8 | Not started |  | ;CSE;ENG;
HD-14 | P3 Build & Harden | HD | AL2 -> AL2023 migration wave 1 (internet-facing, crypto-adjacent) | Migrate priority workloads using golden AMI; decommission AL2 | 13 | 4 | 16 | HD-03, HD-13 | 11 | OK | OK | 2027-01-18 | 2027-02-12 | CSE | ENG; KHE | Linux migration | Wave-1 AL2 retired | AL2 FAQ | Not started |  | ;ENG;KHE;
HD-21 | P3 Build & Harden | HD | Security Hub CSPM remediation sprints | Burn down FSBP/CIS v5.0.0 failures by severity; suppressions only via exception register | 14 | 6 | 19 | HD-10, MR-23 | 12 | OK | OK | 2027-01-25 | 2027-03-05 | CSE | KHE; ENG | AWS remediation | Security Hub score >= target | Security Hub CSPM FSBP; CIS AWS v5.0.0 | Not started |  | ;KHE;ENG;
HD-15 | P3 Build & Harden | HD | AL2 migration wave 2 (to zero AL2) | Remaining workloads; residual exceptions approved with expiry | 17 | 4 | 20 | HD-14 | 16 | OK | OK | 2027-02-15 | 2027-03-12 | CSE | ENG | Linux migration | AL2 count = 0 or approved exceptions | AL2 FAQ | Not started |  | ;ENG;
HD-25 | P3 Build & Harden | HD | EKS on Fargate runtime-monitoring gap | If Fargate in use: Falcon container sidecar or move workloads to EC2 nodes; IRSA (Pod Identity unsupported) | 15 | 3 | 17 | MR-01B, HD-05 | 8 | OK | OK | 2027-02-01 | 2027-02-19 | KHE | CSE | EKS Fargate | Fargate coverage decision + implementation | GuardDuty Runtime Monitoring docs; EKS Pod Identity docs | Not started |  | ;CSE;
HD-18 | P3 Build & Harden | HD | Container supply chain: signing and verification | ECR managed signing (AWS Signer); tag immutability with exclusions; Inspector ECR; EKS admission verification; ECS: CI/CD signature gate; SBOM | 16 | 4 | 19 | HD-17 | 15 | OK | OK | 2027-02-08 | 2027-03-05 | KHE | ENG | Supply chain security | Signed-image enforcement | ECR managed signing; SH ECR.1/.2/.3, Inspector.2 | Not started |  | ;ENG;
HD-26 | P3 Build & Harden | HD | Bottlerocket CIS evidence (if D-05 selects Bottlerocket) | CIS Bottlerocket v1.0.0 report via Bottlerocket tooling (verify method); evidence to GRC platform | 16 | 3 | 18 | HD-05, HD-16A | 8 | OK | OK | 2027-02-08 | 2027-02-26 | KHE | GRCC | Bottlerocket | Bottlerocket CIS evidence | CIS Bottlerocket v1.0.0 | Not started |  | ;GRCC;
HD-20 | P3 Build & Harden | HD | Data-protection configuration | KMS rotation; Secrets Manager rotation; Aurora encryption/deletion protection; OpenSearch FGAC/audit; SQS/SNS/Kinesis/EFS encryption; ACM | 12 | 4 | 15 | PM-09B, ID-05 | 8 | OK | OK | 2027-01-11 | 2027-02-05 | CPE | ENG | AWS data services | Data-protection controls passing | SH KMS.4, SecretsManager.1, RDS.2/.3/.7/.8/.27, Opensearch.1/.3/.5/.7, SQS.1, SNS.1, Kinesis.1, EFS.8, ACM.1 | Not started |  | ;ENG;
HD-30 | P3 Build & Harden | HD | Macie sensitive-data discovery and data-perimeter validation | Automated discovery on S3; validate RCP data perimeter | 13 | 4 | 16 | HD-22, HD-10 | 12 | OK | OK | 2027-01-18 | 2027-02-12 | CPE | GRCC | Data security | Sensitive-data findings triaged | Amazon Macie docs; CSF 2.0 ID.AM-07 | Not started |  | ;GRCC;
ID-10 | P3 Build & Harden | ID | Enrol device-bound FIDO2 keys for admins | Enrol, attestation enforced, spares, loss procedure (signers use hardware wallets - BC-11) | 9 | 2 | 10 | ID-00, ID-03 | 5 | OK | OK | 2026-12-21 | 2027-01-01 | ISE |  | FIDO2 | 100% admins enrolled | Entra passkeys (FIDO2) docs | Not started |  | ;;
ID-08 | P3 Build & Harden | ID | Entra Conditional Access baseline in report-only | Block legacy auth; MFA all; phishing-resistant strength for admins; compliant device for admins; break-glass excluded | 7 | 4 | 10 | ID-01, ID-03, PM-09A | 6 | OK | OK | 2026-12-07 | 2027-01-01 | IDC |  | Entra CA | Report-only impact analysis | Entra CA docs; CIS Controls 6.3-6.5 | Not started |  | ;;
ID-08B | P3 Build & Harden | ID | Enforce Conditional Access baseline (after freeze) | Switch to On in waves; monitor sign-in failures; rollback criteria | 11 | 2 | 12 | ID-08, ID-10 | 10 | OK | OK | 2027-01-04 | 2027-01-15 | IDC | ISE | Entra CA | CA baseline enforced | Entra CA docs | Not started |  | ;ISE;
ID-11 | P3 Build & Harden | ID | AWS IAM Identity Center build-out | SCIM; permission sets; JIT per D-16; remove IAM users/keys; centralized root access (member accounts) | 9 | 4 | 12 | ID-04, PM-09A | 6 | OK | OK | 2026-12-21 | 2027-01-15 | ISE | CSE | IAM Identity Center | No long-lived human IAM keys | SH IAM.1/.2/.4/.6/.8/.22 | Not started |  | ;CSE;
ID-13 | P3 Build & Harden | ID | B2C hardening and step-up MFA on withdrawals | MFA enforcement; step-up on withdrawals and payout-address change with API-side fresh auth_time check; out-of-band confirmation + cool-down; fraud/bot vendor (D-13) | 9 | 5 | 13 | ID-06, PM-09B | 8 | OK | OK | 2026-12-21 | 2027-01-22 | IDC | ISE; ENG | B2C custom policies | Step-up live; B2C logs in Splunk | B2C claim resolvers; B2C Azure Monitor docs | Not started |  | ;ISE;ENG;
ID-12 | P3 Build & Harden | ID | Workload identity rollout | Pod Identity/IRSA; CI/CD OIDC; secret rotation | 12 | 4 | 15 | ID-05, PM-09B | 8 | OK | OK | 2027-01-11 | 2027-02-05 | CPE | ENG | AWS IAM | No static cloud keys in CI/CD | EKS Pod Identity; SH SecretsManager.1 | Not started |  | ;ENG;
ID-09 | P3 Build & Harden | ID | PIM: zero standing privileged access (Entra, Azure, PIM for Groups -> AWS) | Approval + MFA on activation; only break-glass permanent | 13 | 3 | 15 | ID-08B, ID-11 | 12 | OK | OK | 2027-01-18 | 2027-02-05 | ISE |  | Entra PIM | Standing admins = break-glass only | Entra PIM; CIS Controls 5.4/6.8 | Not started |  | ;;
ID-16 | P3 Build & Harden | ID | Workforce ID Protection: risk-based CA, risky service principals | Per D-02 licensing; user/sign-in risk policies; risky SP review | 13 | 3 | 15 | ID-08B | 12 | OK | OK | 2027-01-18 | 2027-02-05 | IDC | ISE | Entra ID Protection | Risk-based CA live | Entra ID Protection docs | Not started |  | ;ISE;
ID-14 | P3 Build & Harden | ID | Customer identity roadmap: B2C to External ID (D-06) | Gaps (no IEF; no ID Protection in external tenants; passkeys not enforceable by CA); JIT password migration; timeline before May 2030 | 14 | 2 | 15 | ID-06 | 7 | OK | OK | 2027-01-25 | 2027-02-05 | IDC | ISE | CIAM strategy | D-06 roadmap | External ID migration docs | Not started |  | ;ISE;
ID-15 | P3 Build & Harden | ID | Wallet sign-in hardening implementation | Implement verifier, nonce store, EIP-1271; tests; monitoring | 15 | 3 | 17 | ID-07 | 9 | OK | OK | 2027-02-01 | 2027-02-19 | BSC | ENG | Web3 auth | Hardened wallet sign-in | EIP-4361; EIP-1271 | Not started |  | ;ENG;
ID-17 | P3 Build & Harden | ID | Token-theft protections | Continuous Access Evaluation; token protection; admin sign-in frequency; privileged access workstation decision | 16 | 3 | 18 | ID-08B | 12 | OK | OK | 2027-02-08 | 2027-02-26 | IDC | ISE | Entra session security | Token protections live | Entra CAE/token protection docs | Not started |  | ;ISE;
ID-19 | P3 Build & Harden | ID | Helpdesk and account-recovery fraud controls | Workforce and B2C support: identity verification, recovery cool-downs, alerts | 16 | 3 | 18 | PM-05, ID-13 | 13 | OK | OK | 2027-02-08 | 2027-02-26 | IDC | ISE; HRB | Identity proofing | Recovery procedures | CIS Controls 5/6; OWASP ASVS | Not started |  | ;ISE;HRB;
MR-07 | P3 Build & Harden | MR | Onboard telemetry to Splunk | AWS, Security Hub OCSF, GuardDuty, VPC/WAF/NFW, EKS audit, Entra, B2C, CrowdStrike; data-quality checks | 7 | 4 | 10 | MR-03, PM-09A, MR-23 | 6 | OK | OK | 2026-12-07 | 2027-01-01 | DET | ISE | Splunk onboarding | Log source register 100% green | Splunkbase 1876/8642/3110/5082 | Not started |  | ;ISE;
MR-24 | P3 Build & Harden | MR | Detection-as-code CI pipeline | contentctl build/test, peer review, version control, deployment | 8 | 3 | 10 | MR-04 | 7 | OK | OK | 2026-12-14 | 2027-01-01 | DET | ISE | Detection engineering | Detection CI live | Splunk contentctl | Not started |  | ;ISE;
MR-11 | P3 Build & Harden | MR | MDR onboarding in phases (EDR/GuardDuty/Entra first, Splunk notables after MR-07) | Log access; runbooks; escalation matrix incl. on-chain; hand-off tests; holiday cover | 5 | 9 | 13 | MR-02, MR-00 | 4 | OK | OK | 2026-11-23 | 2027-01-22 | MDR | ISE | SOC operations | 24/7 MDR live | CSF 2.0 DE.CM/RS.MA | Not started |  | ;ISE;
MR-12 | P3 Build & Harden | MR | Backup and DR implementation | Org backup policies; LAG vault; Aurora configuration; vault lock | 9 | 4 | 12 | MR-06, PM-09B | 8 | OK | OK | 2026-12-21 | 2027-01-15 | CPE | ENG | AWS Backup | Backups compliant | SH Backup.1/RDS.11; AWS Backup LAG vault | Not started |  | ;ENG;
MR-13 | P3 Build & Harden | MR | On-chain monitoring deployment (production) | Privileged-role/upgrade events, Safe/Squads proposals and config-authority changes, spending-limit use, large transfers, stake authority/commission/lockup changes, EIP-7002 requests, oracle deviation; to Splunk/SOAR/pager | 7 | 3 | 9 | BC-09, BC-05, MR-03 | 6 | OK | OK | 2026-12-07 | 2026-12-25 | BSE | DET | On-chain monitoring | On-chain monitors live | SEAL Monitoring framework | Not started |  | ;DET;
MR-14 | P3 Build & Harden | MR | Staking monitoring per chain | ETH: effectiveness, missed attestations, slashing, credential/7002 events; SOL: post-Alpenglow participation metrics (definitions to verify with Anza), delinquency, reward deltas, authority/commission changes | 10 | 2 | 11 | BC-07, MR-13 | 9 | OK | OK | 2026-12-28 | 2027-01-08 | DET | BSE; CSO | Staking ops | Staking dashboards + alerts | BSSC NOS v2; solana.com/upgrades/alpenglow | Not started |  | ;BSE;CSO;
MR-08 | P3 Build & Harden | MR | Detection wave 1: identity and control plane | Break-glass sign-in; CA/PIM changes; app consent; root use; SCP/CloudTrail tamper; IAM key creation; GuardDuty high/critical | 11 | 3 | 13 | MR-07, MR-24, MR-04 | 10 | OK | OK | 2027-01-04 | 2027-01-22 | DET | ISE | Detection engineering | Wave-1 detections in prod | MITRE ATT&CK; ESCU | Not started |  | ;ISE;
MR-20 | P3 Build & Harden | MR | Splunk RBAC, log integrity and silent-source alerts | Role-based access; index integrity; alerts when a source stops sending | 11 | 3 | 13 | MR-07 | 10 | OK | OK | 2027-01-04 | 2027-01-22 | DET | ISE | Splunk administration | Integrity + silent-source alerts | SOC 2 CC7.2; CIS Controls 8 | Not started |  | ;ISE;
MR-09 | P3 Build & Harden | MR | Detection wave 2: workload, Kubernetes, EDR, exfiltration | EKS audit anomalies; runtime; CrowdStrike correlations; S3/RDS exfil; WAF | 14 | 3 | 16 | MR-08 | 13 | OK | OK | 2027-01-25 | 2027-02-12 | DET | ISE; CSE | Detection engineering | Wave-2 detections in prod | MITRE ATT&CK Containers/Cloud | Not started |  | ;ISE;CSE;
MR-10 | P3 Build & Harden | MR | SOAR playbooks (Splunk SOAR) and automation identity lockdown | Enrichment; account disable; instance isolation; on-chain alert triage; Python 3.13; least-privilege SOAR/MDR identities | 14 | 3 | 16 | MR-08 | 13 | OK | OK | 2027-01-25 | 2027-02-12 | DET | ISE | Splunk SOAR | Playbooks in prod | Splunk SOAR release notes; NIST SP 800-61r3 | Not started |  | ;ISE;
GC-19 | P3 Build & Harden | GC | Business continuity and crisis communications plan | From BIA; crisis comms (customers, partners, regulators if any); vendor-failure scenarios (custody, staking, RPC) | 11 | 4 | 14 | GC-18, MR-05 | 8 | OK | OK | 2027-01-04 | 2027-01-29 | ISE | PL; GRC | BC planning | Approved BCP + crisis comms | NIST CSF 2.0 RC.CO; ISO 27001 A.5.29-5.30 | Not started |  | ;PL;GRC;
BC-14 | P3 Build & Harden | BC | Glamsterdam remediation and hard-fork readiness runbook | Fix gas-dependent code; Hoodi regression; fork runbook (monitoring, pause criteria, provider readiness) | 6 | 4 | 9 | BC-04 | 5 | OK | OK | 2026-11-30 | 2026-12-25 | BSC | BSE; ENG | EVM | Fork runbook + regression results | Glamsterdam testnet & repricing posts | Not started |  | ;BSE;ENG;
BC-30 | P3 Build & Harden | BC | Oracle risk review | Price-feed sources, staleness/deviation checks, manipulation resistance | 10 | 2 | 11 | BC-05 | 4 | OK | OK | 2026-12-28 | 2027-01-08 | BSE |  | DeFi security | Oracle risk review | OWASP SC Top 10 2026 | Not started |  | ;;
BC-12 | P3 Build & Harden | BC | Custody policy-engine configuration and co-signer hardening | Allowlists; velocity limits; hot-wallet caps (D-14); approver separation; co-signer host hardening; reject EIP-7702 (type-4) txs | 11 | 3 | 13 | BC-06, PM-04 | 8 | OK | OK | 2027-01-04 | 2027-01-22 | CSO | BSE | MPC custody | Policy-engine config evidence | CCSS v9.0; BSSC KMS; EIP-7702 | Not started |  | ;BSE;
BC-13 | P3 Build & Harden | BC | Secure SDLC implementation incl. verified builds | CI gates per BC-08; solana-verify verified builds; IDL authority to Vault; contract source verification; code owners | 10 | 4 | 13 | BC-08 | 7 | OK | OK | 2026-12-28 | 2027-01-22 | BSC | ENG | CI/CD, smart contracts | SSDLC gates enforced | NIST SSDF v1.1; OWASP SC Top 10 2026 | Not started |  | ;ENG;
BC-23 | P3 Build & Harden | BC | Anchor 1.x migration (or documented decision to stay) | Assess breaking changes; migrate before code freeze; tests | 10 | 5 | 14 | BC-08 | 7 | OK | OK | 2026-12-28 | 2027-01-29 | BSC | ENG | Anchor | Migrated programs or decision record | Anchor releases (v1.2.1) | Not started |  | ;ENG;
BC-26 | P3 Build & Harden | BC | Deployer key and upgrade-path hygiene | Deployer EOAs retired; Solana buffer accounts closed; ProxyAdmin/Ownable owners -> multisig; deploy+initialise atomically | 11 | 3 | 13 | BC-05 | 4 | OK | OK | 2027-01-04 | 2027-01-22 | BSE | ENG | Smart-contract ops | Deployer hygiene record | SEAL Multisig framework; BSSC SCS | Not started |  | ;ENG;
BC-10 | P3 Build & Harden | BC | Privileged on-chain roles under multisig and timelock (role matrix) | Role matrix: upgrades/admin timelocked; pause guardian lower threshold without timelock; canceller role; per-contract immutable-vs-timelocked decision; Safe upgrade to 1.5.0 before delegatecall guard (fork-tested, removable); Squads config authority to Vault; CUKC approval | 11 | 4 | 14 | BC-05, PM-09B, MR-13, GC-02 | 9 | OK | OK | 2027-01-04 | 2027-01-29 | BSE | CSO | Safe/Squads | 100% upgrade/admin roles under multisig+timelock | SEAL Multisig framework; BSSC KMS; Safe 1.5.0 | Not started |  | ;CSO;
BC-19 | P3 Build & Harden | BC | Staking oversight changes (only after monitoring live) | Contract amendments: withdrawal-address ownership, exit SLA, reporting; 0x00/provider-owned 0x01 remediation; consolidations via CUKC | 12 | 3 | 14 | MR-14, BC-07 | 11 | OK | OK | 2027-01-11 | 2027-01-29 | CSO | BSE; GRC | Staking contracts | Amended provider agreement | EIP-7251; BSSC NOS v2 | Not started |  | ;BSE;GRC;
BC-11 | P3 Build & Harden | BC | Signer operations hardening | Dedicated signing devices; clear signing on hardware wallets; independent tx-hash verification; EIP-7702 delegation ban; signer drills | 13 | 3 | 15 | BC-06, ID-00 | 8 | OK | OK | 2027-01-18 | 2027-02-05 | BSE | ISE | Signer ops | Signer SOP + drill record | SEAL Wallet Security; Bybit post-mortem lessons | Not started |  | ;ISE;
BC-15 | P3 Build & Harden | BC | Code freeze for audit scope | Freeze commit hashes incl. timelock/guard configuration; scope doc to auditor | 15 | 1 | 15 | BC-13, BC-14, BC-23, BC-10, PM-03 | 14 | OK | OK | 2027-02-01 | 2027-02-05 | BSE | ENG | Release mgmt | Frozen audit scope | BSSC SCS | Not started |  | ;ENG;
BC-21 | P3 Build & Harden | BC | On-chain IR playbooks and war-room | Pause/guardian; key or signer compromise; front-end/domain hijack; SEAL 911 contact verified via official channel; comms | 15 | 2 | 16 | MR-05, BC-10 | 14 | OK | OK | 2027-02-01 | 2027-02-12 | BSE | ISE | On-chain IR | On-chain playbooks | SEAL Incident Mgmt; NIST SP 800-61r3 | Not started |  | ;ISE;
BC-25 | P3 Build & Harden | BC | dApp front-end and domain integrity | Registrar lock, DNSSEC, CAA; FIDO2 on registrar/CDN/DNS accounts; CloudFront/Shield; CSP + SRI; pinned npm deps; script-change monitoring; security.txt + vulnerability disclosure policy | 4 | 6 | 9 |  |  | OK | OK | 2026-11-16 | 2026-12-25 | CPE | ENG | Web/DNS security | Front-end integrity controls | SEAL Frameworks; OWASP ASVS; RFC 9116 | Not started |  | ;ENG;
GC-23 | P3 Build & Harden | GC | OFAC wallet screening and geo-blocking | Screen counterparties/wallets (vendor with Solana + Ethereum coverage confirmed); geo-block sanctioned jurisdictions on front-ends | 6 | 6 | 11 | GC-01 | 4 | OK | OK | 2026-11-30 | 2027-01-08 | CSO | ENG | Sanctions compliance | Screening + geo-blocking live | OFAC VC guidance (Oct 2021) | Not started |  | ;ENG;
GC-10 | P3 Build & Harden | GC | Security awareness and role-based training | All-staff; phishing simulation; signer training; secure coding (Solidity/Rust); IR roles | 11 | 6 | 16 | GC-04 | 8 | OK | OK | 2027-01-04 | 2027-02-12 | GRC | BSE; ISE | Training | Training completion >=95% | SOC 2 CC2.2; ISO 27001 A.6.3 | Not started |  | ;BSE;ISE;
GC-11 | P3 Build & Harden | GC | HR security controls | Background checks; JML SLAs with Entra lifecycle; DPRK IT-worker screening; contractor access; code of conduct | 11 | 3 | 13 | GC-04 | 8 | OK | OK | 2027-01-04 | 2027-01-22 | HRB | GRC; ISE | HR security | HR control evidence | SOC 2 CC1.4; SEAL DPRK IT Workers; ISO 27001 A.6 | Not started |  | ;GRC;ISE;
GC-26 | P3 Build & Harden | GC | Records retention and legal hold | Retention schedule (logs, tickets, evidence, comms); legal-hold procedure | 10 | 4 | 13 | GC-04 | 8 | OK | OK | 2026-12-28 | 2027-01-22 | GRC | LEG | Records management | Retention schedule + legal hold | ISO 27001 A.5.33; SOC 2 C1.2 | Not started |  | ;LEG;
GC-27 | P3 Build & Harden | GC | Cyber insurance review | Coverage incl. crypto-asset exclusions, incident response panel, vendor requirements | 7 | 4 | 10 | GC-18 | 5 | OK | OK | 2026-12-07 | 2027-01-01 | PL |  | Insurance | Insurance gap memo | NIST CSF 2.0 GV.RM-04 | Not started |  | ;;
GC-28 | P3 Build & Harden | GC | Vendor exit plans (custody, staking, RPC, MDR, Splunk) | Exit/transition plans; MPC key-recovery drill; data return | 12 | 4 | 15 | GC-06, BC-06 | 9 | OK | OK | 2027-01-11 | 2027-02-05 | CSO | GRC; BSE | TPRM | Exit plans + recovery drill record | ISO 27001 A.5.19-5.23; DORA Art 28 (benchmark) | Not started |  | ;GRC;BSE;
PM-13 | P3 Build & Harden | PM | Evergreen operating model live before SOC 2 period | Operating calendar; audit evidence calendar; trigger procedures; control-health dashboard; exception expiry; contractor-dependency KRI | 14 | 3 | 16 | GC-09, GC-12 | 9 | OK | OK | 2027-01-25 | 2027-02-12 | GRC | PL; PMC | GRC operations | Evergreen calendar + dashboards | ISO 27001 9-10; CSF 2.0 GV.OV | Not started |  | ;PL;PMC;
PM-10 | P4 Monitor & Validate | PM | Gate 2 - Design complete / critical exposures closed (W15) | Criteria in Overview | 15 | 1 | 15 | PM-09A, PM-09B, HD-10, ID-08B, MR-07, MR-13, BC-12, HD-12, HD-16A, GC-04, GC-05, GC-06, GC-12, MR-11 | 13 | OK | OK | 2027-02-01 | 2027-02-05 | PL | PMC | Governance | Signed Gate 2 minute | Program governance | Not started |  | ;PMC;
BC-16 | P4 Monitor & Validate | BC | Smart-contract audit (Ethereum + Solana, parallel teams) | External audit of frozen scope incl. timelock/guard config; daily triage | 16 | 4 | 19 | BC-15 | 15 | OK | OK | 2027-02-08 | 2027-03-05 | SCA | BSE | Smart-contract audit | Audit report (preliminary) | OWASP SC Top 10 2026; BSSC SCS | Not started |  | ;BSE;
BC-31 | P4 Monitor & Validate | BC | RPC provider security and redundancy | At least two RPC providers; auth keys in Secrets Manager; response-integrity checks for monitoring | 16 | 2 | 17 | BC-05 | 4 | OK | OK | 2027-02-08 | 2027-02-19 | ISE | BSE | Infrastructure | RPC redundancy live | BSSC NOS v2 | Not started |  | ;BSE;
BC-20 | P4 Monitor & Validate | BC | Crypto-agility and post-quantum roadmap | Crypto inventory (secp256k1, Ed25519, TLS, KMS); vendor PQ roadmaps; NIST IR 8547 (draft) timeline | 16 | 2 | 17 | BC-06, BC-07 | 9 | OK | OK | 2027-02-08 | 2027-02-19 | BSE | CSE | Cryptography | Crypto-agility roadmap | FIPS 203/204/205; NIST IR 8547 ipd | Not started |  | ;CSE;
BC-29 | P4 Monitor & Validate | BC | Treasury segregation, approvals hygiene, address-poisoning controls | Segregate treasury/hot/ops wallets; revoke stale token approvals/Permit2; address allowlists | 16 | 4 | 19 | BC-12 | 13 | OK | OK | 2027-02-08 | 2027-03-05 | CSO | BSE | Treasury ops | Treasury hygiene record | CCSS v9.0; SEAL Treasury Ops | Not started |  | ;BSE;
MR-19 | P4 Monitor & Validate | MR | DR restore test | Restore Aurora, EKS workloads, S3 from LAG vault; measure RTO/RPO vs BIA | 16 | 2 | 17 | MR-12 | 12 | OK | OK | 2027-02-08 | 2027-02-19 | CPE | ENG | DR | Restore test evidence | CSF 2.0 RC.RP; SOC 2 A1.3 | Not started |  | ;ENG;
GC-21 | P4 Monitor & Validate | GC | Corrective-action log and management review | Management review of ISMS-lite; corrective actions tracked to closure | 16 | 2 | 17 | GC-12, PM-06 | 7 | OK | OK | 2027-02-08 | 2027-02-19 | GRC | PL | Management system | Management review minutes + CAPA log | ISO 27001 9.3/10.2 | Not started |  | ;PL;
BC-28 | P4 Monitor & Validate | BC | Mainnet-fork pause/guardian drill | Timed drill of pause paths on a mainnet fork (EVM) and devnet/local validator (Solana) | 17 | 2 | 18 | BC-10, BC-21 | 16 | OK | OK | 2027-02-15 | 2027-02-26 | BSC | BSE | On-chain IR | Drill record vs time-to-pause target | SEAL Incident Mgmt | Not started |  | ;BSE;
MR-15 | P4 Monitor & Validate | MR | Detection validation / purple team | Atomic tests; ATT&CK coverage; tuning; MTTD/MTTA measurement | 17 | 2 | 18 | MR-09, MR-10 | 16 | OK | OK | 2027-02-15 | 2027-02-26 | DET | ISE; MDR | Purple teaming | Validation report | MITRE ATT&CK | Not started |  | ;ISE;MDR;
GC-13 | P4 Monitor & Validate | GC | SOC 2 readiness assessment (independent firm) | Walkthroughs; design and evidence gaps | 17 | 2 | 18 | GC-05, GC-07, GC-09, GC-12, PM-13 | 16 | OK | OK | 2027-02-15 | 2027-02-26 | RDA | GRC | SOC 2 readiness | Readiness report | AICPA TSC 2017 (2022 PoF) | Not started |  | ;GRC;
MR-16 | P4 Monitor & Validate | MR | Penetration test (cloud, EKS, dApp front-end, wallet sign-in, B2C step-up) | Rules of engagement; daily findings | 18 | 2 | 19 | HD-17, HD-19, ID-13, ID-15, PM-03 | 17 | OK | OK | 2027-02-22 | 2027-03-05 | PEN | CSE; ISE | Pentest | Pentest report | OWASP WSTG; CIS Controls 18 | Not started |  | ;CSE;ISE;
GC-14 | P4 Monitor & Validate | GC | SOC 2 readiness remediation | Close gaps; finalise system description | 19 | 3 | 21 | GC-13 | 18 | OK | OK | 2027-03-01 | 2027-03-19 | GRC | GRCC; CSE; ISE; BSE | SOC 2 | Gaps closed | AICPA TSC 2017 (2022 PoF) | Not started |  | ;GRCC;CSE;ISE;BSE;
MR-18 | P4 Monitor & Validate | MR | Tabletop exercises | Cloud ransomware; identity compromise; Drift-style multisig attack; exec participation | 19 | 2 | 20 | MR-05, BC-21, MR-11 | 16 | OK | OK | 2027-03-01 | 2027-03-12 | ISE | BSE; PL; MDR | Exercise design | After-action reports | NIST SP 800-61r3; SEAL | Not started |  | ;BSE;PL;MDR;
PM-11 | P4 Monitor & Validate | PM | Gate 3 - Build complete (W20) | Criteria in Overview | 20 | 1 | 20 | BC-10, MR-09, MR-11, MR-16, BC-16, HD-17, MR-19, PM-10, GC-13, HD-16B | 19 | OK | OK | 2027-03-08 | 2027-03-12 | PL | PMC | Governance | Signed Gate 3 minute | Program governance | Not started |  | ;PMC;
MR-17 | P4 Monitor & Validate | MR | Pentest remediation and retest | Fix criticals/highs; retest | 20 | 3 | 22 | MR-16 | 19 | OK | OK | 2027-03-08 | 2027-03-26 | CSE | PEN; ENG | Remediation | Retest letter | CIS Controls 18 | Not started |  | ;PEN;ENG;
BC-17 | P4 Monitor & Validate | BC | Audit remediation and fix review | Fix findings; auditor fix review; redeploy via multisig/timelock with verified builds | 20 | 3 | 22 | BC-16 | 19 | OK | OK | 2027-03-08 | 2027-03-26 | BSE | SCA; BSC; ENG | Smart contracts | Final audit report + fix review | BSSC SCS | Not started |  | ;SCA;BSC;ENG;
PM-12 | P5 Operationalize & Handover | PM | Runbooks and BAU handover per workstream | Runbooks; owner acceptance; contractor knowledge transfer; contractor access revoked | 21 | 4 | 24 | PM-11 | 20 | OK | OK | 2027-03-15 | 2027-04-09 | PL | CSE; ISE; BSE; GRC; PMC | Transition management | Signed handover acceptance | ISO 27001 A.5.37 | Not started |  | ;CSE;ISE;BSE;GRC;PMC;
PM-14 | P5 Operationalize & Handover | PM | KPI baseline vs target and dashboard | Populate KPI tab; automated feeds from Security Hub, Splunk, GRC platform, on-chain monitor | 21 | 2 | 22 | MR-15, PM-11 | 20 | OK | OK | 2027-03-15 | 2027-03-26 | PMC | DET; GRC | Metrics | KPI dashboard | CSF 2.0 GV.OV/ID.IM | Not started |  | ;DET;GRC;
GC-15 | P5 Operationalize & Handover | GC | SOC 2 Type I (as-of Sun 21 Mar 2027) and Type II period start (Mon 22 Mar 2027) | Engagement letter with period dates; CPA fieldwork; first in-period evidence for every recurring control; Type II report targeted after a 3-6 month period (confirm with CPA) | 22 | 4 | 25 | GC-14 | 21 | OK | OK | 2027-03-22 | 2027-04-16 | CPA | GRC | SOC 2 attestation | Type I report (draft) + Type II period running | AICPA SOC 2; TSC 2017 (2022 PoF) | Not started |  | ;GRC;
GC-16 | P5 Operationalize & Handover | GC | Independent assurance review (third line) | Outsourced IA tests 1st- and 2nd-line controls (risk, exceptions, TPRM, policy lifecycle, change, access); reports to Board/Audit Committee | 22 | 3 | 24 | GC-12, GC-14 | 21 | OK | OK | 2027-03-22 | 2027-04-09 | IA | GRC | Internal audit | IA report | IIA Three Lines; ISO 27001 9.2 | Not started |  | ;GRC;
BC-18 | P5 Operationalize & Handover | BC | Bug bounty and SEAL Safe Harbor decision (D-09) | Bounty scope/rewards; platform; Safe Harbor chain coverage incl. Solana confirmed with SEAL | 23 | 2 | 24 | BC-17 | 22 | OK | OK | 2027-03-29 | 2027-04-09 | BSE | PL; LEG | Bug bounty | Live bounty + D-09 | SEAL Safe Harbor; Immunefi | Not started |  | ;PL;LEG;
PM-15 | P5 Operationalize & Handover | PM | Lessons learned and next-year roadmap | External ID migration, Type II report (Q3 2027), CIS v7.1 deltas, Glamsterdam mainnet, PQ roadmap | 25 | 1 | 25 | PM-12, ID-14 | 24 | OK | OK | 2027-04-12 | 2027-04-16 | PL | CSE; ISE; BSE; GRC | Planning | FY roadmap | CSF 2.0 ID.IM | Not started |  | ;CSE;ISE;BSE;GRC;
PM-16 | P5 Operationalize & Handover | PM | Gate 4 - Program close and BAU acceptance (W26) | Criteria in Overview | 26 | 1 | 26 | PM-12, PM-13, PM-14, PM-15, GC-15, GC-16, BC-18, MR-17, MR-18, HD-15, HD-21, HD-18, HD-25, HD-26, ID-09, ID-16, ID-17, ID-19, GC-21, BC-28, BC-29, GC-28 | 25 | OK | OK | 2027-04-19 | 2027-04-23 | PL | PMC | Governance | Signed Gate 4 minute | Program governance | Not started |  | ;PMC;

## Roles & Skills
Roles & Skills - live counts from Project Plan; capacity rule: leads <= cap and weighted load (lead 1 + support 0.25) <= 4 x FTE
Partners and business contributors carry 0 program FTE. ENG supports only. Weekly load matrix below.
Role ID | Role | Type | Sourcing | Avg FTE (in window) | Window first wk | Window last wk | Core skills | Certifications / evidence | Lead cap (concurrent) | Tasks led | Tasks supported | First wk led | Last wk led | Peak concurrent leads | Load status | Peak weighted load | FTE-weeks
PL | Security Program Lead | Internal | Internal (existing) | 1 | 0 | 26 | Program/portfolio management, risk, executive and board comms, budget, vendor management | CISSP or CISM; PMP/PRINCE2 or equivalent delivery record | 3 | 18 | 13 | 0 | 26 | 3 | OK | 3.75 | 27
CSE | Cloud & Platform Security Engineer | Internal | Internal (existing) | 1 | 0 | 26 | AWS Organizations/Control Tower, SCP/RCP, EKS upgrades, VPC/TGW/Network Firewall, IaC | AWS Certified Security - Specialty; CKS | 3 | 16 | 21 | 0 | 22 | 3 | OK | 4 | 27
ISE | Identity & Security Operations Engineer (IR Lead) | Internal | Internal (existing) | 1 | 0 | 26 | Entra ID CA/PIM, IAM Identity Center, Splunk ES, incident handling | SC-300; SC-200 or Splunk ES Certified Admin; GCIH | 3 | 15 | 34 | 0 | 20 | 3 | OK | 4 | 27
GRC | GRC & Risk Lead (2nd line) | Internal | Internal (existing) | 1 | 0 | 26 | SOC 2, NIST CSF 2.0, ISO 27001, TPRM, risk, audit liaison | CISA and/or CRISC; ISO 27001 Lead Implementer | 3 | 13 | 21 | 0 | 21 | 3 | OK | 4 | 27
BSE | Blockchain Security Engineer | Internal | Internal (existing) | 1 | 0 | 26 | Solidity and Rust/Anchor review, Safe/Squads operations, MPC custody, staking mechanics, on-chain IR | Public audit/contest track record (audit reports, contest placings) | 3 | 20 | 25 | 0 | 24 | 3 | OK | 4 | 27
KHE | Contract Cloud/K8s Hardening Engineer | Contractor | Contractor (T&M) | 1 | 2 | 22 | CIS benchmarks, SSM, Image Builder, AL2023/Bottlerocket, EKS upgrades, Kubernetes admission policy | CKS; AWS Security Specialty; CIS-CAT experience | 3 | 13 | 9 | 2 | 19 | 3 | OK | 3.75 | 21
CPE | Contract Cloud Platform Security Engineer | Contractor | Contractor (T&M) | 1 | 3 | 20 | S3 Object Lock/log archive, AWS Backup/Aurora, KMS/Secrets Manager, EKS node groups, CloudFront/DNS | AWS Security Specialty or SA Professional | 3 | 9 | 0 | 3 | 17 | 3 | OK | 3 | 18
DET | Contract Detection Engineer (Splunk) | Contractor | Contractor (T&M) | 1 | 3 | 24 | SPL, Splunk ES 8 detections, contentctl detection-as-code, Splunk SOAR (Python 3.13) | Splunk Certified Cybersecurity Defense Engineer or ES Admin; GCDA/GCIA | 3 | 9 | 4 | 6 | 18 | 3 | OK | 3 | 22
IDC | Contract Identity Specialist (Entra/B2C) | Contractor | Contractor (T&M) | 0.5 | 3 | 18 | Entra CA/PIM/auth strengths/ID Protection, Azure AD B2C custom policies (IEF), External ID | SC-300; delivered B2C custom-policy projects | 2 | 9 | 0 | 3 | 18 | 2 | OK | 2 | 8
CSO | Contract Custody, Staking & Sanctions Specialist | Contractor | Contractor (T&M) | 1 | 3 | 22 | MPC custody policy engines, CCSS v9, Ethereum/Solana staking, OFAC wallet screening | CCSS auditor (CCSSA) or equivalent custody assessment record | 3 | 6 | 6 | 5 | 19 | 3 | OK | 3.25 | 20
BSC | Contract Smart-Contract Security Engineer | Contractor | Contractor (T&M) | 0.5 | 5 | 22 | Foundry/Slither/Aderyn/Echidna, Anchor 1.x/Trident/solana-verify, SIWE/SIWS | Public audit or contest record on EVM and Solana | 2 | 6 | 3 | 5 | 18 | 2 | OK | 2 | 9
GRCC | Contract SOC 2 Implementation Consultant | Contractor | Contractor (fixed fee) | 1 | 3 | 24 | Control matrices, policy drafting, GRC platform build, evidence design | CISA; >=3 SOC 2 implementations | 3 | 5 | 5 | 3 | 11 | 3 | OK | 3.5 | 22
PMC | Contract PMO Coordinator | Contractor | Contractor (T&M) | 0.5 | 1 | 26 | RAID/RACI, scheduling, procurement admin, KPI reporting, CAB secretariat | PMP/CAPM or equivalent | 2 | 4 | 9 | 2 | 22 | 1 | OK | 1.25 | 13
SCA | Smart-Contract Audit Firm | Partner | Partner (fixed scope) | 0 | 16 | 22 | Solidity + Rust/Anchor audit and fix review (parallel EVM and Solana teams) | Public audit reports on EVM and Solana | 1 | 1 | 1 | 16 | 19 | 1 | OK | 1 | 0
MDR | MDR Provider (24/7) | Partner | Partner (subscription) | 0 | 5 | 26 | 24/7 monitoring, triage, containment on AWS/Entra/EDR | SOC 2 Type II report; CrowdStrike/Splunk integration | 1 | 1 | 2 | 5 | 13 | 1 | OK | 1 | 0
PEN | Penetration Test Firm | Partner | Partner (fixed scope) | 0 | 18 | 22 | AWS/EKS, web/dApp, OAuth/OIDC/B2C testing | CREST or OSCP/OSWE testers | 1 | 1 | 1 | 18 | 19 | 1 | OK | 1 | 0
RDA | Independent SOC 2 Readiness Assessor | Partner | Partner (fixed fee) | 0 | 17 | 18 | SOC 2 readiness walkthroughs (different firm from GRCC and CPA) | CPA/CISA-led readiness practice | 1 | 1 | 0 | 17 | 18 | 1 | OK | 1 | 0
CPA | SOC 2 CPA Firm (independent auditor) | Partner | Partner (engagement) | 0 | 5 | 26 | SOC 2 attestation under AICPA standards | Licensed CPA firm; crypto/fintech SOC 2 references | 1 | 1 | 1 | 22 | 25 | 1 | OK | 1 | 0
LEG | External Regulatory Counsel | Partner | Partner (engagement) | 0 | 0 | 4 | MiCA reverse solicitation, US money transmission/FinCEN, OFAC, staking | Digital-asset regulatory practice | 1 | 0 | 4 | - | - | 0 | OK | 0.5 | 0
IA | Independent Assurance (outsourced internal audit) | Partner | Partner (engagement) | 0 | 22 | 24 | Independent testing of 1st- and 2nd-line controls; reports to Board/Audit Committee | IIA standards; CIA/CISA | 1 | 1 | 0 | 22 | 24 | 1 | OK | 1 | 0
HRB | People Ops Partner (business contributor) | Internal-BAU | Internal (outside program FTE) | 0 | 0 | 26 | Background checks, joiner/mover/leaver, code of conduct | HR operations | 1 | 1 | 1 | 11 | 13 | 1 | OK | 1 | 0
ENG | Platform & App Engineering teams (change implementers) | Internal-BAU | Internal (outside program FTE) | 0 | 0 | 26 | Workload migration, CI/CD, application changes | n/a - supporting only, never lead | 0 | 0 | 34 | - | - | 0 | OK | 2.75 | 0
Internal program FTE (total) |  |  |  | 5 |  | Contractor FTE-weeks | 133
Contractor FTE (peak concurrent week) |  |  |  | 6.5 |  | Internal FTE-weeks | 135
Partner / firm engagements (count) |  |  |  | 7
Internal within 3-5 FTE range? |  |  |  | YES
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Contractor FTE by week | wk -> | 0 | 0.5 | 1.5 | 6 | 6 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6 | 6 | 5 | 5 | 2.5 | 2.5 | 0.5 | 0.5
Concurrent LEAD tasks per role per week
Role | Cap | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PL | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CSE | 3 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
ISE | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
GRC | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
BSE | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
KHE | 3 | 0 | 0 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPE | 3 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DET | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IDC | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSO | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BSC | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRCC | 3 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMC | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
SCA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDR | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PEN | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RDA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
LEG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
HRB | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weighted load per role per week (lead 1.0 + support 0.25); limit 4 x FTE
Role | Limit | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PL | 4 | 3.25 | 2.25 | 2.5 | 3.5 | 2.75 | 2.5 | 3.75 | 1.5 | 2.5 | 1.25 | 1 | 0.25 | 0.25 | 0.25 | 0.5 | 1.25 | 0.5 | 0.25 | 0 | 0.25 | 1.25 | 1 | 1 | 1.25 | 1.25 | 1 | 1
CSE | 4 | 3.25 | 3 | 2.25 | 3.75 | 3 | 3.75 | 4 | 4 | 2.75 | 3.5 | 2.5 | 3.75 | 3.5 | 3.25 | 3.5 | 3.75 | 3.75 | 3.5 | 3.25 | 2.5 | 2.25 | 1.5 | 1.25 | 0.25 | 0.25 | 0.25 | 0
ISE | 4 | 4 | 3.75 | 1.25 | 3.75 | 4 | 3.25 | 4 | 4 | 3 | 3 | 3 | 3.75 | 3.75 | 4 | 3.5 | 2.75 | 2.5 | 1.75 | 1 | 1.5 | 1.25 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0
GRC | 4 | 1.25 | 1.5 | 1.5 | 2.75 | 3.5 | 3.75 | 4 | 3.75 | 4 | 3.25 | 2.25 | 2.75 | 3 | 3 | 2.75 | 2.25 | 3 | 1.25 | 0.25 | 1 | 1 | 1.5 | 1 | 0.75 | 0.75 | 0.5 | 0
BSE | 4 | 3.75 | 3.5 | 3.5 | 3.5 | 3.5 | 4 | 3.25 | 3.25 | 3.75 | 3.25 | 1.25 | 3.75 | 3 | 4 | 2.75 | 3.5 | 3 | 2 | 0.75 | 1 | 1.5 | 1.5 | 1.25 | 1.25 | 1.25 | 0.25 | 0
KHE | 4 | 0 | 0 | 3.25 | 3.5 | 3.5 | 1.75 | 3.5 | 3.5 | 3.5 | 3.75 | 3.5 | 3.75 | 2.75 | 2.75 | 2.75 | 2.75 | 3.75 | 3.5 | 2.5 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPE | 4 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DET | 4 | 0 | 0 | 0 | 0.25 | 0.25 | 0.5 | 1.25 | 2.25 | 2.25 | 2.25 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | 0
IDC | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSO | 4 | 0.5 | 0.5 | 0.25 | 0 | 0 | 1 | 2.5 | 2.5 | 2.5 | 1.5 | 1.25 | 2.5 | 3.25 | 3.25 | 2.25 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BSC | 2 | 0 | 0 | 0 | 0.25 | 0.25 | 1.25 | 2 | 2 | 1.25 | 1.25 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
GRCC | 4 | 0 | 0 | 0 | 1 | 2 | 2.25 | 3.5 | 3.5 | 3 | 2 | 1 | 1 | 0 | 0.25 | 0.25 | 0.25 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
PMC | 2 | 0.25 | 0.5 | 1.25 | 1 | 1 | 1 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.25 | 0 | 0 | 0 | 0.25 | 1.25 | 1.25 | 0.25 | 0.25 | 0 | 0.25
SCA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
MDR | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
PEN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
RDA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPA | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
LEG | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.25 | 0.25 | 0.5 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0 | 0
IA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
HRB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENG | 0 | 0.5 | 0.5 | 1.25 | 1 | 1 | 1 | 2 | 2 | 1.5 | 2 | 2 | 2.5 | 2.75 | 2.75 | 2 | 2 | 1.5 | 1.5 | 1 | 0.75 | 0.75 | 0.5 | 0.5 | 0 | 0 | 0 | 0

## RACI
RACI - workstream x role (R Responsible, A Accountable, C Consulted, I Informed, - none)
Exactly one A per workstream. Executive sponsor (CEO/COO) chairs Steering and is accountable for the program overall.
WS | Workstream | PL | CSE | ISE | GRC | BSE | KHE | CPE | DET | IDC | CSO | BSC | GRCC | PMC | SCA | MDR | PEN | RDA | CPA | LEG | IA | HRB | ENG | # of A (must be 1)
HD | OS & Container Hardening (org guardrails, network, EOL) | I | A | C | C | I | R | R | I | - | - | - | I | I | - | I | C | - | - | - | - | - | R | 1
ID | Identity Hardening (workforce, customer, workload, wallet sign-in) | I | C | A | C | R | - | R | C | R | - | R | I | I | - | I | C | - | - | - | - | C | R | 1
MR | Security Monitoring, Response & Resilience | C | R | A | C | R | C | R | R | C | R | - | I | I | - | R | R | - | - | C | - | - | C | 1
BC | Blockchain Security | C | C | C | C | A | - | - | C | - | R | R | I | I | R | I | C | - | - | C | - | - | R | 1
GC | Governance & Compliance | C | C | C | A | C | - | - | - | - | R | - | R | R | - | - | - | R | R | R | R | R | I | 1
PM | Program Management & Sustainment | A | R | R | R | R | I | I | I | I | I | I | I | R | I | I | I | I | I | I | I | I | I | 1
Role key
PL | Security Program Lead
CSE | Cloud & Platform Security Engineer
ISE | Identity & Security Operations Engineer (IR Lead)
GRC | GRC & Risk Lead (2nd line)
BSE | Blockchain Security Engineer
KHE | Contract Cloud/K8s Hardening Engineer
CPE | Contract Cloud Platform Security Engineer
DET | Contract Detection Engineer (Splunk)
IDC | Contract Identity Specialist (Entra/B2C)
CSO | Contract Custody, Staking & Sanctions Specialist
BSC | Contract Smart-Contract Security Engineer
GRCC | Contract SOC 2 Implementation Consultant
PMC | Contract PMO Coordinator
SCA | Smart-Contract Audit Firm
MDR | MDR Provider (24/7)
PEN | Penetration Test Firm
RDA | Independent SOC 2 Readiness Assessor
CPA | SOC 2 CPA Firm (independent auditor)
LEG | External Regulatory Counsel
IA | Independent Assurance (outsourced internal audit)
HRB | People Ops Partner (business contributor)
ENG | Platform & App Engineering teams (change implementers)

## Governance Model
Governance Model - forums, three lines, policy lifecycle, evergreen loop, operating calendar, triggers
Forum | Cadence | Membership | Decision rights | Inputs | Outputs
Security Steering Committee (incl. Risk & Compliance review) | Monthly (60 min) + at gates W6/W15/W20/W26 | CEO or COO (chair), CTO, CFO, Security Program Lead, GRC Lead; IA attends quarterly; reports quarterly to the Board | Scope, budget, gate pass/fail, risk acceptance above appetite, policy approval, regulatory go/no-go | KPI/KRI pack, risk register, exceptions due, decision log, gate evidence | Signed minutes, decisions, risk acceptances
Architecture Review Board | Fortnightly (first 30 min of the weekly CAB slot); monthly in BAU | Head of Platform (chair), Cloud & Platform Sec Eng, Identity & SecOps Eng, Blockchain Sec Eng, Program Lead | Approve designs/standards; grant time-boxed exceptions (max 90 days) to standards | Design packs, threat model deltas, benchmark changes | Approvals log, exception records
Contract Upgrade & Key Committee (CUKC) | Fortnightly (30 min) + ad hoc within 4h for emergencies | Head of Blockchain Engineering (internal chair), Blockchain Sec Eng (security veto), Custody Ops lead, Program Lead, Legal on call | Approve contract/program deploys and upgrades, signer/threshold/timelock changes, custody policy-engine changes, staking authority/consolidation actions | Audit/diff reports, verified-build hashes, simulation results, monitoring updates | Signed change record; on-chain tx hashes
Change Advisory Board | Weekly; emergency CAB within 2h | Head of Platform/SRE (chair), service owners, Cloud & Platform Sec Eng | Approve production changes (standard/normal/emergency); enforce freeze windows | Change requests with rollback plans | Approved change calendar
Incident Response forum | 24/7: interim internal on-call W0-W12, MDR from W13 (phased from W5); monthly IR review; post-incident review within 5 business days | IR Lead (Identity & SecOps Eng), MDR, Blockchain Sec Eng for on-chain, Program Lead, Legal/Comms | Declare/close incidents, contain, notify (per D-01 matrix), invoke CUKC emergency pause | Alerts, MDR escalations, on-chain monitor alerts | Incident records, PIR actions
Independent assurance | Annual internal-audit cycle (first review W22-W24) + annual SOC 2 by CPA | Outsourced internal audit reporting directly to the Board/Audit Committee; SOC 2 CPA firm; independent readiness assessor | Independently test 1st- and 2nd-line controls; report findings directly to Steering/Board | Control matrix, evidence, risk register | IA report; SOC 2 report
Three lines model
Line | Who | Responsibilities
1st line - own and operate controls | Cloud & Platform Sec Eng, Identity & SecOps Eng, Blockchain Sec Eng, Platform/App engineering, Custody Ops | Implement and run controls; self-assess; raise exceptions
2nd line - oversee and challenge | GRC & Risk Lead (with SOC 2 readiness consultant during program) | Policies, risk register, control monitoring in GRC platform, TPRM, exception expiry; never tests controls it operates
3rd line - independent assurance | Outsourced internal audit (reports to Board/Audit Committee); SOC 2 CPA firm; independent readiness assessor | Independent testing of 1st- and 2nd-line controls; the implementation consultant (GRCC), readiness assessor (RDA) and CPA are three different firms
Policy lifecycle (version-controlled in git)
Stage | What happens | Owner
1 Draft | Author opens a pull request in the policy git repo (markdown, semantic version) | Policy owner
2 Review | GRC review against control matrix; SME review; legal where needed | GRC Lead
3 Approve | Policies: Steering; standards/procedures: ARB or owning forum | Steering / ARB
4 Publish & attest | Tagged release; staff acknowledgement tracked in GRC platform | GRC Lead
5 Operate & monitor | Mapped controls tested automatically where possible; exceptions time-boxed | Control owners
6 Review | Annually, or within 30 days of a trigger event | Policy owner
7 Retire | Superseded versions archived; mapping updated | GRC Lead
Evergreen loop
Step | Mechanism | Owner
1 Monitor | Automated control health (Security Hub CSPM, Inspector, GRC platform tests, Splunk silent-source alerts, on-chain monitors) | Control owners (1st line)
2 Measure | KPI/KRI pack refreshed weekly; exceptions and expiry tracked | PMC -> GRC in BAU
3 Review | Monthly Steering + risk & compliance review; ARB/CUKC/CAB on changes; quarterly board report | Steering
4 Improve | Corrective-action log; design changes via ARB; threat-model and benchmark refresh on triggers | Workstream leads
5 Assure | Independent assurance (IA annually; SOC 2 Type II annually; readiness assessor separate from CPA) | 3rd line
Operating calendar
Cadence | Activities
Weekly | Audit-evidence calendar check; vulnerability & patch SLA review; Security Hub score delta; detection tuning; CAB; CUKC; on-chain/validator alert review; KPI auto-refresh
Monthly | Steering + risk & compliance review; KPI/KRI pack; exception expiry sweep; privileged access review; phishing simulation; staking provider performance report; EOL register update
Quarterly | Full access reviews (Entra, AWS, custody approvers, multisig signers); tabletop exercise; automated tier-1 restore tests; signer key-ceremony drill; board cyber report; benchmark/version check (CIS, EKS, Agave/Firedancer, Safe/Squads); threat-model refresh; SCIM/secret expiry check
Semi-annual | Policy review tranche; pause/guardian drill; staking & custody vendor reassessment; on-chain monitoring coverage review; IR plan update
Annual | SOC 2 Type II examination; penetration test (plus after major change); full DR test; security and fraud risk assessment & risk appetite refresh; management review; cyber insurance renewal; vendor exit-plan test; policy re-approval; internal audit; training refresh; crypto-agility/PQ roadmap review; CSF 2.0 profile re-baseline
Event triggers that force re-assessment
Trigger | Required response
Contract deploy or upgrade | CUKC approval; audit or diff review; verified build; monitor rules updated before execution; timelock respected
Hard fork or client release (e.g. Glamsterdam mainnet, Agave/Firedancer majors) | Fork runbook; provider written readiness; testnet regression; heightened monitoring 72h
New benchmark or vendor version (CIS, EKS EOS, Splunk/Security Hub change) | Gap mapping within 30 days; ARB decision; KPI targets adjusted
Major incident (internal or industry, e.g. multisig/UI compromise) | Post-incident review; threat model update; control changes via ARB/CUKC
New vendor or material vendor change | TPRM tiering and due diligence before contract; SOC report review
Regulatory change or new market (e.g. EU marketing, US market-structure law) | Counsel review; D-01 refresh; re-plan if in scope
Signer, admin or key-person change | Signer rotation; access revocation within 24h; contractor-dependency KRI update
EOL announcement (OS, Kubernetes, tooling) | EOL register entry with owner/date; exception if needed
Exception reaching expiry | Remediate or one renewal max (Steering approval); second expiry escalates as a risk acceptance
Contractor exit or contract change | Knowledge-transfer check; access revoked within 24h; contractor-dependency KRI recalculated
Framework mapping by workstream
WS | NIST CSF 2.0 | ISO 27001:2022 Annex A / clauses | CIS Controls v8.1 | Benchmarks / standards | SOC 2 TSC | Security Hub CSPM control IDs
HD | PR.PS, PR.IR, ID.AM | A.8.8, A.8.9, A.8.20-8.22, A.8.25-8.28 | 1, 2, 4, 7, 12, 13 | CIS AWS Foundations v5.0.0 (automated) / v7.1.0 (manual delta); CIS AL2023 v1.0.0; CIS EKS v2.0.0; CIS EKS Auto Mode v1.0.0; CIS Kubernetes v2.1.0; CIS Bottlerocket v1.0.0 | CC6.1, CC6.6, CC6.8, CC7.1, CC8.1 | EC2.2/.6/.7/.8/.9/.170, SSM.1-.3, EKS.1/.2/.8/.9, ECR.1-.3, S3.1/.5, KMS.3/.4, RDS.2/.3/.7/.8/.27, ELB.1/.4/.5/.16, WAF.10/.11, NetworkFirewall.2/.4/.5, Opensearch.1/.3/.5/.7, EFS.8, SQS.1, SNS.1, Kinesis.1, ACM.1, Inspector.1-.4
ID | PR.AA, GV.RR | A.5.15-5.18, A.8.2, A.8.5 | 5, 6 | Microsoft Entra guidance; OWASP ASVS (customer auth); EIP-4361 (Final); EIP-1271 | CC6.1-CC6.3 | IAM.1/.2/.4/.6/.8/.22, SecretsManager.1/.3
MR | DE.CM, DE.AE, RS.*, RC.* | A.5.24-5.28, A.8.13-8.16, A.5.29-5.30 | 8, 10, 11, 13, 17, 18 | NIST SP 800-61r3; MITRE ATT&CK; SEAL Incident Mgmt/Monitoring | CC7.2-CC7.5, A1.2-A1.3 | GuardDuty.1/.5/.7/.8/.10/.11, CloudTrail.1/.2/.4, Config.1, Backup.1, RDS.11/.14
BC | PR.DS, PR.PS, GV.SC, ID.RA | A.8.24, A.8.25-8.29, A.5.19-5.22 | 3, 16 | BSSC SCS, KMS, NOS v2, TIS, GSP; CCSS v9.0; OWASP SC Top 10 2026 / SCSVS; SEAL Frameworks | CC6.1, CC6.7, CC8.1, CC9.2 | n/a (off-AWS)
GC | GV.OC, GV.RM, GV.RR, GV.PO, GV.OV, GV.SC | Clauses 4-10; A.5.1-5.37; A.6.1-6.8 | 14, 15 | AICPA TSC 2017 (2022 PoF); NIST CSF 2.0; ISO/IEC 27001:2022; CIS Controls v8.1; MiCA/DORA/PCI (go/no-go) | CC1-CC5, CC9 | Account.1
PM | GV.OV, ID.IM | Clauses 6, 9, 10 | - | Program governance | CC3, CC4 | -

## KPIs
KPIs and KRIs - fill 'Current value' and 'Named owner' (yellow); RAG is manual
Example row format for Current value: '87%' or '3'. Owner role is the proposed accountable role.
ID | KPI | Definition | Target | Data source | Frequency | Owner role (proposed) | Current value | Named owner | RAG
K01 | CIS AL2023 Level 1 pass rate (EC2 fleet) | Passed L1 checks / total applicable L1 checks across scanned AL2023 instances | >=90% by W20 | Amazon Inspector CIS scans | Weekly | CSE
K02 | Amazon Linux 2 / EOL OS instance count | Running instances and node groups on AL2 or other EOL OS | 0 (or approved exceptions with expiry) by W20 | AWS Config / SSM inventory | Weekly | CSE
K03 | EKS clusters on a standard-support version | Clusters on a version in standard support / all clusters | 100% by W18 | EKS API; Security Hub EKS.2/EKS.9 | Weekly | CSE
K04 | Patch SLA compliance (critical <=7d, high <=14d) | Findings remediated within SLA / findings due in period | >=95% from W12 | SSM Patch Manager; Inspector | Weekly | KHE -> CSE
K05 | IMDSv2 coverage | Instances requiring IMDSv2 / all instances | 100% of instances by W12 | Security Hub EC2.8 / EC2.170 | Weekly | CSE
K06 | Security Hub CSPM security score (FSBP + CIS v5.0.0) | Security Hub CSPM score as reported | >=90% by W20 | Security Hub CSPM | Weekly | CSE
K07 | Production workloads running signed images | Prod pods/tasks from signed images / all prod pods/tasks | 100% by W19 | ECR signing + admission/CI logs | Weekly | KHE -> CSE
K08 | Admins using phishing-resistant (device-bound FIDO2) MFA | Privileged-role holders with enforced FIDO2 strength / all privileged-role holders | 100% by W12 | Entra authentication-methods report | Weekly | ISE
K09 | Standing privileged admins (excl. 2 break-glass) | Permanent privileged assignments other than break-glass | 0 by W15 | Entra PIM; IAM Identity Center | Weekly | ISE
K10 | Customer withdrawals / payout-address changes protected by step-up MFA | Withdrawal/payout-change requests with fresh step-up (auth_time <=5 min) / all such requests | 100% of flows by W13 | B2C logs + withdrawal API logs in Splunk | Monthly | ISE
K11 | MTTD - identity high-severity events | Event _time to notable/MDR ticket creation | Median <=15 min; p90 <=60 min from W14 | Splunk ES / MDR tickets | Monthly | ISE
K12 | MTTD - on-chain privileged events | Block timestamp to alert delivered to pager | Median <=5 min; p90 <=15 min from W13 | On-chain monitor + Splunk | Monthly | BSE
K13 | MTTA - Sev-1/Sev-2 alerts | Alert creation to human acknowledgement | p90 <=15 min from W13 | Pager / MDR tickets | Monthly | ISE
K14 | MTTR - Sev-1 containment | Acknowledgement to containment action logged | Median <=4 h; p90 <=8 h from W17 | Splunk SOAR / IR records | Monthly | ISE
K15 | Upgrade/admin on-chain roles under multisig + timelock | Roles meeting role-matrix controls / all upgrade/admin roles (pause guardian measured against its own matrix row) | 100% by W15 | Privileged-role register verified on-chain | Monthly | BSE
K16 | Staking - Ethereum: effectiveness vs provider SLA; slashing events | Per provider SLA definition; slashing events count | >= SLA; 0 slashing | Provider reports + own beacon monitoring | Weekly | BSE
K17 | Staking - Solana: participation vs SLA; delinquent epochs; authority mismatches | Post-Alpenglow metric definitions to be confirmed in MR-14 | >= SLA; 0 delinquent epochs; 0 mismatches | Provider reports + own RPC monitoring | Weekly | BSE
K18 | SOC 2 automated control pass rate | Passing automated tests / automated tests mapped in control matrix (denominator fixed in GC-05) | >=95% by W20 | GRC platform | Weekly | GRC
K19 | Prioritised ATT&CK techniques with validated detections | Validated techniques / techniques prioritised in MR-04 | >=80% by W18 | Purple-team results | Quarterly | ISE
K20 | Exceptions past expiry | Open exceptions beyond expiry date | 0 | Exception register | Monthly | GRC
K21 | Tier-1 restore tests meeting RTO/RPO | Successful tier-1 restore tests within RTO/RPO / tier-1 tests run | 100% per quarter | AWS Backup restore testing records | Quarterly | CSE
K22 | Security training completion (incl. signer & secure-coding tracks) | Completed / assigned | >=95% by W17 | LMS / GRC platform | Monthly | GRC
K23 | Audit evidence delivered on time | Evidence items delivered by due date / due | >=95% from W22 | GRC platform evidence calendar | Monthly | GRC
K24 | Post-incident and pentest actions closed on time | Actions closed by due date / due | >=90% | IR / remediation tracker | Monthly | PL
K25 | Tier-1 vendor reviews current | Tier-1 vendors with in-date review / tier-1 vendors | 100% | TPRM register | Quarterly | GRC
Key risk indicators
ID | KRI | Threshold | Data source | Frequency | Owner role | Current value | Named owner
KRI-1 | Contractor dependency: critical runbooks without a trained internal owner | 0 by W24 | Handover tracker | Monthly | PL
KRI-2 | Lead tasks held by contractors after W24 | 0 | Project Plan | Monthly | PL
KRI-3 | Days of telemetry gap on any tier-1 log source | 0 per month | Splunk silent-source alerts | Monthly | ISE

## Risks and Decisions
Risk register (rating = likelihood x impact, 1-5 scales) and decision log (alignment checked by formula)
ID | Risk | Likelihood (1-5) | Impact (1-5) | Rating | Level | Mitigation | Owner
R01 | AL2 workloads cannot migrate on time (app dependencies) | 4 | 4 | 16 | High | Containment (HD-03), two migration waves, time-boxed exceptions with expiry, CrowdStrike prevention | CSE
R02 | EKS forced upgrade after 26 Nov 2026 breaks workloads | 3 | 4 | 12 | Medium | HD-02 controlled 1.31->1.32 upgrade by W4; add-on testing; rollback | CSE
R03 | Staking provider mishandles Alpenglow/Glamsterdam -> missed rewards or slashing | 3 | 3 | 9 | Medium | BC-01 written confirmation; MR-14 monitoring; contract amendments BC-19 | BSE
R04 | Signer-UI compromise or multisig social engineering (Bybit/Drift patterns) | 3 | 5 | 15 | High | BC-10 timelocks/thresholds/delegatecall guard/durable-nonce ban; BC-11 clear signing and independent hash check; MR-13 alerts | BSE
R05 | Smart-contract audit slot slips | 3 | 4 | 12 | Medium | Book in W1-2 (PM-03) sized by nSLOC; code freeze W15; parallel EVM/Solana teams; backup auditor shortlisted | PL
R06 | Small team overload / key-person dependency | 4 | 4 | 16 | High | Capacity rule enforced (<=3 leads and weighted <=4.0 per FTE); 8 contractors for build peaks; deputies named in RACI | PL
R07 | Contractor dependency persists after handover | 3 | 3 | 9 | Medium | K20 KRI; handover PM-12 with internal owners; contractor access revoked at exit | PL
R08 | Splunk ingest/licence overrun (Entra non-interactive logs 5-10x; OCSF volumes) | 4 | 3 | 12 | Medium | Volume sizing in MR-03; filtering at Event Hub/HEC; tiered retention | ISE
R09 | Customer account takeover on withdrawals (B2C has no risk-based protection after P2 retirement) | 3 | 4 | 12 | Medium | Step-up MFA (ID-13); fraud/bot vendor (D-13); detections | ISE
R10 | Regulatory scope changes (EU solicitation found; US market-structure law) | 2 | 5 | 10 | Medium | D-01 with counsel; regulatory-change trigger; quarterly watch | GRC
R11 | Unverified vendor claims (Solana monitoring coverage; CrowdStrike AL2023/Bottlerocket support) | 3 | 3 | 9 | Medium | Written confirmation as contract condition (BC-09, HD-13) | BSE
R12 | Holiday period W9-W10 reduces capacity | 4 | 2 | 8 | Medium | Freeze prod changes; schedule design/non-prod work; no gates in W9-W10 | PL
R13 | SOC 2 Type I exceptions | 3 | 3 | 9 | Medium | Independent readiness (GC-13) and remediation (GC-14) before as-of date | GRC
R14 | Budget not approved for licences/partners | 3 | 4 | 12 | Medium | Budget envelope at Gate 1; prioritised fallback scope | PL
R15 | Glamsterdam mainnet scheduled inside program; gas repricing breaks contracts | 2 | 4 | 8 | Medium | BC-04/BC-14 remediation and Hoodi regression; fork trigger procedure | BSE
R16 | Insider / DPRK IT-worker infiltration | 2 | 5 | 10 | Medium | GC-11 screening; least privilege; PIM; signer separation | GRC
R17 | Business is custodial / an MSB -> FinCEN, state licensing, FTC Safeguards obligations not in plan | 3 | 5 | 15 | High | D-01 answers explicitly; re-plan at Gate 1 if yes | GRC
R18 | EKS 1.32 forced auto-upgrade after 23 Mar 2027 (no notice, no rollback) | 2 | 4 | 8 | Medium | HD-16B completes hops by W18; HD-24 readiness matrix | CSE
R19 | Entra/B2C log evidence lost (30-day / 7-day retention) | 4 | 3 | 12 | Medium | MR-21 archive in W0-W1 | CSE
R20 | Cost overrun: Security Hub per-resource pricing, EKS extended support ($0.60/cluster-hr), Splunk ingest | 3 | 3 | 9 | Medium | D-15 cost decision W4; D-10 upgradePolicy; filtering | PL
R21 | No 24/7 response before MDR is live (incl. holiday weeks) | 3 | 4 | 12 | Medium | MR-00 interim on-call and paging; MDR phased from W5 | ISE
R22 | Internal roles run at the capacity limit (3 leads, weighted 4.0) in several weeks | 3 | 3 | 9 | Medium | PMO coordinator; weekly load review; Steering can descope low-priority tasks (e.g. HD-26/HD-30) | PL
Decision log
ID | Decision | Options | Owning task | Due week | Due date (Fri) | Needed by (task IDs) | Owning task end wk | Earliest consumer start wk | Alignment | Decision taken / date
D-01 | Regulatory scope: MiCA/DORA/PCI no-go conditions; custodial/MSB/state licensing/Safeguards Rule; OFAC | Out of scope with conditions / in scope (re-plan at G1) / partial | GC-01 | 4 | 2026-11-20 | GC-04, MR-05, GC-07, GC-22, GC-23 | 4 | 5 | ALIGNED
D-02 | Entra licensing (admins, access-review population, workforce risk CA, workload identities) | P2 / ID Governance / Entra Suite / Workload ID Premium | ID-03 | 5 | 2026-11-27 | ID-08, ID-09, ID-16 | 5 | 7 | ALIGNED
D-03 | MDR provider and 24/7 owner per alert source | Falcon Complete Next-Gen MDR / Splunk-integrated MDR / other | MR-02 | 4 | 2026-11-20 | MR-11 | 4 | 5 | ALIGNED
D-04 | GRC platform | Vanta / Drata / Secureframe | GC-03 | 4 | 2026-11-20 | GC-09 | 4 | 6 | ALIGNED
D-05 | EKS node OS | AL2023 managed nodes / Bottlerocket / EKS Auto Mode | HD-05 | 4 | 2026-11-20 | HD-08, HD-13, HD-16A, HD-23, HD-26 | 4 | 5 | ALIGNED
D-06 | Customer identity strategy | Stay on B2C to 2029 / migrate to External ID FY27 / other CIAM | ID-14 | 15 | 2027-02-05 | PM-15 | 15 | 25 | ALIGNED
D-07 | On-chain monitoring vendor | Hypernative / Hexagate / OZ Monitor self-hosted / combination | BC-09 | 6 | 2026-12-04 | MR-13 | 6 | 7 | ALIGNED
D-08 | SOC 2 TSC scope and subservice treatment | Security only / +Availability / +Confidentiality; carve-out vs inclusive | GC-07 | 7 | 2026-12-11 | GC-05, GC-13 | 7 | 8 | ALIGNED
D-09 | Bug bounty platform and SEAL Safe Harbor | Immunefi / other; adopt Safe Harbor yes/no | BC-18 | 24 | 2027-04-09 | PM-16 | 24 | 26 | ALIGNED
D-10 | EKS 1.34 clusters and upgradePolicy | Upgrade to 1.35 before 2 Dec / EXTENDED at $0.60 per cluster-hr | HD-01 | 2 | 2026-11-06 | HD-02 | 1 | 2 | ALIGNED
D-11 | Admission policy engine and image-signature verifier | ValidatingAdmissionPolicy / Kyverno; verifier for ECR signatures | HD-08 | 6 | 2026-12-04 | HD-17, HD-18 | 6 | 11 | ALIGNED
D-12 | SOC 2 Type I first vs straight to Type II | Type I as-of 21 Mar 2027 + gap-free Type II / Type II only | GC-07 | 7 | 2026-12-11 | GC-15 | 7 | 22 | ALIGNED
D-13 | B2C fraud/bot protection vendor | Vendor shortlist / defer | ID-06 | 7 | 2026-12-11 | ID-13 | 7 | 9 | ALIGNED
D-14 | Hot-wallet caps and velocity limits | Per risk appetite tiers | PM-04 | 3 | 2026-11-13 | BC-12 | 3 | 11 | ALIGNED
D-15 | Security services plan and cost (Security Hub per-resource, GuardDuty, Inspector, EKS extended, Splunk ingest) | Essentials / add-ons / reduced scope | MR-23 | 4 | 2026-11-20 | MR-07, HD-21 | 4 | 7 | ALIGNED
D-17 | Contractor capacity envelope (8 contractors, 6.5 FTE peak, 133 FTE-weeks) vs descope | Approve / approve with descope list (HD-26, HD-30, BC-20, ID-17) / reject | PM-02A | 1 | 2026-10-30 | PM-03 | 0 | 1 | ALIGNED
D-16 | AWS just-in-time elevation approach | PIM for Groups via SCIM / alternative tool (verify maintenance) | ID-04 | 5 | 2026-11-27 | ID-11, ID-09 | 5 | 9 | ALIGNED
Formulas:
Level = Overview!$B4+7*([Rating]-1)+4

## Review Log
Independent review log (v1 -> v2): four adversarial reviewers + lead re-verification
Status 'Deferred' or 'UNVERIFIED' items carry a named validation task.
ID | Reviewer | Task ID(s) | Severity | Finding | Resolution in v2 | Status
RV-01 | Cloud/OS & container | MR-01 | Critical | GuardDuty Runtime Monitoring agents need SSM (HD-06 W2-6), SCP allowance for guardduty:SendSecurityTelemetry, ECS agent >=1.77.0; EKS on Fargate unsupported. | Split: MR-01 agentless services W0-1; new MR-01B runtime agents W7-8 after HD-06 + CAB; SCP allowance added to HD-04; Fargate gap HD-25; Gate 1 criterion reworded. | Fixed
RV-02 | Cloud/OS & container | HD-06 | High | Default Host Management Configuration needs IMDSv2 and can't attach the Inspector CIS policy; existing instance profiles take precedence. | Instance profiles as primary path; DHMC only where no profile; per-instance IMDSv2 conversion; extended to W2-W6. | Fixed
RV-03 | Cloud/OS & container | HD-16 | Critical | Node OS migration too late (AL2 EOS 30 Jun 2026); 4 version hops in 8 weeks; started in freeze; binding deadline is 1.32 end of extended support 23 Mar 2027 (W22), not 27 Mar. | Split into HD-16A (node groups to AL2023/Bottlerocket at 1.32, W6-W8 before freeze) and HD-16B (hops to 1.36, W11-W18); new HD-24 upgrade-readiness matrix W2-W4; D-05 moved to W4. | Fixed
RV-04 | Cloud/OS & container | HD-02 / D-10 | High | No task executed the 1.34 decision; upgradePolicy (STANDARD auto-upgrades at end of standard support) not inventoried; extended-support cost not costed. | HD-01 records upgradePolicy; D-10 due W2 (owner HD-01); HD-02 W2-W5 covers 1.31 and 1.34; cost into D-15/R20. | Fixed
RV-05 | Cloud/OS & container | HD-04 / HD-10 | Medium | IMDSv2 hop limit per workload type; VPC BPA exclusions; allowed-images audit mode; prod steps in freeze. | Added to HD-04 activities; HD-10 prod from W11; freeze rule in Overview. | Fixed
RV-06 | Cloud/OS & container | HD-12 / HD-05 | Medium | Inspector CIS is x86_64-oriented; Bottlerocket excluded; alternate method undefined. | Noted in HD-05/HD-12; new HD-26 Bottlerocket CIS evidence (method to verify). | Fixed (method UNVERIFIED)
RV-07 | Cloud/OS & container | MR-06 | Medium | Only some resource types back up directly to the air-gapped vault; Aurora backtrack is MySQL-only; no EKS backup design. | MR-06 activities corrected; EKS backup approach added (verify AWS Backup EKS support). | Fixed (EKS support UNVERIFIED)
RV-08 | Cloud/OS & container | Cost | Low | Security Hub per-resource pricing decision needed before trial ends (~W4). | New MR-23 + D-15 due W4. | Fixed
RV-09 | Cloud/OS & container | HD-18 | Low | ECS has no admission control for signatures. | HD-18: CI/CD signature gate for ECS. | Fixed
RV-10 | Cloud/OS & container | HD-09 | Low | CIS v7.1.0 delta should precede control matrix. | HD-09 moved to W6-7; GC-05 depends on it. | Fixed
RV-11 | Cloud/OS & container | Missing | High | Missing: immutable log archive, ECS-on-EC2 AL2 migration, EKS readiness matrix, Fargate gap, Bottlerocket CIS, Control Tower drift, root credential removal, DNS/registrar/CloudFront, Macie. | Added HD-22, HD-23, HD-24, HD-25, HD-26, HD-27, HD-30; root removal in ID-01/ID-11; DNS/registrar in BC-25. | Fixed
RV-12 | Identity & monitoring | MR-11 / MR-02 | Critical | No 24/7 coverage W0-W13 incl. holiday freeze; detection services enabled with no alert routing. | New MR-00 interim on-call + paging W0-W1; MDR signed W4 and onboarded in phases W5-W13 (MR-11 led by MDR). | Fixed
RV-13 | Identity & monitoring | ID-01 | High | Break-glass alert depended on Splunk (W7+); no AWS break-glass; centralized root mgmt doesn't cover management account. | Interim Log Analytics alert to pager; AWS break-glass via management-account root (2 FIDO2) + emergency role. | Fixed
RV-14 | Identity & monitoring | ID-08 / ID-10 | High | CA enforced before FIDO2 keys enrolled; no procurement task; enforcement in freeze. | New ID-00 (order W0); ID-10 W9-10; ID-08 report-only W7-10; new ID-08B enforce W11-12 depending on ID-10; AAGUID allowlist. | Fixed
RV-15 | Identity & monitoring | ID-03 / D-02 | High | Licensing scoped to admins only; access reviews, workforce risk CA, risky SPs need more. | D-02 widened (access-review population, P2 risk CA, Workload ID Premium). | Fixed
RV-16 | Identity & monitoring | ID-02 | High | Azure MFA Phase 2 enforced since postponement cap (1 Jul 2026); automation breaking now. | ID-02 moved to W0-W2 as Immediate action. | Fixed
RV-17 | Identity & monitoring | MR-03 / MR-07 | High | Splunk Add-on for AWS does not ingest Security Hub OCSF; Entra categories incomplete. | Use Splunk Add-on for AWS Security Hub (Splunkbase 8642) via EventBridge->HEC; full Entra category list. | Fixed
RV-18 | Identity & monitoring | Retention | High | Entra keeps sign-in/audit logs 30 days (P1/P2); External ID Basic 7 days; Graph activity not retained. | New MR-21 archive W0-W1 (Immediate); HD-22 immutable archive; retention schedule GC-26. | Fixed
RV-19 | Identity & monitoring | MR-02 | High | Falcon Complete operates inside Falcon, not Splunk; Splunk notables need a 24/7 owner. | D-03 requires a named 24/7 owner per alert source, SLAs and containment authority. | Fixed
RV-20 | Identity & monitoring | ID-13 | Medium | Step-up needs server-side enforcement. | Withdrawal API checks fresh auth_time bound to transaction; out-of-band confirmation + cool-down; pentest in MR-16. | Fixed
RV-21 | Identity & monitoring | ID-07 / ID-15 | Medium | EIP-4361 is Final; session-binding design missing. | Reference corrected; verifier API/custom OIDC IdP, nonce store, EIP-1271 added. | Fixed
RV-22 | Identity & monitoring | ID-11 / ID-09 | Medium | AWS has no native JIT; K09 counts Identity Center but PIM scoped to Entra/Azure. | New D-16 (PIM for Groups via SCIM vs alternative); ID-09 covers PIM for Groups; SCP blocks Identity Store writes. | Fixed
RV-23 | Identity & monitoring | MR-05 | Medium | No IR plan until W8; DORA timelines imprecise. | Interim runbook in MR-00; DORA wording: 4h after classification/24h from awareness, 72h after initial, 1 month after last intermediate. | Fixed
RV-24 | Identity & monitoring | K11-K13 | Medium | MTTD/MTTR clocks undefined; medians hide tails. | KPI definitions added; median + p90; new MTTA KPI (K13). | Fixed
RV-25 | Identity & monitoring | MR-04 | Medium | Detection-as-code was only a repo. | New MR-24 CI pipeline (contentctl) before wave 1. | Fixed
RV-26 | Identity & monitoring | Missing | High | Missing app consent governance, helpdesk fraud, B2C policy review, Splunk integrity, token theft, workforce ID Protection, SOAR identity lockdown. | Added ID-18, ID-19, ID-16, ID-17, MR-20; B2C review in ID-06; SOAR identities in MR-10. | Fixed
RV-27 | Identity & monitoring | R08 | Low | Splunk cost controls vague. | Volume sizing and filtering in MR-03; D-15. | Fixed
RV-28 | Blockchain | BC-10 / K14 | Critical | Admin keys below threshold and without timelock until W16 (Drift pattern). | New BC-22 interim multisig hardening W0-W2 (Immediate). | Fixed
RV-29 | Blockchain | BC-10 / BC-21 | Critical | Timelocking every role includes pause, conflicting with time-to-pause. | Role matrix: pause guardian lower threshold without timelock; canceller role; K15 measured per matrix row; BC-28 pause drill. | Fixed
RV-30 | Blockchain | BC-01 | High | VAT is 0.8 SOL burned per epoch; no fallback; first fee covers epoch 1065. | BC-01 corrected (per epoch, auto top-up, commission pass-through, re-delegation fallback, rewards 1065-1066). Re-verified on solana.com. | Fixed
RV-31 | Blockchain | MR-14 | High | Pre-Alpenglow metrics; lead CSO 0.3 FTE. | Lead DET with BSE/CSO support; metric definitions flagged to verify post-Alpenglow; commission/withdrawer/lockup alerts. | Fixed (metrics UNVERIFIED)
RV-32 | Blockchain | BC-02 | High | No handling of 0x00 credentials or provider-owned 0x01. | Added to BC-02; remediation via BC-19; EIP-7002 request alerts. | Fixed
RV-33 | Blockchain | BC-03 | High | Old Defender relayer addresses may still hold on-chain roles. | BC-03 lists and revokes role holders via multisig. | Fixed
RV-34 | Blockchain | BC-05 / BC-10 | High | Squads config authority and spending limits bypass proposals; IDL authority not inventoried. | Added to BC-05 inventory and BC-10/BC-13 (authorities to Vault). | Fixed
RV-35 | Blockchain | BC-15 / BC-16 | High | No nSLOC sizing; booked slot mismatch; timelock/guard work after freeze; Anchor migration never done. | nSLOC sizing in BC-05; freeze W15 after BC-10/BC-23; audit W16-W19 with parallel teams; new BC-23 Anchor 1.x migration. | Fixed
RV-36 | Blockchain | BC-10 | Medium | Safe 1.5.0 upgrade needs delegatecall that a guard would block; buggy guard can brick Safe. | Upgrade first, then guard; fork-tested; removable. | Fixed
RV-37 | Blockchain | BC-04 / BC-14 | Medium | Checklist covers only gas repricing; other Glamsterdam EIPs affect monitoring/exit SLA; Fusaka gas cap. | Checklist widened; EIP list to be verified against the Glamsterdam meta-EIP (reviewer-cited EIPs not independently verified). | Partially fixed (EIP list UNVERIFIED)
RV-38 | Blockchain | ID-10 | Medium | FIDO2 keys are not on-chain signers. | ID-10 admins only; signer hardware wallets in ID-00 + BC-11. | Fixed
RV-39 | Blockchain | BC-08 | Medium | Missing Solana account-validation checks and EVM storage-layout checks. | Added to BC-08 and BC-13. | Fixed
RV-40 | Blockchain | MR-13 | Medium | No privileged-event monitoring before W12 (Defender gone). | New BC-24 interim OZ Monitor W3-W5; MR-13 moved to W7-W9. | Fixed
RV-41 | Blockchain | BC-18 | Low | Safe Harbor chain coverage (Solana) unconfirmed. | Confirm with SEAL in D-09. | Fixed
RV-42 | Blockchain | Missing | High | Missing front-end/DNS integrity, deployer hygiene, immutability decision, pause drill, treasury hygiene, oracle risk, RPC security, MPC exit/co-signer, verified builds/IDL. | Added BC-25, BC-26, BC-28, BC-29, BC-30, BC-31; immutability in BC-10; MPC exit in GC-28; co-signer in BC-12; verified builds/IDL in BC-13. | Fixed
RV-43 | Governance/PMO | GC-15 / PM-13 | High | Type II window opened before the evergreen calendar was live; 'window open' not testable. | PM-13 moved to W14-W16; Type I as-of Sun 21 Mar 2027 and Type II from Mon 22 Mar 2027 (gap-free); G4 criteria: engagement letter with period dates + first in-period evidence. | Fixed
RV-44 | Governance/PMO | GC-15 | High | Annual/one-off controls occur before the period. | GC-07 agrees with CPA which pre-period runs are accepted; annual items repeat in BAU calendar. | Fixed
RV-45 | Governance/PMO | GC-01 / D-01 | High | Withdrawal flows suggest custody -> FinCEN MSB, state licensing, FTC Safeguards. | D-01 must answer custodial/MSB/states/Safeguards; assumption + R17; re-plan at G1 if yes. | Fixed (contingent)
RV-46 | Governance/PMO | GC-01 / PM-03 | High | Counsel booked too late; budget only at G1. | Counsel engaged W0 inside GC-01; new PM-02A interim budget W1. | Fixed
RV-47 | Governance/PMO | GC-12 | High | Risk/exception process started W14; no risk or fraud assessment. | GC-12 moved to W6-W7 (spreadsheet until platform); interim exception log in PM-07; new GC-17. | Fixed
RV-48 | Governance/PMO | MR-06 | High | RTO/RPO without BIA; no BCP. | New GC-18 BIA W4-W5 feeding MR-06; new GC-19 BCP + crisis comms. | Fixed
RV-49 | Governance/PMO | GC-05 | Medium | Control matrix started before scope decision. | GC-05 depends on GC-07 (W8-W11). | Fixed
RV-50 | Governance/PMO | GC-09/10/11 | Medium | Started in holiday freeze. | GC-09 W6-W9; GC-10/GC-11 W11. | Fixed
RV-51 | Governance/PMO | GC-10/11/13/07 | Medium | Independence: GRC operating HR controls; readiness consultant reviewing own design; CPA as support. | HR controls led by HRB; three separate firms (GRCC implements, RDA assesses readiness, CPA attests); CPA consulted only. | Fixed
RV-52 | Governance/PMO | GC-16 | Medium | IA reported to CEO (Steering chair); limited scope; no board oversight. | IA reports to Board/Audit Committee; covers 1st and 2nd line; new GC-20 board oversight. | Fixed
RV-53 | Governance/PMO | Roles | Medium | Lead-only cap ignores support load and PL forum load. | Added weighted-load rule (lead 1 + support 0.25 <= 4 x FTE); PMO coordinator; CSO raised to 1.0 FTE; supports trimmed; all roles pass. | Fixed
RV-54 | Governance/PMO | Forums | Low | Too many meetings for 5 FTE. | ARB inside the weekly CAB slot fortnightly; CUKC fortnightly + ad hoc. | Fixed
RV-55 | Governance/PMO | KPIs | Medium | No owners; denominators; medians; contractor KPI should be a KRI; no evidence timeliness. | Owners and definitions added; p90; KRIs tab section; K23-K25 added. | Fixed
RV-56 | Governance/PMO | Evergreen | Medium | No CAPA/management review; unlimited renewals; DR/pentest cadence too heavy. | New GC-21; one renewal max; pentest annual + after major change; full DR annual with quarterly automated restore tests. | Fixed
RV-57 | Governance/PMO | G2 / G3 | Medium | No GRC criteria in gates. | G2 includes GC-04/05/06/12; G3 includes GC-13. | Fixed
RV-58 | Governance/PMO | Missing | High | Missing GC-17..GC-31 items. | Added PM-02A, GC-17, GC-18, GC-19, GC-20, GC-21, GC-22, GC-23, GC-25, GC-26, GC-27, GC-28; VDP in BC-25; evidence calendar in PM-13; AML programme contingent on D-01. | Fixed / AML deferred (contingent)
RV-59 | Lead re-verification | BC-01 | Critical | Re-verified Alpenglow on solana.com: epoch 1064, ~15:00 UTC 21 Oct 2026; VAT 0.8 SOL per epoch burned; Agave-4.3.0-based clients only; Firedancer/Frankendancer unsupported during migration. | Plan text aligned. | Verified
RV-60 | Lead re-verification | HD-02 / HD-16B | Critical | Re-verified EKS calendar: 1.31 ext. EOS 26 Nov 2026; 1.32 ext. EOS 23 Mar 2027; 1.34 std. EOS 2 Dec 2026; 1.35 std. EOS 27 Mar 2027; auto-upgrade at end of extended support without notice or rollback; STANDARD policy auto-upgrades at end of standard support. | Deadlines and HD-16B hard stop aligned. | Verified
RV-61 | Lead re-verification | MR-21 | High | Re-verified Entra retention: sign-in/audit 30 days on P1/P2 (7 Free); Graph activity logs not retained unless exported; External ID Basic 7 days. | MR-21 kept as Immediate action. | Verified
RV-62 | Lead re-verification | Deferred | Low | Items not verifiable from public primary sources: CrowdStrike AL2023/Bottlerocket support (login-gated), Hexagate/Tenderly Solana coverage, SOC 2 minimum Type II period (AICPA FAQ login-gated), FIPS 206 status, Bottlerocket CIS reporting method, AWS Backup EKS support. | Kept as UNVERIFIED with written-confirmation or validation tasks (HD-05, BC-09, GC-07, HD-26, MR-06). | Deferred - validation tasks assigned
Summary
Critical | 7 |  | Cloud/OS & container | 11
High | 26 |  | Identity & monitoring | 16
Medium | 22 |  | Blockchain | 15
Low | 7 |  | Governance/PMO | 16
|  |  | Lead re-verification | 4
Not fully fixed | 7

## Sources
Sources - primary sources checked 19 Oct 2026 (status: Verified / Partial / Secondary / Vendor claim / UNVERIFIED)
# | Topic | Fact | Status | URL | Checked
1 | AWS - CIS | Latest CIS AWS Foundations Benchmark v7.1.0 | Verified | https://www.cisecurity.org/benchmark/amazon_web_services | 2026-10-19
2 | AWS - CIS | Security Hub CSPM automates CIS AWS Foundations v1.2.0, v1.4.0, v3.0.0, v5.0.0 | Verified | https://docs.aws.amazon.com/securityhub/latest/userguide/cis-aws-foundations-benchmark.html | 2026-10-19
3 | AWS - CIS | CIS Amazon Linux 2023 v1.0.0; CIS Amazon Linux 2 v4.0.0 | Verified | https://www.cisecurity.org/benchmark/amazon_linux | 2026-10-19
4 | AWS - CIS | CIS Kubernetes v2.1.0; CIS Amazon EKS v2.0.0; CIS EKS Auto Mode v1.0.0 | Verified | https://www.cisecurity.org/benchmark/kubernetes | 2026-10-19
5 | AWS - CIS | CIS Bottlerocket v1.0.0 | Verified | https://www.cisecurity.org/benchmark/bottlerocket | 2026-10-19
6 | Frameworks | CIS Controls v8.1 (Jun 2024) with governance function | Verified | https://www.cisecurity.org/controls | 2026-10-19
7 | AWS - lifecycle | Amazon Linux 2 end of support 2026-06-30; AL2023 supported to Jun 2029 | Verified | https://aws.amazon.com/amazon-linux-2/faqs/ | 2026-10-19
8 | AWS - lifecycle | EKS stopped publishing AL2 AMIs 2025-11-26; 1.32 is last version with AL2 AMIs | Verified | https://docs.aws.amazon.com/eks/latest/userguide/eks-ami-deprecation-faqs.html | 2026-10-19
9 | AWS - lifecycle | EKS version calendar (1.31 ext. EOS 2026-11-26; 1.32 ext. EOS 2027-03-23; 1.34 std. EOS 2026-12-02; 1.35 std. EOS 2027-03-27); auto-upgrade behaviour; upgradePolicy | Verified (lead re-check) | https://docs.aws.amazon.com/eks/latest/userguide/kubernetes-versions.html | 2026-10-19
10 | AWS - lifecycle | EKS pricing: standard $0.10, extended $0.60 per cluster-hour | Verified | https://aws.amazon.com/eks/pricing/ | 2026-10-19
11 | AWS - services | New AWS Security Hub GA 2025-12-02 (correlation, exposure, OCSF) | Verified | https://aws.amazon.com/blogs/aws/aws-security-hub-now-generally-available-with-near-real-time-analytics-and-risk-prioritization/ | 2026-10-19
12 | AWS - services | Security Hub CSPM posture checks (FSBP, CIS, PCI, NIST) | Verified | https://docs.aws.amazon.com/securityhub/latest/userguide/what-is-securityhub.html | 2026-10-19
13 | AWS - services | Security Hub per-resource pricing (unit rate inferred from examples) | Partial | https://aws.amazon.com/security-hub/pricing/ | 2026-10-19
14 | AWS - services | GuardDuty Runtime Monitoring: EKS on EC2, ECS (Fargate and EC2), EC2; not EKS on Fargate | Verified | https://docs.aws.amazon.com/guardduty/latest/ug/runtime-monitoring.html | 2026-10-19
15 | AWS - services | GuardDuty Runtime Monitoring OS/kernel prerequisites | Verified | https://docs.aws.amazon.com/guardduty/latest/ug/prereq-runtime-monitoring-cpu-os-kernel-support.html | 2026-10-19
16 | AWS - services | GuardDuty Extended Threat Detection | Verified | https://docs.aws.amazon.com/guardduty/latest/ug/guardduty-extended-threat-detection.html | 2026-10-19
17 | AWS - services | Inspector CIS scans prerequisites (SSM, instance profile with AmazonInspector2ManagedCisPolicy) | Verified | https://docs.aws.amazon.com/inspector/latest/user/scanning-cis.html | 2026-10-19
18 | AWS - services | Inspector CIS supported OS (AL2023 yes; AL2 and Bottlerocket no) | Verified | https://docs.aws.amazon.com/inspector/latest/user/supported.html | 2026-10-19
19 | AWS - services | Inspector Code Security launched 2025-06-17 | Verified | https://aws.amazon.com/about-aws/whats-new/2025/06/amazon-inspector-code-security-shift-security-development | 2026-10-19
20 | AWS - services | EKS Pod Identity limits (no Fargate, Windows, Outposts) | Verified | https://docs.aws.amazon.com/eks/latest/userguide/pod-identities.html | 2026-10-19
21 | AWS - services | EC2 declarative policies: 7 attributes; EBS default encryption not one | Verified | https://docs.aws.amazon.com/organizations/latest/userguide/orgs_manage_policies_declarative_syntax.html | 2026-10-19
22 | AWS - services | ECR managed signing (AWS Signer) launched 2025-11-21 | Verified | https://aws.amazon.com/about-aws/whats-new/2025/11/amazon-ecr-managed-container-image-signing | 2026-10-19
23 | AWS - services | ECR tag immutability exclusions 2025-07-23 | Verified | https://aws.amazon.com/about-aws/whats-new/2025/07/amazon-ecr-exceptions-tag-immutability/ | 2026-10-19
24 | AWS - services | IAM Access Analyzer internal access findings 2025-06-17 | Verified | https://aws.amazon.com/about-aws/whats-new/2025/06/iam-access-analyzer-aws-organization-access-resources | 2026-10-19
25 | AWS - services | Resource Control Policies launched 2024-11-13 | Verified | https://aws.amazon.com/about-aws/whats-new/2024/11/resource-control-policies-restrict-access-aws-resources | 2026-10-19
26 | AWS - services | Centralized root access management (Nov 2024) | Verified | https://aws.amazon.com/about-aws/whats-new/2024/11/manage-root-access-aws-identity-access-management/ | 2026-10-19
27 | AWS - services | AWS Backup direct backup to logically air-gapped vault 2025-11-17 | Verified | https://aws.amazon.com/about-aws/whats-new/2025/11/aws-backup-direct-to-logically-air-gapped-vault | 2026-10-19
28 | AWS - services | Control Tower 2026 release notes | Verified | https://docs.aws.amazon.com/controltower/latest/userguide/2026-all.html | 2026-10-19
29 | AWS - controls | Security Hub control reference (EC2.x, EKS.x, IAM.x, S3.x, etc. as cited) | Verified (titles via summariser) | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html (and per-service pages eks-, iam-, s3-, rds-controls.html etc.) | 2026-10-19
30 | Tooling | CrowdStrike Falcon cloud workload coverage (AL2023/Bottlerocket support UNVERIFIED - login-gated) | Partial | https://github.com/CrowdStrike/falcon-helm | 2026-10-19
31 | Tooling | Splunk Add-on for AWS v8.2.2 (2026-08-19) | Verified | https://splunkbase.splunk.com/app/1876/ | 2026-10-19
32 | Tooling | Splunk Add-on for AWS Security Hub (OCSF via EventBridge->HEC) | Verified (reviewer) | https://splunkbase.splunk.com/app/8642 | 2026-10-19
33 | Tooling | Splunk Add-on for Microsoft Cloud Services v6.3.3 | Verified | https://splunkbase.splunk.com/app/3110 | 2026-10-19
34 | Tooling | CrowdStrike Falcon Event Streams add-on v3.7.2 | Verified | https://splunkbase.splunk.com/app/5082/ | 2026-10-19
35 | Tooling | Splunk ES 8.7.1 release notes | Verified | https://help.splunk.com/en/splunk-enterprise-security-8/release-notes-and-resources | 2026-10-19
36 | Tooling | Splunk SOAR 8.7.0; Python 3.13 playbooks | Verified | https://help.splunk.com/en/splunk-soar/soar-on-premises/release-notes | 2026-10-19
37 | Tooling | Falcon Complete Next-Gen MDR | Verified | https://crowdstrike.com/services/endpoint-security/falcon-complete-next-gen-mdr/ | 2026-10-19
38 | Identity | Azure AD B2C end of sale 1 May 2025; supported to at least May 2030; P2 discontinued 15 Mar 2026 | Verified | https://learn.microsoft.com/azure/active-directory-b2c/faq | 2026-10-19
39 | Identity | External ID: no IEF custom policies; migration planning | Verified | https://learn.microsoft.com/en-us/entra/external-id/customers/plan-your-migration-from-b2c-to-external-id | 2026-10-19
40 | Identity | External ID supported features (no ID Protection / risk CA in external tenants) | Verified | https://learn.microsoft.com/en-us/entra/external-id/customers/concept-supported-features-customers | 2026-10-19
41 | Identity | External ID customer passkeys (CA cannot require) | Verified (GA status UNVERIFIED) | https://learn.microsoft.com/en-us/entra/external-id/customers/how-to-sign-in-with-passkey | 2026-10-19
42 | Identity | Entra licensing (CA P1; PIM/ID Protection P2; ID Governance) | Verified | https://learn.microsoft.com/et-ee/entra/fundamentals/licensing | 2026-10-19
43 | Identity | Mandatory Azure MFA phases; workload identities exempt | Verified | https://learn.microsoft.com/entra/identity/authentication/concept-mandatory-multifactor-authentication | 2026-10-19
44 | Identity | Emergency access (break-glass) guidance | Verified | https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/security-emergency-access | 2026-10-19
45 | Identity | Authentication strengths (phishing-resistant) | Verified | https://learn.microsoft.com/azure/active-directory/authentication/concept-authentication-strengths | 2026-10-19
46 | Identity | Entra log retention (30 days P1/P2; Graph activity must be exported) | Verified (lead re-check) | https://learn.microsoft.com/en-us/entra/identity/monitoring-health/reference-reports-data-retention | 2026-10-19
47 | Identity | Stream Entra logs to Event Hub | Verified | https://learn.microsoft.com/ms-my/entra/identity/monitoring-health/howto-stream-logs-to-event-hub | 2026-10-19
48 | Identity | B2C logs via Azure Lighthouse / Azure Monitor | Verified | https://learn.microsoft.com/el-gr/azure/active-directory-b2c/azure-monitor | 2026-10-19
49 | Identity | B2C claim resolvers (acr_values, max_age) for step-up | Verified (reviewer) | https://learn.microsoft.com/en-us/azure/active-directory-b2c/claim-resolver-overview | 2026-10-19
50 | Identity | IAM Identity Center with Entra (SAML+SCIM) limitations | Verified | https://docs.aws.amazon.com/singlesignon/latest/userguide/idp-microsoft-entra.html | 2026-10-19
51 | Identity | Microsoft Sentinel Azure-portal experience ends 31 Mar 2027 (not adopted here) | Verified | https://learn.microsoft.com/partner-center/announcements/2026-february | 2026-10-19
52 | Identity | EIP-4361 Sign-In with Ethereum (Final) | Verified (reviewer) | https://eips.ethereum.org/EIPS/eip-4361 | 2026-10-19
53 | Blockchain | Solana Alpenglow mainnet epoch 1064 (~21 Oct 2026 15:00 UTC); VAT 0.8 SOL per epoch; Agave-4.3.0-based clients only | Verified (lead re-check) | https://solana.com/upgrades/alpenglow | 2026-10-19
54 | Blockchain | Agave releases (v4.2.2 latest; v4.3.0 candidate) | Verified | https://github.com/anza-xyz/agave/releases | 2026-10-19
55 | Blockchain | Firedancer releases | Partial | https://github.com/firedancer-io/firedancer/releases | 2026-10-19
56 | Blockchain | Solana vote-account key model (withdrawer cold) | Verified | https://docs.anza.xyz/operations/guides/vote-accounts | 2026-10-19
57 | Blockchain | Solana stake and withdraw authorities | Verified | https://docs.anza.xyz/cli/examples/delegate-stake | 2026-10-19
58 | Blockchain | Pectra mainnet 7 May 2025 | Verified | https://blog.ethereum.org/2025/04/23/pectra-mainnet | 2026-10-19
59 | Blockchain | EIP-7002 execution-layer triggerable withdrawals | Verified | https://eips.ethereum.org/EIPS/eip-7002 | 2026-10-19
60 | Blockchain | EIP-7251 max effective balance 2048 ETH (0x02) | Verified | https://eips.ethereum.org/EIPS/eip-7251 | 2026-10-19
61 | Blockchain | EIP-7702 EOA code delegation (security considerations) | Verified | https://eips.ethereum.org/EIPS/eip-7702 | 2026-10-19
62 | Blockchain | Fusaka mainnet 3 Dec 2025 | Verified | https://blog.ethereum.org/2025/11/06/fusaka-mainnet-announcement | 2026-10-19
63 | Blockchain | Glamsterdam on Hoodi 26 Oct 2026; no mainnet date | Verified | https://blog.ethereum.org/2026/10/16/glamsterdam-hoodi-announcement | 2026-10-19
64 | Blockchain | Glamsterdam gas repricing testing guidance | Verified | https://blog.ethereum.org/2026/08/24/glamsterdam-repricing-testing | 2026-10-19
65 | Blockchain | EIP-3076 slashing protection interchange (Last Call) | Verified | https://eips.ethereum.org/EIPS/eip-3076 | 2026-10-19
66 | Blockchain | Safe smart account v1.5.0 | Partial (release year not shown) | https://github.com/safe-global/safe-smart-account/releases | 2026-10-19
67 | Blockchain | Squads v4 (audits, formal verification, time locks, spending limits) | Verified | https://github.com/Squads-Protocol/v4 | 2026-10-19
68 | Blockchain | solana-verify verified builds | Partial | https://github.com/Ellipsis-Labs/solana-verifiable-build/releases | 2026-10-19
69 | Blockchain | Trident fuzzer | Partial | https://github.com/Ackee-Blockchain/trident/releases | 2026-10-19
70 | Blockchain | Slither | Partial | https://github.com/crytic/slither/releases | 2026-10-19
71 | Blockchain | Aderyn v0.6.8 | Verified | https://github.com/Cyfrin/aderyn/releases | 2026-10-19
72 | Blockchain | Foundry v1.8.3 | Verified | https://github.com/foundry-rs/foundry/releases | 2026-10-19
73 | Blockchain | Anchor v1.2.1 (6 Oct 2026) | Verified | https://github.com/solana-foundation/anchor/releases | 2026-10-19
74 | Blockchain | OpenZeppelin Defender shut down 1 Jul 2026 | Verified | https://www.openzeppelin.com/news/doubling-down-on-open-source-and-phasing-out-defender | 2026-10-19
75 | Blockchain | OpenZeppelin Monitor (EVM, Stellar, Solana; AGPL-3.0) | Verified | https://github.com/OpenZeppelin/openzeppelin-monitor | 2026-10-19
76 | Blockchain | Hypernative Solana monitoring (vendor claim - confirm in writing) | Vendor claim | https://www.hypernative.io/blog/solana-network-and-projects-building-on-it-are-now-secured-by-hypernative | 2026-10-19
77 | Blockchain | Hexagate chain coverage (Solana not named) | Partial | https://www.chainalysis.com/product/hexagate/ | 2026-10-19
78 | Blockchain | BSSC standards (NOS, TIS, KMS, GSP) May 2025 | Verified (press release) | https://www.businesswire.com/news/home/20250513728554/en | 2026-10-19
79 | Blockchain | BSSC SCS, NOS v2, GSP update (14 May 2026) | Verified (press release) | https://www.businesswire.com/news/home/20260514859476/en/BSSC-Unveils-Smart-Contract-Security-Standard-and-Major-Updates-to-Core-Specifications | 2026-10-19
80 | Blockchain | CCSS v9.0 | Verified | https://cryptoconsortium.org/standards-2/ | 2026-10-19
81 | Blockchain | OWASP Smart Contract Top 10 (2026 edition) | Verified | https://scs.owasp.org/ | 2026-10-19
82 | Blockchain | OWASP SCSVS (incubator) | Partial | https://owasp.org/www-project-smart-contract-security-verification-standard/ | 2026-10-19
83 | Blockchain | SEAL Frameworks | Verified | https://frameworks.securityalliance.org/ | 2026-10-19
84 | Blockchain | SEAL 911 | Verified | https://securityalliance.org/our-work/seal-911 | 2026-10-19
85 | Blockchain | SEAL Safe Harbor | Verified | https://securityalliance.org/our-work/safe-harbor | 2026-10-19
86 | Blockchain | FBI attribution of Bybit $1.5B theft (Feb 2025) | Verified | https://www.fbi.gov/investigate/cyber/alerts/2025/north-korea-responsible-for-1-5-billion-bybit-hack | 2026-10-19
87 | Blockchain | Bybit technical analysis (signer UI compromise) | Secondary | https://nccgroup.com/sg/research-blog/in-depth-technical-analysis-of-the-bybit-hack | 2026-10-19
88 | Blockchain | Drift (Apr 2026) Squads 2-of-5 no timelock, durable nonce | Secondary | https://blocksec.com/blog/drift-protocol-incident-multisig-governance-compromise-via-durable-nonce-exploitation | 2026-10-19
89 | Crypto-agility | NIST FIPS 203/204/205 final (Aug 2024) | Verified | https://csrc.nist.gov/Projects/post-quantum-cryptography/publications | 2026-10-19
90 | Crypto-agility | NIST IR 8547 (initial public draft) transition timeline | Verified (draft) | https://nvlpubs.nist.gov/nistpubs/ir/2024/NIST.IR.8547.ipd.pdf | 2026-10-19
91 | Regulatory | MiCA Art 143 transitional measures (ended 1 Jul 2026 at latest) | Verified | https://www.esma.europa.eu/publications-and-data/interactive-single-rulebook/mica/article-143-transitional-measures | 2026-10-19
92 | Regulatory | MiCA Art 61 reverse solicitation | Verified | https://www.esma.europa.eu/publications-and-data/interactive-single-rulebook/mica/article-61-provision-crypto-asset-services | 2026-10-19
93 | Regulatory | ESMA reverse-solicitation guidelines | Verified | https://www.esma.europa.eu/sites/default/files/2025-02/ESMA35-1872330276-2030_Guidelines_on_reverse_solicitation_under_MiCA.pdf | 2026-10-19
94 | Regulatory | DORA scope Art 2(1)(f) CASPs authorised under MiCA; applies 17 Jan 2025 | Verified | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32022R2554 | 2026-10-19
95 | Regulatory | DORA incident reporting timelines (Del. Reg. 2025/301 Art 5) | Verified | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32025R0301 | 2026-10-19
96 | Regulatory | PCI DSS v4.0.1 future-dated requirements effective 31 Mar 2025 | Verified | https://blog.pcisecuritystandards.org/now-is-the-time-for-organizations-to-adopt-the-future-dated-requirements-of-pci-dss-v4-x | 2026-10-19
97 | Regulatory | PCI SAQ A update (Jan 2025) | Verified | https://blog.pcisecuritystandards.org/important-updates-announced-for-merchants-validating-to-self-assessment-questionnaire-a | 2026-10-19
98 | Regulatory | FinCEN CVC guidance (DApp operators as money transmitters) | Verified (reviewer) | https://www.fincen.gov/sites/default/files/2019-05/FinCEN%20Guidance%20CVC%20FINAL%20508.pdf | 2026-10-19
99 | Regulatory | OFAC sanctions compliance guidance for the virtual currency industry (Oct 2021) | Verified | https://ofac.treasury.gov/recent-actions/20211015 | 2026-10-19
100 | Regulatory | FTC Safeguards Rule notification requirement (May 2024) | Verified (reviewer) | https://www.ftc.gov/business-guidance/blog/2024/05/safeguards-rule-notification-requirement-now-effect | 2026-10-19
101 | Regulatory | CLARITY Act stalled in Senate (Sep 2026) | Secondary | https://www.orrick.com/en/Insights/2026/10/The-CLARITY-Act-Stalls-in-the-Senate-Whats-Next-for-Digital-Asset-Regulation | 2026-10-19
102 | Assurance | AICPA 2017 Trust Services Criteria (revised points of focus 2022) | Verified | https://www.aicpa-cima.com/resources/download/2017-trust-services-criteria-with-revised-points-of-focus-2022 | 2026-10-19
103 | Assurance | SOC 2 description criteria | Verified (reviewer) | https://www.aicpa-cima.com/resources/article/get-description-criteria-for-your-organizations-soc-2-r-report | 2026-10-19
104 | Assurance | SOC 2 Type II minimum period (AICPA FAQ login-gated) | UNVERIFIED | https://www.aicpa-cima.com/resources/article/read-the-latest-faqs-for-soc-2-r-and-soc-3-r-examinations | 2026-10-19
105 | Frameworks | NIST CSF 2.0 (26 Feb 2024) | Verified | https://www.nist.gov/news-events/news/2024/02/nist-releases-version-20-landmark-cybersecurity-framework | 2026-10-19
106 | Frameworks | NIST SP 800-61r3 (3 Apr 2025) | Verified | https://www.nist.gov/news-events/news/2025/04/nist-revises-sp-800-61-incident-response-recommendations-and-considerations | 2026-10-19
107 | Frameworks | NIST SSDF v1.1 final; v1.2 draft | Verified | https://csrc.nist.gov/pubs/sp/800/218/r1/ipd | 2026-10-19
108 | Frameworks | ISO/IEC 27001:2022 transition ended 31 Oct 2025 (IAF MD 26) | Verified | https://iaf.nu/iaf_system/uploads/documents/IAF_MD26_Issue_2_15012023.pdf | 2026-10-19
109 | Frameworks | ISO/IEC 27001:2022/Amd 1:2024 | Verified | https://www.iso.org/standard/88435.html | 2026-10-19
110 | GRC tooling | Vanta SOC 2 + Entra integration | Vendor | https://help.vanta.com/en/articles/11345655-connecting-vanta-microsoft-entra | 2026-10-19
111 | GRC tooling | Drata Microsoft 365 integration | Vendor | https://help.drata.com/en/articles/4797766-microsoft-365-integration-guide | 2026-10-19
112 | GRC tooling | Secureframe Entra ID integration | Vendor | https://support.secureframe.com/hc/en-us/articles/20710013602963-Microsoft-Entra-ID | 2026-10-19